## PMR
DEPARTMENT OF AGRICULTURE REGIONAL FIELD OFFICE 1 | [11 empty] | Procurement Monitoring Report as of July 14, 2025
[5 empty] | Actual Procurement Activities | [20 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column1 | Column2
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
-
DA-RFO-1-2025-GOODS-004-R | REBIDDING OF SUPPLY AND DELIVERY OF VARIOUS INORGANIC FERTILIZERS | HVCDP, SAAD, 4K, Livestock and Corn Program | Yes | Competitive Bidding | 2024-10-01 | January 22, 2025 - February 11, 2025 |  | JANUARY 30, 2025 (9:00 AM) |  | FEBRUARY 11, 2025 (9:00 AM) |  | 2025-02-14 | 2025-02-21 | 2025-03-12 |  |  |  | 2025-03-12 | 2025-03-17 | 2025-03-17 | 5 |  | ON-GOING DELIVERY |  | Government of the Philippines (current year's budget) | 60705800 |  |  | 51646750 |  |  | 0.14923 | 1.COA 2.RAFC 3.PCCI | JANUARY 30, 2025 (9:00 AM) |  | FEBRUARY 11, 2025 (9:00 AM) | 2025-02-14 | 2025-02-21 |  |  | FALSE | FALSE
DA-RFO-1-2025-GOODS-005 | SUPPLY AND DELIVERY OF VARIOUS VEGETABLE SEEDS | HVCDP, SAAD, 4K and Corn Program | Yes | Competitive Bidding | 2024-10-01 | November 7-27, 2024 |  | NOVEMBER 15, 2024 (1:00 PM) |  | NOVEMBER 27, 2024 (1:00 PM) |  | 2024-12-04 | 2024-12-12 | 2025-01-22 |  |  |  | 2025-01-23 | 2025-02-03 | 2025-02-03 |  |  | 2025-03-03 | 2025-04-07 | Government of the Philippines (current year's budget) | 32420355 |  |  | 11291465 |  |  |  | 1.COA 2.RAFC 3.PCCI | NOVEMBER 15, 2024 (1:00 PM) |  | NOVEMBER 27, 2024 (1:00 PM) | 2024-12-04 | 2024-12-12 | 2025-03-03
DA-RFO-1-2025-GOODS-005-R | REBIDDING OF SUPPLY AND DELIVERY OF VARIOUS VEGETABLE SEEDS | HVCDP, SAAD, 4K and Corn Program | Yes | Competitive Bidding | 2024-10-01 | January 8-28, 2025 |  | JANUARY 16, 2025 (9:00 AM) |  | JANUARY 28, 2025 (9:00 AM) |  | 2025-01-30 | FEBRUARY 3-4, 2025 | 2025-03-05 |  |  |  | 2025-03-05 | 2025-03-11 | 2025-03-11 |  |  | 2025-03-31 | 2025-04-15 | Government of the Philippines (current year's budget) | 20763655 |  |  | 9966231 |  |  |  | 1.COA 2.RAFC 3.PCCI | JANUARY 16, 2025 (9:00 AM) |  | JANUARY 28, 2025 (9:00 AM) | 2025-01-30 | FEBRUARY 3-4, 2025 | 2025-03-31
DA-RFO-1-2025-GOODS-005-R | REBIDDING OF SUPPLY AND DELIVERY OF VARIOUS VEGETABLE SEEDS | HVCDP, SAAD, 4K and Corn Program | Yes | Competitive Bidding | 2024-10-01 | January 8-28, 2025 |  | JANUARY 16, 2025 (9:00 AM) |  | JANUARY 28, 2025 (9:00 AM) |  | 2025-01-30 | 2025-01-30 | 2025-03-05 |  |  |  | 2025-03-05 | 2025-03-17 | 2025-03-17 |  |  | 2025-03-31 | 2025-06-03 | Government of the Philippines (current year's budget) |  |  |  | 10375195 |  |  |  | 1.COA 2.RAFC 3.PCCI | JANUARY 16, 2025 (9:00 AM) |  | JANUARY 28, 2025 (9:00 AM) | 2025-01-30 | 2025-01-30 | 2025-03-31
DA-RFO-1-2025-GOODS-006-R | REBIDDING OF SUPPLY AND DELIVERY OF EIGHTY THOUSAND (80,000) KILOGRAMS GARLIC PLANTING MATERIAL | HVCDP | Yes | Competitive Bidding | 2024-10-01 | December 5-26, 2024 |  | DECEMBER 12, 2024 (1:00 PM) |  | DECEMBER 26, 2024 (1:00 PM) |  | 2024-12-27 | 2025-01-02 | 2025-01-27 |  |  |  | 2025-01-27 | 2025-02-12 | 2025-02-12 |  |  | FOR DELIVERY (Last week of August 2025) |  | Government of the Philippines (current year's budget) | 20000000 |  |  | 14400000 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 12, 2024 (1:00 PM) |  | DECEMBER 26, 2024 (1:00 PM) | 2024-12-27 | 2025-01-02
DA-RFO-1-2025-GOODS-007 | SUPPLY AND DELIVERY OF ONE (1) UNIT MOTOR VEHICLE | AFD-GSS | Yes | Competitive Bidding | 2024-09-27 | November 13 2024 to December 2, 2024 |  | NOVEMBER 20, 2024 (9:00 AM) |  | DECEMBER 2, 2024 (9:00 AM) |  | 2024-12-09 | 2024-12-16 | 2025-01-21 |  |  |  | 2025-01-21 | 2025-02-10 | 2025-02-10 |  |  | 2025-06-13 | 2025-06-13 | Government of the Philippines (current year's budget) | 2400000 |  |  | 2350000 |  |  |  | 1.COA 2.RAFC 3.PCCI | NOVEMBER 20, 2024 (9:00 AM) |  | DECEMBER 2, 2024 (9:00 AM) | 2024-12-09 | 2024-12-16 | 2025-06-13
SUPPLY AND DELIVERY OF VARIOUS PUMP AND ENGINE SETS
DA-RFO-1-2025-GOODS-008 | LOT 1: SUPPLY AND DELIVERY OF ONE HUNDRED FIFTY-EIGHT (158) UNITS PUMP AND ENGINE SETS | Corn, HVCDP, AMIA OAP and Livestock | Yes | Competitive Bidding | 2024-10-07 | November 13 2024 to December 2, 2024 |  | NOVEMBER 20, 2024 (10:00 AM) |  | DECEMBER 2, 2024 (10:00 AM) |  | 2024-12-03 | 2024-12-19 | 2025-02-10 |  |  |  | 2025-02-10 | 2025-02-21 | 2025-02-21 |  |  | 2025-03-26 | 2025-05-06 | Government of the Philippines (current year's budget) | 15800000 |  |  | 15784200 |  |  |  | 1.COA 2.RAFC 3.PCCI | NOVEMBER 20, 2024 (10:00 AM) |  | DECEMBER 2, 2024 (10:00 AM) | 2024-12-03 | 2024-12-19 | 2025-03-26
DA-RFO-1-2025-GOODS-008 | LOT 2: SUPPLY AND DELIVERY OF ONE HUNDRED TWENTY (120) UNITS PUMP AND ENGINE SETS | Corn, HVCDP, AMIA OAP and Livestock | Yes | Competitive Bidding | 2024-10-07 | November 13 2024 to December 2, 2024 |  | NOVEMBER 20, 2024 (10:00 AM) |  | DECEMBER 2, 2024 (10:00 AM) |  | 2024-12-03 | 22-24-Jan-25 | 2025-02-14 |  |  |  | 2025-02-14 | 2025-02-28 | 2025-02-28 |  |  | 2025-03-27 | 2025-04-03 | Government of the Philippines (current year's budget) | 12000000 |  |  | 11988000 |  |  |  | 1.COA 2.RAFC 3.PCCI | NOVEMBER 20, 2024 (10:00 AM) |  | DECEMBER 2, 2024 (10:00 AM) | 2024-12-03 | 22-24-Jan-25 | 2025-03-27
SUPPLY AND DELIVERY OF OPV WHITE CORN SEEDS - GLUTINOUS
DA-RFO-1-2025-GOODS-009-R | REBIDDING OF LOT 1: SUPPLY AND DELIVERY OF FOUR HUNDRED (400) BAGS OPV WHITE CORN SEEDS - GLUTINOUS FOR PANGASINAN | CORN | Yes | Competitive Bidding | 2024-10-01 | December 13- 2024 to January 7, 2025 |  | DECEMBER 20, 2024 (1:00 PM) |  | JANUARY 21, 2025 (11:00 AM) |  | 2025-01-24 | 2025-01-30 | 2025-02-19 |  |  |  | 2025-02-20 | 2025-03-10 | 2025-03-10 |  |  | 27-May-2025 (First delivery- 200 bags; schedule of 2nd delivery is on 1-15 August 2025) | 2025-06-10 | Government of the Philippines (current year's budget) | 1008000 |  |  | 1006000 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 20, 2024 (1:00 PM) |  | JANUARY 21, 2025 (11:00 AM) | 2025-01-24 | 2025-01-30 | 27-May-2025 (First delivery- 200 bags; schedule of 2nd delivery is on 1-15 August 2025)
DA-RFO-1-2025-GOODS-009-R | REBIDDING OF LOT 2: SUPPLY AND DELIVERY OF ONE HUNDRED FIFTY (150) BAGS OPV WHITE CORN SEEDS - GLUTINOUS FOR LA UNION | CORN | Yes | Competitive Bidding | 2024-10-01 | December 13- 2024 to January 7, 2025 |  | DECEMBER 20, 2024 (1:00 PM) |  | JANUARY 21, 2025 (11:00 AM) |  | 2025-01-24 | 2025-01-27 | 2025-02-19 |  |  |  | 2025-02-20 | 2025-03-10 | 2025-03-10 |  |  | 15-May-2025 (First delivery- 50 bags; schedule of 2nd delivery is on 1-15 August 2025) | 2025-05-27 | Government of the Philippines (current year's budget) | 378000 |  |  | 378000 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 20, 2024 (1:00 PM) |  | JANUARY 21, 2025 (11:00 AM) | 2025-01-24 | 2025-01-27 | 15-May-2025 (First delivery- 50 bags; schedule of 2nd delivery is on 1-15 August 2025)
DA-RFO-1-2025-GOODS-009-R | REBIDDING OF LOT 3: SUPPLY AND DELIVERY OF TWO HUNDRED SEVENTY-FIVE (275) BAGS OPV WHITE CORN SEEDS - GLUTINOUS FOR ILOCOS SUR | CORN | Yes | Competitive Bidding | 2024-10-01 | December 13- 2024 to January 7, 2025 |  | DECEMBER 20, 2024 (1:00 PM) |  | JANUARY 21, 2025 (11:00 AM) |  | 2025-01-24 | 2025-01-27 | 2025-02-19 |  |  |  | 2025-02-19 | 2025-03-10 | 2025-03-10 |  |  | 14-May-2025 (First delivery- 125 bags; schedule of 2nd delivery is on 1-15 August 2025) | 2025-06-05 | Government of the Philippines (current year's budget) | 693000 |  |  | 693000 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 20, 2024 (1:00 PM) |  | JANUARY 21, 2025 (11:00 AM) | 2025-01-24 | 2025-01-27 | 14-May-2025 (First delivery- 125 bags; schedule of 2nd delivery is on 1-15 August 2025)
DA-RFO-1-2025-GOODS-009-R | REBIDDING OF LOT 4: SUPPLY AND DELIVERY OF TWO HUNDRED SEVENTY-FIVE (275) BAGS OPV WHITE CORN SEEDS - GLUTINOUS FOR ILOCOS NORTE | CORN | Yes | Competitive Bidding | 2024-10-01 | December 13- 2024 to January 7, 2025 |  | DECEMBER 20, 2024 (1:00 PM) |  | JANUARY 21, 2025 (11:00 AM) |  | 2025-01-24 | 2025-01-27 | 2025-02-19 |  |  |  | 2025-02-20 | 2025-03-10 | 2025-03-10 |  |  | 15-May-2025 (First delivery- 125 bags; schedule of 2nd delivery is on 1-15 August 2025) | 2025-06-05 | Government of the Philippines (current year's budget) | 693000 |  |  | 693000 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 20, 2024 (1:00 PM) |  | JANUARY 21, 2025 (11:00 AM) | 2025-01-24 | 2025-01-27 | 15-May-2025 (First delivery- 125 bags; schedule of 2nd delivery is on 1-15 August 2025)
DA-RFO 1-2025-GOODS-010 | SUPPLY AND DELIVERY OF FOUR (4) UNITS RICE TRANSPLANTER (RIDING TYPE) | RICE | Yes | Competitive Bidding | 2024-10-07 | November 14 2024 to December 3, 2024 |  | NOVEMBER 21, 2024 (9:00 AM) |  | DECEMBER 3, 2024 (9:00 AM) |  | 2024-12-10 | 2025-01-08 | 2025-02-03 |  |  |  | 2025-02-03 | 2025-02-14 | 2025-02-14 |  |  | 2025-03-11 | 2025-05-02 | Government of the Philippines (current year's budget) | 6400000 |  |  | 6380000 |  |  |  | 1.COA 2.RAFC 3.PCCI | NOVEMBER 21, 2024 (9:00 AM) |  | DECEMBER 3, 2024 (9:00 AM) | 2024-12-10 | 2025-01-08 | 2025-03-11
DA-RFO 1-2025-GOODS-011 | SUPPLY AND DELIVERY OF FOUR (4) UNITS SINGLE PASS RICE MILL (TRAILER TYPE) | RICE | Yes | Competitive Bidding | 2024-10-07 | November 14 2024 to December 3, 2024 |  | NOVEMBER 21, 2024 (10:00 AM) |  | DECEMBER 3, 2024 (10:00 AM) |  | 2024-12-10 | 2025-01-08 | 2025-02-03 |  |  |  | 2025-02-03 | 2025-02-14 | 2025-02-14 |  |  | 2025-04-07 | DELIVERED | Government of the Philippines (current year's budget) | 5400000 |  |  | 5380000 |  |  |  | 1.COA 2.RAFC 3.PCCI | NOVEMBER 21, 2024 (10:00 AM) |  | DECEMBER 3, 2024 (10:00 AM) | 2024-12-10 | 2025-01-08 | 2025-04-07
DA-RFO 1-2025-GOODS-012 | SUPPLY AND DELIVERY OF SIXTEEN (16) UNITS HAND TRACTOR WITH ACCESSORIES | LIVESTOCK & RICE | Yes | Competitive Bidding | 2024-10-07 | November 14 2024 to December 3, 2024 |  | NOVEMBER 21, 2024 (11:00 AM) |  | DECEMBER 3, 2024 (11:00 AM) |  | 2024-12-10 | 2025-01-07 | 2025-02-03 |  |  |  | 2025-02-03 | 2025-02-14 | 2025-02-14 |  |  | 2025-03-03 | 2025-03-21 | Government of the Philippines (current year's budget) | 3120000 |  |  | 3109120 |  |  |  | 1.COA 2.RAFC 3.PCCI | NOVEMBER 21, 2024 (11:00 AM) |  | DECEMBER 3, 2024 (11:00 AM) | 2024-12-10 | 2025-01-07 | 2025-03-03
DA-RFO 1-2025-GOODS-013 | SUPPLY AND DELIVERY OF SIXTEEN (16) UNITS MULTI-PURPOSE CULTIVATOR | HVCDP | Yes | Competitive Bidding | 2024-10-07 | November 21, 2024 to December 10, 2024 |  | NOVEMBER 28, 2024 (10:00 AM) |  | DECEMBER 10, 2024 (10:00 AM) |  | 2024-12-17 | 22-24-Jan-2025 | 2025-02-14 |  |  |  | 2025-02-14 | 2025-02-21 | 2025-02-21 |  |  | 2025-03-13 | 2025-03-26 | Government of the Philippines (current year's budget) | 4800000 |  |  | 4799848 |  |  |  | 1.COA 2.RAFC 3.PCCI | NOVEMBER 28, 2024 (10:00 AM) |  | DECEMBER 10, 2024 (10:00 AM) | 2024-12-17 | 22-24-Jan-2025 | 2025-03-13
DA-RFO 1-2025-GOODS-014 | SUPPLY AND DELIVERY OF TWO (2) UNITS RECIRCULATING DRYER | CORN | Yes | Competitive Bidding | 2024-10-07 | November 21, 2024 to December 10, 2024 |  | NOVEMBER 28, 2024 (11:00 AM) |  | DECEMBER 10, 2024 (11:00 AM) |  | 2024-12-17 | 2025-01-09 | 2025-02-03 |  |  |  | 2025-02-03 | 2025-02-14 | 2025-02-14 |  |  | 2025-05-18 | 2025-05-22 | Government of the Philippines (current year's budget) | 6000000 |  |  | 5900000 |  |  |  | 1.COA 2.RAFC 3.PCCI | NOVEMBER 28, 2024 (11:00 AM) |  | DECEMBER 10, 2024 (11:00 AM) | 2024-12-17 | 2025-01-09 | 2025-05-18
SUPPLY AND DELIVERY OF FOUR UNITS (4) HAMMER MILL AND FOUR (4) UNITS CORN SHELLER
DA-RFO-1-2025-GOODS-015 | LOT 1: SUPPLY AND DELIVERY OF FOUR (4) UNITS HAMMER MILL | HVCDP, NUPAP, Corn, 4K Program, AMIA, OAP & Livestock | Yes | Competitive Bidding | 2024-10-07 | November 21, 2024 to December 10, 2024 |  | NOVEMBER 28, 2024 (1:00 PM) |  | DECEMBER 10, 2024 (1:00 PM) |  | 2024-12-17 | 2025-01-09 | 2025-02-03 |  |  |  | 2025-02-03 | 2025-02-12 | 2025-02-12 |  |  | 2025-02-27 | 2025-03-20 | Government of the Philippines (current year's budget) | 1060000 |  |  | 963200 |  |  |  | 1.COA 2.RAFC 3.PCCI | NOVEMBER 28, 2024 (1:00 PM) |  | DECEMBER 10, 2024 (1:00 PM) | 2024-12-17 | 2025-01-09 | 2025-02-27
DA-RFO-1-2025-GOODS-015 | LOT 2: SUPPLY AND DELIVERY OF FOUR (4) UNITS CORN SHELLER | HVCDP, NUPAP, Corn, 4K Program, AMIA, OAP & Livestock | Yes | Competitive Bidding | 2024-10-07 | November 21, 2024 to December 10, 2024 |  | NOVEMBER 28, 2024 (1:00 PM) |  | DECEMBER 10, 2024 (1:00 PM) |  | 2024-12-17 | JANUARY 8-9, 2025 | 2025-02-10 |  |  |  | 2025-02-10 | 2025-02-24 | 2025-02-24 |  |  | 2025-03-27 | 2025-05-09 | Government of the Philippines (current year's budget) | 1400000 |  |  | 1399992 |  |  |  | 1.COA 2.RAFC 3.PCCI | NOVEMBER 28, 2024 (1:00 PM) |  | DECEMBER 10, 2024 (1:00 PM) | 2024-12-17 | JANUARY 8-9, 2025 | 2025-03-27
DA-RFO-1-2025-GOODS-016 | SUPPLY AND DELIVERY OF TWENTY-NINE THOUSAND EIGHT HUNDRED (29,800) KILOGRAMS MOLASSES | OAP, AMIA and Livestock | Yes | Competitive Bidding | 2024-10-07 | November 27, 2024 to December 19, 2024 |  | DECEMBER 4, 2024 (11:00 AM) |  | DECEMBER 27, 2024 (10:00 AM) |  | 2025-01-03 | 2025-01-15 | 2025-02-10 |  |  |  | 2025-02-10 | 2025-02-21 | 2025-02-21 |  |  | DELIVERED | PAID | Government of the Philippines (current year's budget) | 1,192,000.00) |  |  | 1124950 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 4, 2024 (11:00 AM) |  | DECEMBER 27, 2024 (10:00 AM) | 2025-01-03 | 2025-01-15 | DELIVERED
DA-RFO 1-2025-GOODS-017-R | REBIDDING OF SUPPLY AND DELIVERY OF THIRTY-SEVEN (37) UNITS MOBILE SOLAR-POWERED IRRIGATION SYSTEM | OAP, AMIA, Corn, SAAD and 4K Program | Yes | Competitive Bidding | 2024-10-07 | January 30, 2025 - February 18, 2025 |  | FEBRUARY 10, 2025 (2:00 PM) |  | FEBRUARY 24, 2025 (2:00 PM) |  | 2025-02-26 | 2025-03-06 | 2025-03-26 |  |  |  | 2025-03-27 | 2025-03-28 | 2025-03-28 |  |  | DELIVERED | FOR CONDUCT OF DURABILITY TEST ON JULY 15, 2025 | Government of the Philippines (current year's budget) | 14800000 |  |  | 10286000 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 10, 2025 (2:00 PM) |  | FEBRUARY 24, 2025 (2:00 PM) | 2025-02-26 | 2025-03-06 | DELIVERED
DA-RFO 1-2025-GOODS-018-R | REBIDDING OF SUPPLY AND DELIVERY OF VARIOUS SEEDLINGS | HVCDP and 4KProgram | Yes | Competitive Bidding | 2024-10-01 | January 8-28, 2025 |  | JANUARY 16, 2025 (10:00 AM) |  | JANUARY 28, 2025 (10:00 AM) |  | 2025-01-30 | 2025-02-03 | 2025-02-20 |  |  |  | 2025-02-21 | 2025-03-17 | 2025-03-17 |  |  | 2025-05-19 | 2025-06-02 | Government of the Philippines (current year's budget) | 6966250 |  |  | 3364000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JANUARY 16, 2025 (10:00 AM) |  | JANUARY 28, 2025 (10:00 AM) | 2025-01-30 | 2025-02-03 | 2025-05-19
SUPPLY AND DELIVERY OF VARIOUS PESTICIDES
DA-RFO-1-2025-GOODS-019 | LOT 1: SUPPLY AND DELIVERY OF TWO THOUSAND FORTY-FIVE (2,045) BOTTLES BOTANICAL PESTICIDES | HVCDP, NUPAP, SAAD and 4K Program | Yes | Competitive Bidding | 2024-10-01 | November 28, 2024 to December 19, 2024 |  | DECEMBER 5, 2024 (10:00 AM) |  | DECEMBER 19, 2024 (10:00 AM) |  | 2024-12-26 | 2025-01-03 | 2025-01-27 |  |  |  | 2025-01-27 | 2025-02-12 | 2025-02-12 |  |  | 2025-03-07 | 2025-03-27 | Government of the Philippines (current year's budget) | 2454000 |  |  | 2454000 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 5, 2024 (10:00 AM) |  | DECEMBER 19, 2024 (10:00 AM) | 2024-12-26 | 2025-01-03 | 2025-03-07
DA-RFO-1-2025-GOODS-019 | LOT 2: SUPPLY AND DELIVERY OF FOUR THOUSAND (4,000) PACKS FUNGICIDE | HVCDP, NUPAP, SAAD and 4K Program | Yes | Competitive Bidding | 2024-10-01 | November 28, 2024 to December 19, 2024 |  | DECEMBER 5, 2024 (10:00 AM) |  | DECEMBER 19, 2024 (10:00 AM) |  | 2024-12-26 | 2025-01-06 | 2025-01-27 |  |  |  | 2025-01-27 | 2025-02-06 | 2025-02-06 |  |  | 2025-02-20 | 2025-03-11 | Government of the Philippines (current year's budget) | 2000000 |  |  | 1960000 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 5, 2024 (10:00 AM) |  | DECEMBER 19, 2024 (10:00 AM) | 2024-12-26 | 2025-01-06 | 2025-02-20
DA-RFO-1-2025-GOODS-019 | LOT 3: SUPPLY AND DELIVERY OF ONE THOUSAND TWO HUNDRED (1,200) BOTTLES INSECTICIDES | HVCDP, NUPAP, SAAD and 4K Program | Yes | Competitive Bidding | 2024-10-01 | November 28, 2024 to December 19, 2024 |  | DECEMBER 5, 2024 (10:00 AM) |  | DECEMBER 19, 2024 (10:00 AM) |  | 2024-12-26 | JAN 2-3, 2025 | 2025-01-27 |  |  |  | 2025-01-27 | 2025-02-12 | 2025-02-12 |  |  | 2025-02-20 | 2025-03-11 | Government of the Philippines (current year's budget) | 1200000 |  |  | 1200000 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 5, 2024 (10:00 AM) |  | DECEMBER 19, 2024 (10:00 AM) | 2024-12-26 | JAN 2-3, 2025 | 2025-02-20
SUPPLY AND DELIVERY OF VARIOUS FOLIAR FERTILIZERS
DA-RFO-1-2025-GOODS-020 | LOT 1: SUPPLY AND DELIVERY OF ONE THOUSAND SIX HUNDRED THIRTY-FIVE (1,635) PACKS FOLIAR FERTILIZER | HVCDP, NUPAP, Corn, SAAD and 4K Program | Yes | Competitive Bidding | 2024-10-01 | November 28, 2024 to December 19, 2024 |  | DECEMBER 5, 2024 (11:00 AM) |  | DECEMBER 19, 2024 (11:00 AM) |  | 2024-12-26 | 2025-01-02 | 2025-01-21 |  |  |  | 2025-01-21 | 2025-02-03 | 2025-02-03 |  |  | 2025-02-20 | 2025-03-11 | Government of the Philippines (current year's budget) | 1880250 |  |  | 1880250 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 5, 2024 (11:00 AM) |  | DECEMBER 19, 2024 (11:00 AM) | 2024-12-26 | 2025-01-02 | 2025-02-20
DA-RFO-1-2025-GOODS-020 | LOT 2: SUPPLY AND DELIVERY OF FIVE THOUSAND FORTY (5,040) PACKS ORGANIC FOLIAR FERTILIZER | HVCDP, NUPAP, Corn, SAAD and 4K Program | Yes | Competitive Bidding | 2024-10-01 | November 28, 2024 to December 19, 2024 |  | DECEMBER 5, 2024 (11:00 AM) |  | DECEMBER 19, 2024 (11:00 AM) |  | 2024-12-26 | JAN 2-3, 2025 | 2025-01-21 |  |  |  | 2025-01-21 | 2025-02-03 | 2025-02-03 |  |  | 2025-02-20 | 2025-03-11 | Government of the Philippines (current year's budget) | 5040000 |  |  | 5040000 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 5, 2024 (11:00 AM) |  | DECEMBER 19, 2024 (11:00 AM) | 2024-12-26 | JAN 2-3, 2025 | 2025-02-20
DA-RFO-1-2025-GOODS-020-R | REBIDDING OF LOT 3: SUPPLY AND DELIVERY OF ONE THOUSAND FOUR HUNDRED NINETY-SEVEN (1,497) BOTTLES LIQUID FERTILIZER | HVCDP, NUPAP, Corn, SAAD and 4K Program | Yes | Competitive Bidding | 2024-10-01 | November 28, 2024 to December 19, 2024 |  | JANUARY 16, 2025 (11:00 AM) |  | JANUARY 28, 2025 (11:00 AM) |  | 2025-01-30 | FEB. 3-4, 2025 | 2025-02-25 |  |  |  | 2025-03-03 | 2025-03-17 | 2025-03-17 |  |  | 2025-04-02 | 2025-05-30 | Government of the Philippines (current year's budget) | 1197600 |  |  | 1194606 |  |  |  | 1.COA 2.RAFC 3.PCCI | JANUARY 16, 2025 (11:00 AM) |  | JANUARY 28, 2025 (11:00 AM) | 2025-01-30 | FEB. 3-4, 2025 | 2025-04-02
DA-RFO-1-2025-GOODS-020 | LOT 4: SUPPLY AND DELIVERY OF ONE THOUSAND SEVEN HUNDRED TEN (1,710) PACKS FOLIAR FERTILIZER | HVCDP, NUPAP, Corn, SAAD and 4K Program | Yes | Competitive Bidding | 2024-10-01 | November 28, 2024 to December 19, 2024 |  | DECEMBER 5, 2024 (11:00 AM) |  | DECEMBER 19, 2024 (11:00 AM) |  | 2024-12-26 | 2025-01-07 | 2025-01-21 |  |  |  | 2025-01-21 | 2025-02-03 | 2025-02-03 |  |  | 2025-02-26 | 2025-03-11 | Government of the Philippines (current year's budget) | 2565000 |  |  | 2564145 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 5, 2024 (11:00 AM) |  | DECEMBER 19, 2024 (11:00 AM) | 2024-12-26 | 2025-01-07 | 2025-02-26
DA-RFO-1-2025-GOODS-020-R | REBIDDING OF LOT 5: SUPPLY AND DELIVERY OF TWO THOUSAND SIX HUNDRED NINETY-EIGHT (2,698) BOTTLES FOLIAR FERTILIZER | HVCDP, NUPAP, Corn, SAAD and 4K Program | Yes | Competitive Bidding | 2024-10-01 | November 28, 2024 to December 19, 2024 |  | JANUARY 16, 2025 (11:00 AM) |  | JANUARY 28, 2025 (11:00 AM) |  | 2025-01-30 | 2025-02-03 | 2025-02-25 |  |  |  | 2025-03-03 | 2025-03-11 | 2025-03-11 |  |  | 2025-04-02 | 2025-05-30 | Government of the Philippines (current year's budget) | 2158400 |  |  | 2158400 |  |  |  | 1.COA 2.RAFC 3.PCCI | JANUARY 16, 2025 (11:00 AM) |  | JANUARY 28, 2025 (11:00 AM) | 2025-01-30 | 2025-02-03 | 2025-04-02
DA-RFO 1-2025-GOODS-021 | SUPPLY AND DELIVERY OF SIX HUNDRED THIRTY-ONE (631) UNITS KNAPSACK SPRAYER | HVCDP | Yes | Competitive Bidding | N/A | November 28, 2024 to December 19, 2024 |  | DECEMBER 5, 2024 (1:00 PM) |  | DECEMBER 19, 2024 (1:00 PM) |  | 2024-12-26 | 2025-01-07 | 2025-01-21 |  |  |  | 2025-01-21 | 2025-02-06 | 2025-02-06 |  |  | 2025-03-07 | 2025-04-24 | Government of the Philippines (current year's budget) | 1262000 |  |  | 933880 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 5, 2024 (1:00 PM) |  | DECEMBER 19, 2024 (1:00 PM) | 2024-12-26 | 2025-01-07 | 2025-03-07
SUPPLY AND DELIVERY OF VARIOUS PLASTIC CRATES AND PALLETS
DA-RFO-1-2025-GOODS-022 | LOT 1: SUPPLY AND DELIVERY OF FIVE THOUSAND THREE HUNDRED FIFTY-SEVEN (5,357) PIECES PLASTIC CRATES | HVCDP, NUPAP, Corn, 4K Program, AMIA, OAP & Livestock | Yes | Competitive Bidding | 2024-10-07 | November 28, 2024 to December 19, 2024 |  | DECEMBER 5, 2024 (2:00 PM) |  | DECEMBER 19, 2024 (2:00 PM) |  | 2024-12-26 | 2025-01-06 | 2025-01-27 |  |  |  | 2025-01-27 | 2025-02-14 | 2025-02-14 |  |  | 2025-03-14 | 2025-04-24 | Government of the Philippines (current year's budget) | 2946350 |  |  | 2945278.6 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 5, 2024 (2:00 PM) |  | DECEMBER 19, 2024 (2:00 PM) | 2024-12-26 | 2025-01-06 | 2025-03-14
DA-RFO-1-2025-GOODS-022 | LOT 2: SUPPLY AND DELIVERY OF ONE THOUSAND TWO HUNDRED SIXTY (1,260) PIECES PLASTIC CRATES | HVCDP, NUPAP, Corn, 4K Program, AMIA, OAP & Livestock | Yes | Competitive Bidding | 2024-10-07 | November 28, 2024 to December 19, 2024 |  | DECEMBER 5, 2024 (2:00 PM) |  | DECEMBER 19, 2024 (2:00 PM) |  | 2024-12-26 | 2025-01-06 | 2025-01-27 |  |  |  | 2025-01-28 | 2025-02-14 | 2025-02-14 |  |  | 2025-03-11 | 2025-04-24 | Government of the Philippines (current year's budget) | 478800 |  |  | 478548 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 5, 2024 (2:00 PM) |  | DECEMBER 19, 2024 (2:00 PM) | 2024-12-26 | 2025-01-06 | 2025-03-11
DA-RFO-1-2025-GOODS-022 | LOT 3: SUPPLY AND DELIVERY OF THREE HUNDRED TWENTY (320) PIECES PALLETS | HVCDP, NUPAP, Corn, 4K Program, AMIA, OAP & Livestock | Yes | Competitive Bidding | 2024-10-07 | November 28, 2024 to December 19, 2024 |  | DECEMBER 5, 2024 (2:00 PM) |  | DECEMBER 19, 2024 (2:00 PM) |  | 2024-12-26 | 2025-01-06 | 2025-01-27 |  |  |  | 2025-01-28 | 2025-02-14 | 2025-02-14 |  |  | 2025-03-11 | 2025-04-24 | Government of the Philippines (current year's budget) | 1600000 |  |  | 1599360 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 5, 2024 (2:00 PM) |  | DECEMBER 19, 2024 (2:00 PM) | 2024-12-26 | 2025-01-06 | 2025-03-11
DA-RFO 1-2025-GOODS-023 | SUPPLY AND DELIVERY OF TWO THOUSAND NINETY-ONE (2,091) PIECES PLASTIC DRUM WITH COVER | OAP, SAAD, 4K AMIA and Livestock Program | Yes | Competitive Bidding | 2024-10-07 | November 28, 2024 to December 19, 2024 |  | DECEMBER 5, 2024 (3:00 PM) |  | DECEMBER 19, 2024 (3:00 PM) |  | 2024-12-26 | 2025-01-20 | 2025-02-12 |  |  |  | 2025-02-12 | 2025-03-03 | 2025-03-03 |  |  | March 10-April 3, 2025 | April 3, May 9, 20, 21 & 29, 2025 | Government of the Philippines (current year's budget) | 4182000 |  |  | 3134409 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 5, 2024 (3:00 PM) |  | DECEMBER 19, 2024 (3:00 PM) | 2024-12-26 | 2025-01-20 | March 10-April 3, 2025
DA-RFO 1-2025-GOODS-024 | SUPPLY AND DELIVERY OF VARIOUS GARDEN TOOLS AND FARM SUPPLIES | HVCDP, 4K Program, AMIA & NUPAP | Yes | Competitive Bidding | 2024-10-07 | December 5-26, 2024 |  | DECEMBER 12, 2024 (9:00 AM) |  | DECEMBER 26, 2024 (9:00 AM) |  | 2025-01-02 | 2025-01-14 | 10-Feb-2025 |  |  |  | 2025-02-12 | 2025-03-03 | 2025-03-03 |  |  | 2025-06-02 | 2025-06-11 | Government of the Philippines (current year's budget) | 5300055 |  |  | 4040880 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 12, 2024 (9:00 AM) |  | DECEMBER 26, 2024 (9:00 AM) | 2025-01-02 | 2025-01-14 | 2025-06-02
DA-RFO 1-2025-GOODS-024-R | REBIDDING OF SUPPLY AND DELIVERY OF VARIOUS GARDEN TOOLS AND FARM SUPPLIES | HVCDP & NUPAP | No | Competitive Bidding | 2024-10-07 | January 30, 2025 - February 18, 2025 |  | FEBRUARY 6, 2025 (11:00 AM) |  | FEBRUARY 24, 2025 (11:00 AM) |  | 2025-03-03 | 2025-03-28 | 2025-04-10 |  |  |  | 2025-04-11 | 2025-04-25 | 2025-04-25 |  |  | 2025-06-23 |  | Government of the Philippines (current year's budget) | 1190000 |  |  | 878730 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 6, 2025 (11:00 AM) |  | FEBRUARY 24, 2025 (11:00 AM) | 2025-03-03 | 2025-03-28 | 2025-06-23
DA-RFO 1-2025-GOODS-025-R | REBIDDING OF SUPPLY AND DELIVERY OF VARIOUS HDPE PIPES AND GARDEN HOSE | SAAD Program, 4K Program and AMIA Program | Yes | Competitive Bidding | 2024-10-07 | January 7-27, 2025 |  | JANUARY 14, 2025 (10:00 AM) |  | JANUARY 27, 2025 (10:00 AM) |  | 2025-02-03 | 2025-02-14 | 2025-03-07 |  |  |  | 2025-03-10 | 2025-03-24 | 2025-03-24 |  |  | 2025-04-23 | 2025-04-25 | Government of the Philippines (current year's budget) | 1231800 |  |  | 22035.6 |  |  |  | 1.COA 2.RAFC 3.PCCI | JANUARY 14, 2025 (10:00 AM) |  | JANUARY 27, 2025 (10:00 AM) | 2025-02-03 | 2025-02-14 | 2025-04-23
DA-RFO 1-2025-GOODS-025-R | REBIDDING OF SUPPLY AND DELIVERY OF VARIOUS HDPE PIPES AND GARDEN HOSE | SAAD Program, 4K Program and AMIA Program | Yes | Competitive Bidding | 2024-10-07 | January 7-27, 2025 |  | JANUARY 14, 2025 (10:00 AM) |  | JANUARY 27, 2025 (10:00 AM) |  | 2025-02-03 | 2025-02-14 | 2025-03-07 |  |  |  | 2025-03-11 | 2025-03-24 | 2025-03-24 |  |  | April 11, 15, 23, 2025 | April 11, 15, May 9, 2025 | Government of the Philippines (current year's budget) |  |  |  | 504630 |  |  |  | 1.COA 2.RAFC 3.PCCI | JANUARY 14, 2025 (10:00 AM) |  | JANUARY 27, 2025 (10:00 AM) | 2025-02-03 | 2025-02-14 | April 11, 15, 23, 2025
DA-RFO-1-2025-GOODS-026 | SUPPLY AND DELIVERY OF VARIOUS VEGETABLE SEEDS | NUPAP | Yes | Competitive Bidding | 2024-11-15 | December 13, 2024 to January 07, 2025 |  | DECEMBER 20, 2024 (9:00 AM) |  | JANUARY 20, 2025 (9:00 AM) |  | 2025-01-27 | JANUARY 30-31, 2025 | 2025-03-05 |  |  |  | 2025-03-05 | 2025-03-17 | 2025-03-17 |  |  | 2025-03-31 | 2025-06-03 | Government of the Philippines (current year's budget) | 8945190 |  |  | 8942085 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 20, 2024 (9:00 AM) |  | JANUARY 20, 2025 (9:00 AM) | 2025-01-27 | JANUARY 30-31, 2025 | 2025-03-31
DA-RFO-1-2025-GOODS-027 | SUPPLY AND DELIVERY OF FORTY-FIVE THOUSAND EIGHT HUNDRED (45,800) PACKS BIO FERTILIZER | CORN | Yes | Competitive Bidding | 2024-11-27 | December 13, 2024 to January 07, 2025 |  | DECEMBER 20, 2024 (10:00 AM) |  | JANUARY 7, 2025 (10:00 AM) |  | 2025-01-21 | 2025-01-22 | 2025-03-10 |  |  |  | 2025-03-10 | 2025-03-24 | 2025-03-24 |  |  | 2025-04-02 | 2025-04-22 | Government of the Philippines (current year's budget) | 9160000 |  |  | 9155420 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 20, 2024 (10:00 AM) |  | JANUARY 7, 2025 (10:00 AM) | 2025-01-21 | 2025-01-22 | 2025-04-02
SUPPLY AND DELIVERY OF VARIOUS INSECTICIDES
DA-RFO-1-2025-GOODS-028 | LOT 1: SUPPLY AND DELIVERY OF EIGHT HUNDRED (800) BOTTLES SYNTHETIC INSECTICIDE (Tetraniliprole) | CORN | Yes | Competitive Bidding | 2024-11-15 | December 13, 2024 to January 07, 2025 |  | DECEMBER 20, 2024 (11:00 AM) |  | JANUARY 21, 2025 (10:00 AM) |  | 2025-01-21 | 2025-01-23 | 26-Feb-2025 |  |  |  | 2025-03-03 | 2025-03-11 | 2025-03-11 |  |  | 2025-03-17 | 2025-03-27 | Government of the Philippines (current year's budget) | 1040000 |  |  | 999600 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 20, 2024 (11:00 AM) |  | JANUARY 21, 2025 (10:00 AM) | 2025-01-21 | 2025-01-23 | 2025-03-17
DA-RFO-1-2025-GOODS-028 | LOT 2: SUPPLY AND DELIVERY OF EIGHT HUNDRED (800) BOTTLES SYNTHETIC INSECTICIDE (Spinetoram) | CORN | Yes | Competitive Bidding | 2024-11-15 | December 13, 2024 to January 07, 2025 |  | DECEMBER 20, 2024 (11:00 AM) |  | JANUARY 21, 2025 (10:00 AM) |  | 2025-01-21 | 2025-01-23 | 26-Feb-2025 |  |  |  | 2025-03-03 | 2025-03-11 | 2025-03-11 |  |  | 2025-03-17 | 2025-03-27 | Government of the Philippines (current year's budget) | 1816000 |  |  | 1759600 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 20, 2024 (11:00 AM) |  | JANUARY 21, 2025 (10:00 AM) | 2025-01-21 | 2025-01-23 | 2025-03-17
DA-RFO-1-2025-GOODS-028-R | REBIDDING OF LOT 3: SUPPLY AND DELIVERY OF ONE THOUSAND SEVEN HUNDRED SIXTY (1,760) PACKS BIO INSECTICIDE (Bacillus Thurengiensis var Aizawai) | CORN | No | Competitive Bidding | 2024-11-15 | January 30, 2025 - February 18, 2025 |  | FEBRUARY 6, 2025 (9:00 AM) |  | FEBRUARY 24, 2025 (9:00 AM) |  | 2025-02-28 | 2025-03-03 | 2025-03-18 |  |  |  | 2025-03-20 | 2025-03-27 | 2025-03-27 |  |  | 2025-04-07 | 2025-04-15 | Government of the Philippines (current year's budget) | 792000 |  |  | 792000 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 6, 2025 (9:00 AM) |  | FEBRUARY 24, 2025 (9:00 AM) | 2025-02-28 | 2025-03-03 | 2025-04-07
DA-RFO-1-2025-GOODS-028-N | SECOND NEGOTIATED PROCUREMENT OF LOT 5: SUPPLY AND DELIVERY OF EIGHT HUNDRED (800) BOTTLES BOTANICAL PESTICIDE | CORN | No | Competitive Bidding | 2024-11-15 | May 5-19, 2025 |  | MAY 9, 2025 (10:00 AM) |  | MAY 19, 2025 (3:00 PM) |  | 2025-05-26 | 2025-06-10 | 2025-06-23 |  |  |  | 1925-06-27 | 2025-07-02 | 2025-07-02 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 960000 |  |  | 935200 |  |  |  | 1.COA 2.RAFC 3.PCCI | MAY 9, 2025 (10:00 AM) |  | MAY 19, 2025 (3:00 PM) | 2025-05-26 | 2025-06-10
SUPPLY AND DELIVERY OF VARIOUS HYBRID YELLOW CORN SEEDS
DA-RFO 1-2025-GOODS-030 | LOT 1: SUPPLY AND DELIVERY OF FIVE THOUSAND EIGHT HUNDRED SIXTEEN (5,816) BAGS HYBRID YELLOW CORN SEEDS (NSIC 2021 GMCn 75) | CORN | Yes | Competitive Bidding | 2024-10-01 | December 18, 2024 to January 8, 2025 |  | DECEMBER 26, 2024 (4:00 PM¦) |  | JANUARY 20, 2025 (10:00 AM) |  | 2025-01-21 | 2025-01-31 | 2025-03-04 |  |  |  | 2025-03-04 | 2025-03-11 | 2025-03-11 |  |  | 28-Mar-2025 (first delivery- 4,618 bags; Schelule of 2nd delivery is on 1-15 August 2025) | 2025-05-07 |  | 34896000 |  |  | 34896000 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 26, 2024 (4:00 PM¦) |  | JANUARY 20, 2025 (10:00 AM) | 2025-01-21 | 2025-01-31 | 28-Mar-2025 (first delivery- 4,618 bags; Schelule of 2nd delivery is on 1-15 August 2025)
DA-RFO 1-2025-GOODS-030 | LOT 2: SUPPLY AND DELIVERY OF THREE THOUSAND (3,000) BAGS HYBRID YELLOW CORN SEEDS (NSIC 2023 GMCn 89) | CORN | Yes | Competitive Bidding | 2024-10-01 | December 18, 2024 to January 8, 2025 |  | DECEMBER 26, 2024 (4:00 PM¦) |  | JANUARY 20, 2025 (10:00 AM) |  | 2025-01-21 | 2025-01-22 | 2025-03-04 |  |  |  | 2025-03-04 | 2025-03-11 | 2025-03-11 |  |  | 2025-03-27 | 2025-04-08 |  | 18000000 |  |  | 18000000 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 26, 2024 (4:00 PM¦) |  | JANUARY 20, 2025 (10:00 AM) | 2025-01-21 | 2025-01-22 | 2025-03-27
DA-RFO 1-2025-GOODS-030-R | REBIDDING OF LOT 3: SUPPLY AND DELIVERY OF SEVEN THOUSAND (7,000) BAGS HYBRID YELLOW CORN SEEDS (NSIC 2023 GMCn 91) | CORN | No | Competitive Bidding | 2024-10-01 | January 30, 2025 - February 18, 2025 |  | FEBRUARY 6, 2025 (10:00 AM) |  | FEBRUARY 24, 2025 (10:00 AM) |  | 2025-02-28 | 2025-03-03 | 2025-03-18 |  |  |  | 2025-03-20 | 2025-03-27 | 2025-03-27 |  |  | 2025-04-15 | 2025-04-22 |  | 42000000 |  |  | 42000000 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 6, 2025 (10:00 AM) |  | FEBRUARY 24, 2025 (10:00 AM) | 2025-02-28 | 2025-03-03 | 2025-04-15
DA-RFO-1-2025-GOODS-030-N | NEGOTIATED PROCUREMENT OF LOT 4: SUPPLY AND DELIVERY OF SEVEN THOUSAND (7,000) BAGS HYBRID YELLOW CORN SEEDS (NSIC 2023 GMCn92) | CORN | No | Competitive Bidding | 2024-10-01 | March 7-18, 2025 |  | MARCH 11, 2025 (3:00 PM) |  | MARCH 18, 2025 (11:00 AM) |  | 2025-03-18 | 2025-03-19 | 2025-03-27 |  |  |  | 2025-03-20 | 2025-03-27 | 2025-03-27 |  |  | 07-Jun-2025 First delivery- 5,860 bags; Schelule of 2nd delivery is on 1-15 August 2025) | 2025-06-04 |  | 42000000 |  |  | 42000000 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 11, 2025 (3:00 PM) |  | MARCH 18, 2025 (11:00 AM) | 2025-03-18 | 2025-03-19 | 07-Jun-2025 First delivery- 5,860 bags; Schelule of 2nd delivery is on 1-15 August 2025)
DA-RFO 1-2025-GOODS-030 | LOT 5: SUPPLY AND DELIVERY OF EIGHT HUNDRED FOUR (804) BAGS HYBRID YELLOW CORN SEEDS (NSIC 2021 Cn 333) | CORN | Yes | Competitive Bidding | 2024-10-01 | December 18, 2024 to January 8, 2025 |  | DECEMBER 26, 2024 (4:00 PM¦) |  | JANUARY 8, 2025 (9:00 AM) |  | 2025-01-21 | 2025-01-22 | 2025-03-04 |  |  |  | 2025-03-04 | FOR DELIVERY (August 2025) | [6 empty] | 3618000 |  |  | 3618000 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 26, 2024 (4:00 PM¦) |  | JANUARY 8, 2025 (9:00 AM) | 2025-01-21 | 2025-01-22 | FOR DELIVERY (August 2025)
DA-RFO 1-2025-GOODS-030 | LOT 6: SUPPLY AND DELIVERY OF ONE THOUSAND THREE HUNDRED TWENTY-FIVE (1,325) BAGS HYBRID YELLOW CORN SEEDS (NSIC 2018 GMCn 57) | CORN | Yes | Competitive Bidding | 2024-10-01 | December 18, 2024 to January 8, 2025 |  | DECEMBER 26, 2024 (4:00 PM¦) |  | JANUARY 8, 2025 (9:00 AM) |  | 2025-01-27 | 2025-02-06 | 2025-03-04 |  |  |  | 2025-03-04 | FOR DELIVERY (August 2025) | [6 empty] | 5962500 |  |  | 5962500 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 26, 2024 (4:00 PM¦) |  | JANUARY 8, 2025 (9:00 AM) | 2025-01-27 | 2025-02-06 | FOR DELIVERY (August 2025)
DA-RFO 1-2025-GOODS-030 | LOT 7: SUPPLY AND DELIVERY OF TWO THOUSAND FIVE HUNDRED (2,500) BAGS HYBRID YELLOW CORN SEEDS (NSIC 2012 Cn 261) | CORN | Yes | Competitive Bidding | 2024-10-01 | December 18, 2024 to January 8, 2025 |  | DECEMBER 26, 2024 (4:00 PM¦) |  | JANUARY 8, 2025 (9:00 AM) |  | 2025-01-21 | 2025-01-22 | 2025-03-04 |  |  |  | 2025-03-04 | FOR DELIVERY (August 2025) | [6 empty] | 11250000 |  |  | 11250000 |  |  |  | 1.COA 2.RAFC 3.PCCI | DECEMBER 26, 2024 (4:00 PM¦) |  | JANUARY 8, 2025 (9:00 AM) | 2025-01-21 | 2025-01-22 | FOR DELIVERY (August 2025)
SUPPLY, DELIVERY, SUBSCRIPTION, INSTALLATION, AND CONFIGURATION OF VARIOUS ICT EQUIPMENT AND NETWORK SOFTWARES
DA-RFO 1-2025-GOODS-032 | LOT 1: SUPPLY AND DELIVERY OF VARIOUS ICT EQUIPMENT | IMS | No | Competitive Bidding | 2024-12-05 | January 7-27, 2025 |  | JANUARY 14, 2025 (1:00 PM) |  | JANUARY 27, 2025 (1:00 PM) |  | 2025-01-30 | 2025-02-28 | 2025-03-05 |  |  |  | 2025-03-05 | 2025-03-26 | 2025-03-26 |  |  | 2025-07-04 | 2025-07-08 | Government of the Philippines (current year's budget) | 7912000 |  |  | 7435000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JANUARY 14, 2025 (1:00 PM) |  | JANUARY 27, 2025 (1:00 PM) | 2025-01-30 | 2025-02-28 | 2025-07-04
DA-RFO 1-2025-GOODS-032-R | REBIDDING OF LOT 2: SUPPLY, DELIVERY AND SUBSCRIPTION OF VARIOUS ICT SOFTWARE | IMS | No | Competitive Bidding | 2024-12-05 | February 26, 2025 to March 18, 2025 |  | MARCH 5, 2025 (11:00 AM) |  | MARCH 18, 2025 (10:00 AM) |  | 2025-02-03 | 2025-02-21 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-05-05 | 2025-05-05 |  |  | FOR DELIVERY (AUGUST 2025) |  | Government of the Philippines (current year's budget) | 2900000 |  |  | 2017011 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 5, 2025 (11:00 AM) |  | MARCH 18, 2025 (10:00 AM) | 2025-02-03 | 2025-02-21 | FOR DELIVERY (AUGUST 2025)
DA-RFO 1-2025-GOODS-032-R | REBIDDING OF LOT 3: SUPPLY, DELIVERY, INSTALLATION AND CONFIGURATION OF VARIOUS ICT NETWORK EQUIPMENT | IMS | No | Competitive Bidding | 2024-12-05 | February 26, 2025 to March 18, 2025 |  | MARCH 5, 2025 (11:00 AM) |  | MARCH 18, 2025 (10:00 AM) |  | 2025-02-03 | 2025-02-20 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-05-05 | 2025-05-05 |  |  | FOR DELIVERY (AUGUST 2025) |  | Government of the Philippines (current year's budget) | 4620000 |  |  | 2234454 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 5, 2025 (11:00 AM) |  | MARCH 18, 2025 (10:00 AM) | 2025-02-03 | 2025-02-20 | FOR DELIVERY (AUGUST 2025)
DA-RFO 1-2025-GOODS-032 | LOT 4: SUPPLY, DELIVERY, INSTALLATION AND CONFIGURATION OF 100-PORT DATA AND VOICE STRUCTURED CABLING WITH FIBER OPTIC CABLE BACKBONES | IMS | No | Competitive Bidding | 2024-12-05 | January 7-27, 2025 |  | JANUARY 14, 2025 (1:00 PM) |  | JANUARY 27, 2025 (1:00 PM) |  | 2025-01-30 | 2025-02-05 | 2025-03-05 |  |  |  | 2025-03-05 | 2025-03-19 | 2025-03-20 |  |  | 2025-05-27 | 2025-05-27 | Government of the Philippines (current year's budget) | 1000000 |  |  | 895000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JANUARY 14, 2025 (1:00 PM) |  | JANUARY 27, 2025 (1:00 PM) | 2025-01-30 | 2025-02-05 | 2025-05-27
DA-RFO 1-2025-GOODS-033 | SUPPLY AND DELIVERY OF VARIOUS COMMON-USED OFFICE SUPPLIES | GSS | No | Competitive Bidding | 2024-11-12 | January 7-27, 2025 |  | JANUARY 14, 2025 (3:00 PM) |  | JANUARY 27, 2025 (3:00 PM) |  | 2025-02-03 | 2025-02-21 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-04-04 | 2025-04-10 |  |  | 2025-05-19 | 2025-05-19 | Government of the Philippines (current year's budget) | 6294122.5 |  |  | 2017011 |  |  |  | 1.COA 2.RAFC 3.PCCI | JANUARY 14, 2025 (3:00 PM) |  | JANUARY 27, 2025 (3:00 PM) | 2025-02-03 | 2025-02-21 | 2025-05-19
DA-RFO 1-2025-GOODS-033 | SUPPLY AND DELIVERY OF VARIOUS COMMON-USED OFFICE SUPPLIES | GSS | No | Competitive Bidding | 2024-11-12 | January 7-27, 2025 |  | JANUARY 14, 2025 (3:00 PM) |  | JANUARY 27, 2025 (3:00 PM) |  | 2025-02-03 | 2025-02-20 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-04-04 | 2025-04-08 |  |  | 2025-06-10 | 2025-06-10 | Government of the Philippines (current year's budget) |  |  |  | 2234454 |  |  |  | 1.COA 2.RAFC 3.PCCI | JANUARY 14, 2025 (3:00 PM) |  | JANUARY 27, 2025 (3:00 PM) | 2025-02-03 | 2025-02-20 | 2025-06-10
DA-RFO 1-2025-GOODS-034 | LOT 1: SUPPLY AND DELIVERY OF FIVE HUNDRED SEVENTY-FOUR (574) LITERS ORGANIC LIQUID FERTILIZER | AMIA and 4K Program | No | Competitive Bidding | n/a | January 8-28, 2025 |  | JANUARY 16, 2025 (1:00 PM) |  | JANUARY 28, 2025 (1:00 PM) |  | 2025-01-30 | 2025-02-03 | 2025-03-05 |  |  |  | 2025-03-05 | 2025-03-19 | 2025-03-19 |  |  | DELIVERED |  | Government of the Philippines (current year's budget) | 516600 |  |  | 516600 |  |  |  | 1.COA 2.RAFC 3.PCCI | JANUARY 16, 2025 (1:00 PM) |  | JANUARY 28, 2025 (1:00 PM) | 2025-01-30 | 2025-02-03
DA-RFO-1-2025-GOODS-035 | LOT 1: SUPPLY AND DELIVERY OF TWENTY THOUSAND THREE HUNDRED FORTY-SIXTY (20,346) BAGS HYBRID PALAY SEEDS (NSIC Rc456H) | RICE | No | Competitive Bidding | 2024-10-03 | FEBRUARY 3-25, 2025 |  | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) |  | 2025-03-04 | 2025-03-10 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-03-27 | 2025-03-27 |  |  | 2025-04-25 | Pang - 07-May-25 La Union - 02-May-25 Ilocos Sur - 06-May-25 Ilocos Norte - 06-May-25 | Government of the Philippines (current year's budget) | 101730000 |  |  | 101730000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JANUARY 16, 2025 (1:00 PM) |  | JANUARY 28, 2025 (1:00 PM) | 2025-01-30 | 2025-02-03 | 2025-04-25
DA-RFO-1-2025-GOODS-035 | LOT 2: SUPPLY AND DELIVERY OF TWELVE THOUSAND FIVE HUNDRED TWENTY-SIX (12,526) BAGS HYBRID PALAY SEEDS (NSIC Rc486H) | RICE | No | Competitive Bidding | 2024-10-03 | FEBRUARY 3-25, 2025 |  | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) |  | 2025-03-04 | 2025-03-10 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-03-27 | 2025-03-27 |  |  | 2025-04-28 | Pang - 07-May-25 La Union - 23-Apr-25 Ilocos Sur - 06-May-25 Ilocos Norte - 07-May-25 | Government of the Philippines (current year's budget) | 62630000 |  |  | 62630000 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) | 2025-03-04 | 2025-03-10 | 2025-04-28
DA-RFO-1-2025-GOODS-035-R | REBIDDING OF LOT 3: SUPPLY AND DELIVERY OF TWENTY-TWO THOUSAND NINE HUNDRED SEVENTY-FIVE (22,975) BAGS HYBRID PALAY SEEDS (NSIC Rc234H) | RICE | No | Competitive Bidding | 2024-10-03 | April 3, 2025 to April 22, 2025 |  | APRIL 10, 2025 (9:00 AM) |  | APRIL 22, 2025 (9:00 AM) |  | 2025-04-29 | 2025-05-05 | 2025-05-13 |  |  |  | 2025-05-19 | 2025-03-30 | 2025-03-30 |  |  | for Dry Season delivery |  | Government of the Philippines (current year's budget) | 114875000 |  |  | 114875000 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) | 2025-03-04 | 2025-03-10
DA-RFO-1-2025-GOODS-035 | LOT 4: SUPPLY AND DELIVERY OF TWENTY THOUSAND FIVE HUNDRED FORTY-EIGHT (20,548) BAGS HYBRID PALAY SEEDS (NSIC Rc376H) | RICE | No | Competitive Bidding | 2024-10-03 | FEBRUARY 3-25, 2025 |  | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) |  | 2025-03-04 | MARCH 13-14, 2025 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-03-27 | 2025-03-27 |  |  | 2025-04-30 | Pang - 07-May-25 La Union - 02-May-25 Ilocos Sur - 06-May-25 Ilocos Norte - 07-May-25 | Government of the Philippines (current year's budget) | 102740000 |  |  | 102740000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 10, 2025 (9:00 AM) |  | APRIL 22, 2025 (9:00 AM) | 2025-04-29 | 2025-05-05 | 2025-04-30
DA-RFO-1-2025-GOODS-035-R | REBIDDING OF LOT 5: SUPPLY AND DELIVERY OF FIVE THOUSAND EIGHTY (5,080) BAGS HYBRID PALAY SEEDS (NSIC Rc548H) | RICE | No | Competitive Bidding | 2024-10-03 | April 3, 2025 to April 22, 2025 |  | APRIL 10, 2025 (9:00 AM) |  | APRIL 22, 2025 (9:00 AM) |  | 2025-04-23 | 2025-05-05 | 2025-05-13 |  |  |  | 2025-05-19 | 2025-05-30 | 2025-03-30 |  |  | for Dry Season delivery |  | Government of the Philippines (current year's budget) | 25400000 |  |  | 25400000 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) | 2025-03-04 | MARCH 13-14, 2025
DA-RFO-1-2025-GOODS-035-R | REBIDDING OF LOT 6: SUPPLY AND DELIVERY OF ONE THOUSAND SIX HUNDRED TEN (1,610) BAGS HYBRID PALAY SEEDS (NSIC Rc546H) | RICE | No | Competitive Bidding | 2024-10-03 | April 3, 2025 to April 22, 2025 |  | APRIL 10, 2025 (9:00 AM) |  | APRIL 22, 2025 (9:00 AM) |  | 2025-04-23 | 2025-05-05 | 2025-05-13 |  |  |  | 2025-05-19 | 2025-05-30 | 2025-03-30 |  |  | for Dry Season delivery |  | Government of the Philippines (current year's budget) | 8050000 |  |  | 8050000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 10, 2025 (9:00 AM) |  | APRIL 22, 2025 (9:00 AM) | 2025-04-23 | 2025-05-05
DA-RFO-1-2025-GOODS-035 | LOT 7: SUPPLY AND DELIVERY OF ONE THOUSAND SIX HUNDRED TEN (1,610) BAGS HYBRID PALAY SEEDS (NSIC Rc524H) | RICE | No | Competitive Bidding | 2024-10-03 | FEBRUARY 3-25, 2025 |  | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) |  | 2025-03-04 | MARCH 13-14, 2025 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-03-27 | 2025-03-27 |  |  | for Dry Season delivery |  | Government of the Philippines (current year's budget) | 8050000 |  |  | 8050000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 10, 2025 (9:00 AM) |  | APRIL 22, 2025 (9:00 AM) | 2025-04-23 | 2025-05-05
DA-RFO-1-2025-GOODS-035 | LOT 8: SUPPLY AND DELIVERY OF THIRTY THOUSAND NINE HUNDRED SEVENTY (30,970) BAGS HYBRID PALAY SEEDS (NSIC Rc488H) | RICE | No | Competitive Bidding | 2024-10-03 | FEBRUARY 3-25, 2025 |  | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) |  | 2025-03-04 | 2025-03-11 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-03-27 | 2025-03-27 |  |  | 2025-05-30 | Pang 6/11/2025, La Union 6/2/2025, Ilocos Sur 5/30/2025, Ilocos Norte 5/27/2025 | Government of the Philippines (current year's budget) | 154850000 |  |  | 154850000 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) | 2025-03-04 | MARCH 13-14, 2025
DA-RFO-1-2025-GOODS-035 | LOT 9: SUPPLY AND DELIVERY OF TWENTY-NINE THOUSAND SIXTY (29,060) BAGS HYBRID PALAY SEEDS (NSIC Rc540H) | RICE | No | Competitive Bidding | 2024-10-03 | FEBRUARY 3-25, 2025 |  | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) |  | 2025-03-04 | 2025-03-11 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-03-27 | 2025-03-27 |  |  | 2025-05-30 | Pang - 11-Jun-25 La Union - 03-Jun-25 Ilocos Sur - 05-Jun-25 Ilocos Norte - 05-Jun-25 | Government of the Philippines (current year's budget) | 145300000 |  |  | 145300000 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) | 2025-03-04 | 2025-03-11 | 2025-05-30
DA-RFO-1-2025-GOODS-035 | LOT 10: SUPPLY AND DELIVERY OF EIGHT THOUSAND ONE HUNDRED FORTY-EIGHT (8,148) BAGS HYBRID PALAY SEEDS (NSIC Rc132H) | RICE | No | Competitive Bidding | 2024-10-03 | FEBRUARY 3-25, 2025 |  | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) |  | 2025-03-04 | 2025-03-11 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-03-27 | 2025-03-27 |  |  | 2025-04-29 | Pang - 16-Apr-25 La Union - 22-Apr-25 Ilocos Sur - 06-May-25 Ilocos Norte - 06-May-25 | Government of the Philippines (current year's budget) | 40740000 |  |  | 40740000 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) | 2025-03-04 | 2025-03-11 | 2025-04-29
DA-RFO-1-2025-GOODS-035 | LOT 11: SUPPLY AND DELIVERY OF TWELVE THOUSAND FOUR HUNDRED TWENTY-THREE (12,423) BAGS HYBRID PALAY SEEDS (NSIC Rc350H) | RICE | No | Competitive Bidding | 2024-10-03 | FEBRUARY 3-25, 2025 |  | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) |  | 2025-03-04 | 2025-03-11 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-03-27 | 2025-03-27 |  |  | 2025-04-23 | Pang - 30-Apr-25 La Union - 16-Apr-25 Ilocos Sur - 06-May-25 Ilocos Norte - 06-May-25 | Government of the Philippines (current year's budget) | 62115000 |  |  | 62115000 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) | 2025-03-04 | 2025-03-11 | 2025-04-23
DA-RFO-1-2025-GOODS-035 | LOT 12: SUPPLY AND DELIVERY OF THIRTY THOUSAND TWO HUNDRED SEVENTY-EIGHT (30,278) BAGS HYBRID PALAY SEEDS (NSIC Rc666H) | RICE | No | Competitive Bidding | 2024-10-03 | FEBRUARY 3-25, 2025 |  | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) |  | 2025-03-04 | 13-14-Mar-2025 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-03-27 | 2025-03-27 |  |  | 2025-04-30 | Pang - 07-May-25 La Union - 02-May-25 Ilocos Sur - 06-May-25 Ilocos Norte - 07-May-25 | Government of the Philippines (current year's budget) | 151390000 |  |  | 151390000 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) | 2025-03-04 | 2025-03-11
DA-RFO-1-2025-GOODS-035 | LOT 13: SUPPLY AND DELIVERY OF TWENTY-SIX THOUSAND EIGHT HUNDRED FORTY-FIVE (26,845) BAGS HYBRID PALAY SEEDS (NSIC Rc656H) | RICE | No | Competitive Bidding | 2024-10-03 | FEBRUARY 3-25, 2025 |  | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) |  | 2025-03-04 | 13-14-Mar-2025 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-03-27 | 2025-03-27 |  |  | 2025-04-30 | Pang - 07-May-25 La Union - 02-May-25 Ilocos Sur - 06-May-25 Ilocos Norte - 07-May-25 | Government of the Philippines (current year's budget) | 134225000 |  |  | 134225000 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 11, 2025 (1:00 PM) |  | FEBRUARY 25, 2025 (9:00 AM) | 2025-03-04 | 13-14-Mar-2025
SUPPLY AND DELIVERY OF VARIOUS LIVESTOCK AND POULTRY FEEDS
DA-RFO-1-2025-GOODS-036 | LOT 1: SUPPLY AND DELIVERY OF VARIOUS LIVESTOCK AND POULTRY FEEDS FOR DA-INREC, DINGRAS, ILOCOS NORTE | R&D | No | Competitive Bidding | n/a | February 5-26, 2025 |  | FEBRUARY 12, 2025 (9:00 AM) |  | FEBRUARY 26, 2025 (9:00 AM) |  | 2025-02-28 | 2025-03-13 | 2025-03-27 |  |  |  | 2025-03-27 | 2025-03-31 | 2025-03-31 |  |  | 2025-04-14 | 2025-04-14 | Government of the Philippines (current year's budget) | 828900 |  |  | 452200 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 12, 2025 (9:00 AM) |  | FEBRUARY 26, 2025 (9:00 AM) | 2025-02-28 | 2025-03-13 | 2025-04-14
DA-RFO-1-2025-GOODS-036 | LOT 2: SUPPLY AND DELIVERY OF VARIOUS LIVESTOCK AND POULTRY FEEDS FOR DA-ISReC, SAN JUAN, ILOCOS SUR | R&D | No | Competitive Bidding | n/a | February 5-26, 2025 |  | FEBRUARY 12, 2025 (9:00 AM) |  | FEBRUARY 26, 2025 (9:00 AM) |  | 2025-02-28 | 2025-03-13 | 2025-03-27 |  |  |  | 2025-03-27 | 2025-03-31 | 2025-03-31 |  |  | 2025-04-14 | 2025-04-14 | Government of the Philippines (current year's budget) | 221100 |  |  | 173235 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 12, 2025 (9:00 AM) |  | FEBRUARY 26, 2025 (9:00 AM) | 2025-02-28 | 2025-03-13 | 2025-04-14
DA-RFO-1-2025-GOODS-036 | LOT 3: SUPPLY AND DELIVERY OF VARIOUS LIVESTOCK AND POULTRY FEEDS FOR DA-ILIARC, BACNOTAN, LA UNION | R&D | No | Competitive Bidding | n/a | February 5-26, 2025 |  | FEBRUARY 12, 2025 (9:00 AM) |  | FEBRUARY 26, 2025 (9:00 AM) |  | 2025-02-28 | 2025-03-13 | 2025-03-27 |  |  |  | 2025-03-27 | 2025-03-31 | 2025-03-31 | 4 |  | 2025-04-14 | 2025-04-14 | Government of the Philippines (current year's budget) | 171830 |  |  | 157770 |  |  | 0.081825 | 1.COA 2.RAFC 3.PCCI | FEBRUARY 12, 2025 (9:00 AM) |  | FEBRUARY 26, 2025 (9:00 AM) | 2025-02-28 | 2025-03-13 | 2025-04-14 |  | FALSE | FALSE
DA-RFO-1-2025-GOODS-036 | LOT 4: SUPPLY AND DELIVERY OF VARIOUS LIVESTOCK AND POULTRY FEEDS FOR DA-PREC, SUAL, PANGASINAN | R&D | No | Competitive Bidding | n/a | February 5-26, 2025 |  | FEBRUARY 12, 2025 (9:00 AM) |  | FEBRUARY 26, 2025 (9:00 AM) |  | 2025-02-28 | 2025-03-13 | 2025-03-27 |  |  |  | 2025-03-27 | 2025-03-31 | 2025-03-31 |  |  | 2025-04-14 | 2025-04-14 | Government of the Philippines (current year's budget) | 508000 |  |  | 452200 |  |  |  | 1.COA 2.RAFC 3.PCCI | FEBRUARY 12, 2025 (9:00 AM) |  | FEBRUARY 26, 2025 (9:00 AM) | 2025-02-28 | 2025-03-13 | 2025-04-14 |  | FALSE | FALSE
DA-RFO-1-2025-GOODS-037 | SUPPLY AND DELIVERY OF SIXTY-EIGHT (68) UNITS GRASSCUTTER | HVCDP & NUPAP | No | Competitive Bidding | n/a | February 19, 2025 to March 10, 2025 |  | FEBRUARY 26, 2025 (1:00 PM) |  | MARCH 10, 2025 (10:00 AM) |  | 2025-03-11 | 2025-03-14 | 2025-03-27 |  |  |  | 2025-03-27 | 2025-03-27 | 2025-03-27 | 0 |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 1360000 |  |  | 642600 |  |  | 0.5275 | 1.COA 2.RAFC 3.PCCI | FEBRUARY 26, 2025 (1:00 PM) |  | MARCH 10, 2025 (10:00 AM) | 2025-03-11 | 2025-03-14 |  |  | FALSE | FALSE
DA-RFO-1-2025-GOODS-039 | LOT 1: SUPPLY AND DELIVERY OF ONE HUNDRED SEVENTY THOUSAND SIX HUNDRED FIFTEEN (170,615) BAGS COMPLETE FERTILIZER | RICE | No | Competitive Bidding | 2025-01-16 | February 20, 2025 to March 17, 2025 |  | MARCH 3, 2025 (9:00 AM) |  | MARCH 17, 2025 (9:00 AM) |  | 2025-03-21 | 2025-04-28 | 2025-05-13 |  |  |  | 2025-05-19 | 2025-05-29 | 2025-05-29 |  |  | FOR DELIVERY |  |  | 0 |  |  | 0
DA-RFO-1-2025-GOODS-040 | LOT 1: SUPPLY AND DELIVERY OF SEVEN THOUSAND FOUR HUNDRED FORTY-FOUR (7,444) PACKS BIOFERTILIZER | RICE | No | Competitive Bidding | 2025-02-11 | February 20, 2025 to March 17, 2025 |  | MARCH 3, 2025 (10:30 AM) |  | MARCH 17, 2025 (10:30 AM) |  | 2025-03-21 | 2025-03-25 | 2025-03-27 |  |  |  | 2025-03-27 | 2025-03-28 | 2025-03-28 |  |  | 2025-04-22 | 2025-05-09 | Government of the Philippines (current year's budget) | 5583000 |  |  | 5583000 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 3, 2025 (10:30 AM) |  | MARCH 17, 2025 (10:30 AM) | 2025-03-21 | 2025-03-25 | 2025-04-22
DA-RFO-1-2025-GOODS-040-R | REBIDDING OF LOT 2: SUPPLY AND DELIVERY OF THREE THOUSAND SEVEN HUNDRED TWENTY-TWO (3,722) BOTTLES BIOFERTILIZER | RICE | No | Competitive Bidding | 2025-02-11 | April 3, 2025 to April 22, 2025 |  | APRIL 10, 2025 (10:00 AM) |  | APRIL 22, 2025 (10:00 AM) |  | 2025-04-23 | 2025-04-29 | 2025-05-28 |  |  |  | 2025-05-29 | 2025-06-05 | 2025-06-11 |  |  | 2025-06-20 | 2025-07-03 | Government of the Philippines (current year's budget) | 5583000 |  |  | 5583000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 10, 2025 (10:00 AM) |  | APRIL 22, 2025 (10:00 AM) | 2025-04-23 | 2025-04-29 | 2025-06-20
DA-RFO-1-2025-GOODS-040-R | REBIDDING OF LOT 3: SUPPLY AND DELIVERY OF FOUR THOUSAND SIX HUNDRED EIGHTY-FOUR (4,684) PACKS BIOFERTILIZER | RICE | No | Competitive Bidding | 2025-02-11 | April 3, 2025 to April 22, 2025 |  | APRIL 10, 2025 (10:00 AM) |  | APRIL 22, 2025 (10:00 AM) |  | 2025-04-23 | 2025-04-29 | 2025-05-28 |  |  |  | 2025-05-29 | 2025-06-05 | 2025-06-11 |  |  | 2025-06-20 | 2025-07-03 | Government of the Philippines (current year's budget) | 4684000 |  |  | 4684000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 10, 2025 (10:00 AM) |  | APRIL 22, 2025 (10:00 AM) | 2025-04-23 | 2025-04-29 | 2025-06-20
SUPPLY AND DELIVERY OF VARIOUS SOIL AMELIORANTS
DA-RFO-1-2025-GOODS-041 | LOT 1: SUPPLY AND DELIVERY OF FIVE THOUSAND SIX HUNDRED TWENTY (5,620) PACKS SOIL AMELIORANT | RICE | No | Competitive Bidding | 2025-02-11 | February 20, 2025 to March 17, 2025 |  | MARCH 3, 2025 (1:00 PM) |  | MARCH 17, 2025 (1:00 PM) |  | 2025-03-21 | 2025-03-25 | 2025-03-27 |  |  |  | 2025-03-27 | 2025-03-28 | 2025-03-28 |  |  | 2025-04-22 | 2026-05-09 | Government of the Philippines (current year's budget) | 4215000 |  |  | 4206570 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 3, 2025 (1:00 PM) |  | MARCH 17, 2025 (1:00 PM) | 2025-03-21 | 2025-03-25 | 2025-04-22
DA-RFO-1-2025-GOODS-041 | LOT 2: SUPPLY AND DELIVERY OF EIGHT THOUSAND FIVE HUNDRED (8,500) PACKS SOIL AMELIORANT | RICE | No | Competitive Bidding | 2025-02-11 | February 20, 2025 to March 17, 2025 |  | MARCH 3, 2025 (1:00 PM) |  | MARCH 17, 2025 (1:00 PM) |  | 2025-03-21 | 2025-03-25 | 2025-03-27 |  |  |  | 2025-03-27 | 2025-03-28 | 2025-03-28 |  |  | 2025-04-22 | 2025-05-09 | Government of the Philippines (current year's budget) | 2125000 |  |  | 2125000 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 3, 2025 (1:00 PM) |  | MARCH 17, 2025 (1:00 PM) | 2025-03-21 | 2025-03-25 | 2025-04-22
DA-RFO-1-2025-GOODS-041 | LOT 3: SUPPLY AND DELIVERY OF SIX THOUSAND FIVE HUNDRED SIXTY-SIX (6,566) PACKS SOIL AMELIORANT | RICE | No | Competitive Bidding | 2025-02-11 | February 20, 2025 to March 17, 2025 |  | MARCH 3, 2025 (1:00 PM) |  | MARCH 17, 2025 (1:00 PM) |  | 2025-03-21 | 2025-03-24 | 2025-03-27 |  |  |  | 2025-03-27 | 2025-03-28 | 2025-03-28 |  |  | 2025-04-22 | 2025-05-09 | Government of the Philippines (current year's budget) | 5252800 |  |  | 5251158.5 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 3, 2025 (1:00 PM) |  | MARCH 17, 2025 (1:00 PM) | 2025-03-21 | 2025-03-24 | 2025-04-22
DA-RFO 1-2025-GOODS-042 | SUPPLY AND DELIVERY OF VARIOUS MYCOTOXIN (AFLATOXIN) EXTRACTION AND TEST KITS | ILD | No | Competitive Bidding | 2024-10-07 | 2024-10-07 |  | MARCH 5, 2025 (1:00 PM) |  | MARCH 18, 2025 (1:00 PM) |  | 2025-03-25 | 2025-04-24 | 2025-05-05 |  |  |  | 2025-05-06 | 2025-05-19 | 2025-05-19 |  |  | 2025-06-10 | 2025-06-10 | Government of the Philippines (current year's budget) | 1353200 |  |  | 1294544 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 5, 2025 (1:00 PM) |  | MARCH 18, 2025 (1:00 PM) | 2025-03-25 | 2025-04-24
DA-RFO 1-2025-GOODS-043 | SUPPLY AND DELIVERY OF VARIOUS VETERINARY DRUGS AND BIOLOGICS | Livestock & SAAD | No | Competitive Bidding | 2024-10-02 | 2024-10-02 |  | MARCH 5, 2025 (2:00 PM) |  | MARCH 18, 2025 (2:00 PM) |  | 2025-03-25 | 2025-03-28 | 2025-04-28 |  |  |  | 2025-05-02 | 2025-05-19 | 2025-05-19 |  |  | DELIVERED |  | Government of the Philippines (current year's budget) | 2535775 |  |  | 971900 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 5, 2025 (2:00 PM) |  | MARCH 18, 2025 (2:00 PM) | 2025-03-25 | 2025-03-28
DA-RFO 1-2025-GOODS-043 | SUPPLY AND DELIVERY OF VARIOUS VETERINARY DRUGS AND BIOLOGICS | Livestock & SAAD | No | Competitive Bidding | 2024-10-02 | 2024-10-02 |  | MARCH 5, 2025 (2:00 PM) |  | MARCH 18, 2025 (2:00 PM) |  | 2025-03-25 | 2025-03-28 | 2025-04-28 |  |  |  | 2025-05-02 | 2025-05-20 | 2025-05-20 |  |  | DELIVERED |  | Government of the Philippines (current year's budget) |  |  |  | 234126 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 5, 2025 (2:00 PM) |  | MARCH 18, 2025 (2:00 PM) | 2025-03-25 | 2025-03-28
SUPPLY AND DELIVERY OF CATTLE AND CARABAO
DA-RFO-1-2025-GOODS-044 | LOT 1: SUPPLY AND DELIVERY OF TWENTY-TWO (22) HEADS UPGRADED CATTLE (BULL) | OAP/AMIA | No | Competitive Bidding | 2024-11-12 | February 26, 2025 to March 18, 2025 |  | MARCH 5, 2025 (3:00 PM) |  | MARCH 18, 2025 (3:00 PM) |  | 2025-03-25 | 2025-04-23 | 2025-05-23 |  |  |  | 2025-05-23 | 2025-05-23 | 2025-05-23 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 1430000 |  |  | 1429780 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 5, 2025 (3:00 PM) |  | MARCH 18, 2025 (3:00 PM) | 2025-03-25 | 2025-04-23 | FOR DELIVERY
DA-RFO-1-2025-GOODS-044 | LOT 2: SUPPLY AND DELIVERY OF EIGHTY-ONE (81) HEADS UPGRADED CATTLE (HEIFER) | OAP/AMIA | No | Competitive Bidding | 2024-11-12 | February 26, 2025 to March 18, 2025 |  | MARCH 5, 2025 (3:00 PM) |  | MARCH 18, 2025 (3:00 PM) |  | 2025-03-25 | 2025-04-23 | 2025-05-23 |  |  |  | 2025-05-23 | 2025-05-23 | 2025-05-23 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 5265000 |  |  | 5264190 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 5, 2025 (3:00 PM) |  | MARCH 18, 2025 (3:00 PM) | 2025-03-25 | 2025-04-23 | FOR DELIVERY
DA-RFO-1-2025-GOODS-044 | LOT 3: SUPPLY AND DELIVERY OF TWO (2) HEADS PUREBRED ISLAND BORN BRAHMAN CATTLE (BULL) | OAP/AMIA | No | Competitive Bidding | 2024-11-12 | February 26, 2025 to March 18, 2025 |  | MARCH 5, 2025 (3:00 PM) |  | MARCH 18, 2025 (3:00 PM) |  | 2025-03-25 | 2025-04-23 | 2025-05-23 |  |  |  | 2025-05-23 | 2025-05-23 | 2025-05-23 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 360000 |  |  | 359980 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 5, 2025 (3:00 PM) |  | MARCH 18, 2025 (3:00 PM) | 2025-03-25 | 2025-04-23 | FOR DELIVERY
DA-RFO 1-2025-GOODS-045 | SUPPLY AND DELIVERY OF VARIOUS TEST KITS | ILD | No | Competitive Bidding | 2024-10-07 | March 4-24, 2025 |  | MARCH 11, 2025 (1:00 PM) |  | MARCH 24, 2025 (1:00 PM) |  | 2025-03-26 | 2025-04-03 | 2025-04-28 |  |  |  | 2025-05-02 | 2025-05-19 | 2025-05-19 |  |  | 2025-06-10 | 2025-06-10 | Government of the Philippines (current year's budget) | 2195000 |  |  | 2195000 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 11, 2025 (1:00 PM) |  | MARCH 24, 2025 (1:00 PM) | 2025-03-26 | 2025-04-03
DA-RFO 1-2025-GOODS-046 | SUPPLY AND DELIVERY OF VARIOUS BAMBOO PROCESSING EQUIPMENT | HVCDP | No | Competitive Bidding | 2024-10-07 | March 10, 2025 to April 1, 2025 |  | MARCH 19, 2025 (3:00 PM) |  | APRIL 1, 2025 (9:00 AM) |  | 2025-04-10 | 2025-04-16 | 2025-05-07 |  |  |  | 2025-05-07 | 2025-05-19 | 2025-05-19 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 3340000 |  |  | 3320000 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 19, 2025 (3:00 PM) |  | APRIL 1, 2025 (9:00 AM) | 2025-04-10 | 2025-04-16
DA-RFO 1-2025-GOODS-047 | SUPPLY AND DELIVERY OF ONE (1) LOT VARIOUS INORGANIC FERTILIZERS | Research | No | Competitive Bidding | 2025-02-13 | March 17, 2025 to April 8, 2025 |  | MARCH 24, 2025 (2:00 PM) |  | APRIL 8, 2025 (9:00 AM) |  | 2025-04-10 | 2025-04-14 | 2025-05-26 |  |  |  | 2025-05-29 | 2025-06-11 | 2025-06-11 |  |  |  |  | Government of the Philippines (current year's budget) | 2765450 |  |  | 2669290 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 24, 2025 (2:00 PM) |  | APRIL 8, 2025 (9:00 AM) | 2025-04-10 | 2025-04-14
DA-RFO-1-2025-GOODS-048 | SUPPLY AND DELIVERY OF FIVE HUNDRED FIFTY-SEVEN (557) CANS YELLOW ONION SEEDS | HVCDP | No | Competitive Bidding | 2025-03-18 | March 21, 2025 to April 15, 2025 |  | APRIL 1, 2025 (11:00 AM) |  | APRIL 15, 2025 (9:00 AM) |  | 2025-04-22 | 2025-04-30 | 2025-05-13 |  |  |  | 2025-05-19 | 2025-06-04 | 2025-06-20 |  |  |  |  | Government of the Philippines (current year's budget) | 5597850 |  |  | 5597293 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 1, 2025 (11:00 AM) |  | APRIL 15, 2025 (9:00 AM) | 2025-04-22 | 2025-04-30 | 2025-06-04
DA-RFO-1-2025-GOODS-049 | PROVISION OF LABOR AND MATERIALS FOR THE INSTALLATION OF ONE (1) LOT THREE (3) PHASE LINE CONVERSION AND EXTENSION OF POWER SUPPLY IN PREC SUAL INCUBATION HUB | DA-PREC | No | Competitive Bidding | 2025-03-26 | March 28, 2025 to April 16, 2025 |  | APRIL 4, 2025 (10:00 AM) |  | APRIL 16, 2025 (9:00 AM) |  | 2025-04-22 | 2025-04-29 | 2025-05-28 |  |  |  | 2025-05-29 | 2025-05-23 | 2025-05-23 |  |  | COMPLETED |  | Government of the Philippines (current year's budget) | 3999666 |  |  | 3559956.33 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 4, 2025 (10:00 AM) |  | APRIL 16, 2025 (9:00 AM) | 2025-04-22 | 2025-04-29
DA-RFO 1-2025-GOODS-050 | SUPPLY AND DELIVERY OF VARIOUS PESTICIDES | CORN | No | Competitive Bidding | N/A | April 3, 2025 to April 22, 2025 |  | APRIL 10, 2025 (11:00 AM) |  | APRIL 22, 2025 (11:00 AM) |  | 2025-04-23 | 2025-04-29 | 2025-05-26 |  |  |  | 2025-05-29 | 2025-06-24 | 2025-06-27 |  |  | 2025-06-24 | 2025-06-27 | Government of the Philippines (current year's budget) | 1950000 |  |  | 1608000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 10, 2025 (11:00 AM) |  | APRIL 22, 2025 (11:00 AM) | 2025-04-23 | 2025-04-29 | 2025-06-24
SUPPLY AND DELIVERY OF VARIOUS COMBINE HARVESTERS
DA-RFO-1-2025-GOODS-051 | LOT 1: SUPPLY AND DELIVERY OF SIX (6) UNITS RICE COMBINE HARVESTER (65 to 72 HP) | RICE | No | Competitive Bidding | 2024-10-07 | April 8-28, 2025 |  | APRIL 15, 2025 (1:00 PM) |  | APRIL 28, 2025 (9:00 AM) |  | 2025-04-30 | MAY 7-8, 2025 | 2025-06-09 |  |  |  | 2025-06-09 | 2025-06-18 | 2025-06-18 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 12000000 |  |  | 11970000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 15, 2025 (1:00 PM) |  | APRIL 28, 2025 (9:00 AM) | 2025-04-30 | MAY 7-8, 2025
DA-RFO-1-2025-GOODS-051 | LOT 2: SUPPLY AND DELIVERY OF SIX (6) UNITS RICE COMBINE HARVESTER (30 to 40 HP) | RICE | No | Competitive Bidding | 2024-10-07 | April 8-28, 2025 |  | APRIL 15, 2025 (1:00 PM) |  | APRIL 28, 2025 (9:00 AM) |  | 2025-04-30 | MAY 7-8, 2025 | 2025-06-09 |  |  |  | 2025-06-11 | 2025-06-18 | 2025-06-18 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 9300000 |  |  | 9288000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 15, 2025 (1:00 PM) |  | APRIL 28, 2025 (9:00 AM) | 2025-04-30 | MAY 7-8, 2025 | 2025-06-27
DA-RFO-1-2025-GOODS-051 | LOT 3: SUPPLY AND DELIVERY OF FIVE (5) UNITS CORN COMBINE HARVESTER | CORN | No | Competitive Bidding | 2024-10-07 | April 8-28, 2025 |  | APRIL 15, 2025 (1:00 PM) |  | APRIL 28, 2025 (9:00 AM) |  | 2025-04-30 | MAY 7-8, 2025 | 2025-06-09 |  |  |  | 2025-06-09 | 2025-06-18 | 2025-06-18 |  |  | 2025-06-27 | 2025-06-27 | Government of the Philippines (current year's budget) | 11750000 |  |  | 11725000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 15, 2025 (1:00 PM) |  | APRIL 28, 2025 (9:00 AM) | 2025-04-30 | MAY 7-8, 2025
| SUPPLY AND DELIVERY OF VARIOUS FOUR-WHEEL DRIVE TRACTORS | [23 empty] | Government of the Philippines (current year's budget) | [7 empty] | 1.COA 2.RAFC 3.PCCI
DA-RFO-1-2025-GOODS-052 | LOT 1: SUPPLY AND DELIVERY OF NINE (9) UNITS FOUR-WHEEL DRIVE TRACTOR | RICE & CORN | No | Competitive Bidding | 2024-10-07 | April 8-28, 2025 |  | APRIL 15, 2025 (2:00 PM) |  | APRIL 28, 2025 (10:00 AM) |  | 2025-04-30 | MAY 7-8, 2025 | 2025-05-28 |  |  |  | 2025-03-30 | 2025-06-16 | 2025-06-16 |  |  | on-going delivery |  | Government of the Philippines (current year's budget) | 31500000 |  |  | 31320000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 15, 2025 (2:00 PM) |  | APRIL 28, 2025 (10:00 AM) | 2025-04-30 | MAY 7-8, 2025 | on-going delivery
DA-RFO-1-2025-GOODS-052 | LOT 2: SUPPLY AND DELIVERY OF TWELVE (12) UNITS FOUR-WHEEL TRACTORS WITH ACCESSORIES | RICE & CORN | No | Competitive Bidding | 2024-10-07 | April 8-28, 2025 |  | APRIL 15, 2025 (2:00 PM) |  | APRIL 28, 2025 (10:00 AM) |  | 2025-04-30 | MAY 7-8, 2025 | 2025-05-28 |  |  |  | 2025-03-30 | 2025-06-11 | 2025-06-11 |  |  | on-going delivery |  | Government of the Philippines (current year's budget) | 18000000 |  |  | 17760000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 15, 2025 (2:00 PM) |  | APRIL 28, 2025 (10:00 AM) | 2025-04-30 | MAY 7-8, 2025
SUPPLY AND DELIVERY OF VARIOUS VEHICLES
DA-RFO-1-2025-GOODS-053 | LOT 1: SUPPLY AND DELIVERY OF SEVEN (7) UNITS HAULING VEHICLE | Rice, Corn, Livestock, Organic Agriculture, HVCDP, SAAD and AMIA Program | No | Competitive Bidding | 2025-10-11 | April 21, 2025 to May 13, 2025 |  | APRIL 28, 2025 (1:00 PM) |  | MAY 13, 2025 (9:00 AM) |  | 2025-05-20 | 2025-05-26 | 2025-06-17 |  |  |  | 2025-06-18 | 2025-06-23 | 2025-06-23 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 17500000 |  |  | 17495000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 28, 2025 (1:00 PM) |  | MAY 13, 2025 (9:00 AM) | 2025-05-20 | 2025-05-26
DA-RFO-1-2025-GOODS-053 | LOT 2: SUPPLY AND DELIVERY OF THREE (3) UNITS HAULING TRUCK | Rice, Corn, Livestock, Organic Agriculture, HVCDP, SAAD and AMIA Program | No | Competitive Bidding | 2025-10-11 | April 21, 2025 to May 13, 2025 |  | APRIL 28, 2025 (1:00 PM) |  | MAY 13, 2025 (9:00 AM) |  | 2025-05-20 | 2025-05-27 | 2025-06-17 |  |  |  | 2025-06-18 | 2025-06-23 | 2025-06-23 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 7875000 |  |  | 6360000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 28, 2025 (1:00 PM) |  | MAY 13, 2025 (9:00 AM) | 2025-05-20 | 2025-05-27
DA-RFO-1-2025-GOODS-053 | LOT 4: SUPPLY AND DELIVERY OF ONE (1) UNIT HAULING VEHICLE (CLOSED VAN) | Rice, Corn, Livestock, Organic Agriculture, HVCDP, SAAD and AMIA Program | No | Competitive Bidding | 2025-10-11 | April 21, 2025 to May 13, 2025 |  | APRIL 28, 2025 (1:00 PM) |  | MAY 13, 2025 (9:00 AM) |  | 2025-05-20 | 2025-05-26 | 2025-06-17 |  |  |  | 2025-06-18 | 2025-06-26 | 2025-06-26 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 1400000 |  |  | 1395000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 28, 2025 (1:00 PM) |  | MAY 13, 2025 (9:00 AM) | 2025-05-20 | 2025-05-26 | FOR DELIVERY
DA-RFO-1-2025-GOODS-053 | LOT 6: SUPPLY AND DELIVERY OF TWO (2) UNITS HAULING VEHICLE (DROPSIDE) | Rice, Corn, Livestock, Organic Agriculture, HVCDP, SAAD and AMIA Program | No | Competitive Bidding | 2025-10-11 | April 21, 2025 to May 13, 2025 |  | APRIL 28, 2025 (1:00 PM) |  | MAY 13, 2025 (9:00 AM) |  | 2025-05-20 | 2025-05-27 | 2025-06-17 |  |  |  | 2025-06-18 | 2025-06-26 | 2025-06-26 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 3600000 |  |  | 3520000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 28, 2025 (1:00 PM) |  | MAY 13, 2025 (9:00 AM) | 2025-05-20 | 2025-05-27 | FOR DELIVERY
DA-RFO-1-2025-GOODS-053 | LOT 7: SUPPLY AND DELIVERY OF EIGHT (8) UNITS HAULING VEHICLE | Rice, Corn, Livestock, Organic Agriculture, HVCDP, SAAD and AMIA Program | No | Competitive Bidding | 2025-10-11 | April 21, 2025 to May 13, 2025 |  | APRIL 28, 2025 (1:00 PM) |  | MAY 13, 2025 (9:00 AM) |  | 2025-05-20 | 2025-05-27 | 2025-06-17 |  |  |  | 2025-06-23 | 2025-07-04 | 2025-07-04 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 12000000 |  |  | 10920000 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 28, 2025 (1:00 PM) |  | MAY 13, 2025 (9:00 AM) | 2025-05-20 | 2025-05-27
4313950
4243780
3681510
DA-RFO-1-2025-GOODS-056 | SUPPLY AND DELIVERY OF VARIOUS LABORATORY SUPPLIES | ILD | No | Competitive Bidding | n/a | April 29, 2025 to May 19, 2025 |  | MAY 6, 2025 (1:00 PM) |  | MAY 19, 2025 (1:00 PM) |  | 2025-05-26 | 2025-06-05 | 2025-06-24 |  |  |  | 2025-06-25 | 2025-07-04 | 2025-07-04 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) |  |  |  | 445500 |  |  |  | 1.COA 2.RAFC 3.PCCI | MAY 6, 2025 (1:00 PM) |  | MAY 19, 2025 (1:00 PM) | 2025-05-26 | 2025-06-05
DA-RFO-1-2025-GOODS-056 | SUPPLY AND DELIVERY OF VARIOUS LABORATORY SUPPLIES | ILD | No | Competitive Bidding | n/a | April 29, 2025 to May 19, 2025 |  | MAY 6, 2025 (1:00 PM) |  | MAY 19, 2025 (1:00 PM) |  | 2025-05-26 | 2025-06-05 | 2025-06-24 |  |  |  | 2025-06-25 | 2025-07-04 | 2025-07-04 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) |  |  |  | 1350346 |  |  |  | 1.COA 2.RAFC 3.PCCI | MAY 6, 2025 (1:00 PM) |  | MAY 19, 2025 (1:00 PM) | 2025-05-26 | 2025-06-05
-
-
-
-
-
-
-
-
-
-
[25 empty] | Total Allotted Budget of Procurement Activities | 1755521298.5 | 0 | 0 |  |  |  | 2.614%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 1709625917.03 | 0 | 0
[25 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 45895381.47 | [14 empty] | 2023-06-30
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column42
ONGOING PROCUREMENT ACTIVITIES | [31 empty] | -
DA-RFO-1-2025-GOODS-001-R | REBIDDING OF SUPPLY AND DELIVERY OF FLEET CARD FOR THE DA RFO-1 OFFICIAL VEHICLES IN SOURCING OF FUEL TO BE USED DURING OFFICIAL TRAVELS OF PERSONNEL AND AGRICULTURAL MACHINERIES/EQUIPMENT FOR THE PERIOD JANUARY 1, 2025 TO DECEMBER 31, 2025 | GSS | Yes | Competitive Bidding | 2024-09-27 | November 27, 2024 to December 19, 2024 |  | DECEMBER 4, 2024 |  | DECEMBER 18, 2024 |  | 2024-12-20 | 2024-12-27 | 2025-01-20 | 9 | 33 |  | 2025-01-20 | 2025-02-06 | 2025-02-06 | 17 |  |  |  | Government of the Philippines (current year's budget) | 14400000 |  |  | 14400000 |  |  | 0 | 1.COA 2.RAFC 3.PCCI | DECEMBER 4, 2024 |  | DECEMBER 18, 2024 | 2024-12-20 | 2024-12-27 |  |  | 0
DA-RFO-1-2025-GOODS-002 | PROVISION OF SECURITY SERVICES OF DA RFO 1 FOR THE PERIOD OF JANUARY 1, 2025 TO DECEMBER 31, 2025 | GSS | Yes | Competitive Bidding | 2024-09-27 | October 30, 2024 to November 18, 2024 |  | NOVEMBER 06, 2024 |  | NOVEMBER 18, 2024 |  | 2024-11-26 | 2024-12-02 | 2025-01-20 |  |  |  | 2025-01-20 | 2025-01-27 | 2025-01-27 |  |  |  |  | Government of the Philippines (current year's budget) | 16667040 |  |  | 15217365.12 |  |  |  | 1.COA 2.RAFC 3.PCCI | NOVEMBER 06, 2024 |  | NOVEMBER 18, 2024 | 2024-11-26 | 2024-12-02
DA-RFO-1-2025-GOODS-039 | LOT 1: SUPPLY AND DELIVERY OF ONE HUNDRED SEVENTY THOUSAND SIX HUNDRED FIFTEEN (170,615) BAGS COMPLETE FERTILIZER | RICE | No | Competitive Bidding | 2025-01-16 | February 20, 2025 to March 17, 2025 |  | MARCH 3, 2025 (9:00 AM) |  | MARCH 17, 2025 (9:00 AM) |  | 2025-03-21 | 2025-04-28 | 2025-05-13 |  |  |  | 2025-05-19 | 2025-05-29 | 2025-05-29 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 272984000 |  |  | 272984000 |  |  |  | 1.COA 2.RAFC 3.PCCI | MARCH 3, 2025 (9:00 AM) |  | MARCH 17, 2025 (9:00 AM) | 2025-03-21 | 2025-04-28
DA-RFO-1-2025-GOODS-039-N | NEGOTIATED PROCUREMENT OF LOT 2: SUPPLY AND DELIVERY OF ONE HUNDRED SEVENTY THOUSAND SIX HUNDRED FIFTEEN (170,615) BAGS AMMONIUM SULFATE | RICE | No | Competitive Bidding | 2025-01-16 | July 10-29, 2025 |  | JULY 17, 2025 (10:00 AM) |  | JULY 29, 2025 (10:00 AM) | [14 empty] | Government of the Philippines (current year's budget) | 170615000 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.PCCI | JULY 17, 2025 (10:00 AM) |  | JULY 29, 2025 (10:00 AM)
DA-RFO-1-2025-GOODS-044-N | NEGOTIATED PROCUREMENT OF LOT 4: SUPPLY AND DELIVERY OF FIFTY (50) HEADS UPGRADED CARAHEIFER | OAP | No | Competitive Bidding | 2024-11-12 | June 19, 2025 to July 8, 2025 |  | JUNE 30, 2025 (11:00 AM) |  | JULY 15, 2025 (11:00 AM | [14 empty] | Government of the Philippines (current year's budget) | 4450000 | [6 empty] | 1.COA 2.RAFC 3.PCCI | JUNE 30, 2025 (11:00 AM) |  | JULY 15, 2025 (11:00 AM
DA-RFO-1-2025-GOODS-053 | LOT 3: SUPPLY AND DELIVERY OF FOUR (4) UNITS ANIMAL TRANSPORT VEHICLE | Rice, Corn, Livestock, Organic Agriculture, HVCDP, SAAD and AMIA Program | No | Competitive Bidding | 2025-10-11 | April 21, 2025 to May 13, 2025 |  | APRIL 28, 2025 (1:00 PM) |  | MAY 13, 2025 (9:00 AM) |  | 2025-05-20 | 2025-06-23 | [11 empty] | Government of the Philippines (current year's budget) | 18000000 |  |  | 16128568 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 28, 2025 (1:00 PM) |  | MAY 13, 2025 (9:00 AM) | 2025-05-20 | 2025-06-23
DA-RFO 1-2025-GOODS-053-N | NEGOTIATED PROCUREMENT OF LOT 5: SUPPLY AND DELIVERY OF ONE (1) UNIT HAULING VEHICLE | Rice, Corn, Livestock, Organic Agriculture, HVCDP, SAAD and AMIA Program | No | Competitive Bidding | 2025-10-11 | June 26, 2025 to July 14, 2025 |  | JULY 2, 2025 (9:00 AM) |  | JULY 14, 2025 (1:00 PM) | [14 empty] | Government of the Philippines (current year's budget) | 2000000 | [6 empty] | 1.COA 2.RAFC 3.PCCI | JULY 2, 2025 (9:00 AM) |  | JULY 14, 2025 (1:00 PM)
DA-RFO-1-2025-GOODS-054 | SUPPLY AND DELIVERY OF VARIOUS VEGETABLE SEEDS | HVCDP | No | Competitive Bidding | 2025-01-21 | April 22, 2025 to May 13, 2025 |  | APRIL 29, 2025 (9:00 AM) |  | MAY 13, 2025 (1:00 PM) |  | 2025-05-19 | 2025-05-22 | 2025-06-17 |  |  |  | 2025-06-23 | 2025-06-30 | 2025-06-30 |  |  |  |  | Government of the Philippines (current year's budget) |  |  |  | 4313950 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 29, 2025 (9:00 AM) |  | MAY 13, 2025 (1:00 PM) | 2025-05-19 | 2025-05-22
DA-RFO-1-2025-GOODS-054 | SUPPLY AND DELIVERY OF VARIOUS VEGETABLE SEEDS | HVCDP | No | Competitive Bidding | 2025-01-21 | April 22, 2025 to May 13, 2025 |  | APRIL 29, 2025 (9:00 AM) |  | MAY 13, 2025 (1:00 PM) |  | 2025-05-19 | MAY 22&30, 2025 | 2025-06-17 |  |  |  | 2025-06-23 | FOR SIGNATURE NOA AND CONTRACT (WINNING BIDDER) | [5 empty] | Government of the Philippines (current year's budget) | 12500060 |  |  | 4243780 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 29, 2025 (9:00 AM) |  | MAY 13, 2025 (1:00 PM) | 2025-05-19 | MAY 22&30, 2025
DA-RFO-1-2025-GOODS-054 | SUPPLY AND DELIVERY OF VARIOUS VEGETABLE SEEDS | HVCDP | No | Competitive Bidding | 2025-01-21 | April 22, 2025 to May 13, 2025 |  | APRIL 29, 2025 (9:00 AM) |  | MAY 13, 2025 (1:00 PM) |  | 2025-05-19 | MAY 30-31, 2025 | 2025-06-17 |  |  |  | 2025-06-23 | FOR SIGNATURE NOA AND CONTRACT (WINNING BIDDER) | [5 empty] | Government of the Philippines (current year's budget) |  |  |  | 3681510 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 29, 2025 (9:00 AM) |  | MAY 13, 2025 (1:00 PM) | 2025-05-19 | MAY 30-31, 2025
DA-RFO-1-2025-GOODS-055 | SUPPLY AND DELIVERY OF ONE THOUSAND SIX HUNDRED SIXTY-SIX (1,666) BAGS ORGANIC PLANT SUPPLEMENT | HVCDP | No | Competitive Bidding | 2025-01-21 | April 22, 2025 to May 13, 2025 |  | APRIL 29, 2025 (10:00 AM) |  | MAY 13, 2025 (2:00 PM) |  | 2025-05-19 | 2025-06-10 | 2025-07-08 |  |  |  | 2025-07-08 | [6 empty] | Government of the Philippines (current year's budget) | 2998800 |  |  | 2877182 |  |  |  | 1.COA 2.RAFC 3.PCCI | APRIL 29, 2025 (10:00 AM) |  | MAY 13, 2025 (2:00 PM) | 2025-05-19 | 2025-06-10
DA-RFO-1-2025-GOODS-056 | SUPPLY AND DELIVERY OF VARIOUS LABORATORY SUPPLIES | ILD | No | Competitive Bidding | n/a | April 29, 2025 to May 19, 2025 |  | MAY 6, 2025 (1:00 PM) |  | MAY 19, 2025 (1:00 PM) |  | 2025-05-26 | 2025-06-05 | 2025-06-24 |  |  |  | 2025-06-25 | FOR APPROVAL OF CONTRACT | [5 empty] | Government of the Philippines (current year's budget) | 1451360 |  |  | 958600 |  |  |  | 1.COA 2.RAFC 3.PCCI | MAY 6, 2025 (1:00 PM) |  | MAY 19, 2025 (1:00 PM) | 2025-05-26 | 2025-06-05
DA-RFO 1-2025-GOODS-059 | PROVISION OF ONE (1) LOT DEDICATED WIRED FIBER INTERNET CONNECTION AT DA-RFO 1 FOR THE PERIOD OF JULY 2025 TO DECEMBER 2025 | IMS | No | Competitive Bidding | 2025-04-30 | May 26, 2025 to June 3, 2025 |  | JUNE 3, 2025 (9:00 AM) |  | JUNE 17, 2025 (9:00 AM) |  | 2025-06-17 | 2025-06-27 | FOR SIGNATURE OF BAC RES & NOA (ORED) | [10 empty] | Government of the Philippines (current year's budget) | 1255000 |  |  | 693912 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 3, 2025 (9:00 AM) |  | JUNE 17, 2025 (9:00 AM) | 2025-06-17 | 2025-06-27
DA-RFO 1-2025-GOODS-060 | SUPPLY AND DELIVERY OF VARIOUS SEEDLINGS | HVCDP | No | Competitive Bidding | 2024-10-01 | May 26, 2025 to June 3, 2025 |  | JUNE 3, 2025 (10:00 AM) |  | JUNE 17, 2025 (10:00 AM) |  | 2025-06-17 | 2025-06-23 | 2025-06-27 |  |  |  | 2025-06-27 | [6 empty] | Government of the Philippines (current year's budget) | 3077250 |  |  | 615615 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 3, 2025 (10:00 AM) |  | JUNE 17, 2025 (10:00 AM) | 2025-06-17 | 2025-06-23
DA-RFO 1-2025-GOODS-060 | SUPPLY AND DELIVERY OF VARIOUS SEEDLINGS | HVCDP and 4KProgram | No | Competitive Bidding | 2024-10-01 | May 26, 2025 to June 3, 2025 |  | JUNE 3, 2025 (10:00 AM) |  | JUNE 17, 2025 (10:00 AM) |  | 2025-06-17 | 2025-06-23 | 2025-06-27 |  |  |  | 2025-06-27 | [6 empty] | Government of the Philippines (current year's budget) |  |  |  | 2391250 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 3, 2025 (10:00 AM) |  | JUNE 17, 2025 (10:00 AM) | 2025-06-17 | 2025-06-23
DA-RFO-1-2025-GOODS-061 | SUPPLY AND DELIVERY OF VARIOUS INORGANIC FERTILIZERS | RICE | No | Competitive Bidding | 2025-05-19 | June 10, 2025 to July 1, 2025 |  | JUNE 19, 2025 (9:00 AM) |  | JULY 1, 2025 (9:00 AM) |  | 2025-07-01 | AWAITING POST-QUAL REPORT | [11 empty] | Government of the Philippines (current year's budget) | 16600000 |  |  | 16102000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 19, 2025 (9:00 AM) |  | JULY 1, 2025 (9:00 AM) | 2025-07-01
SUPPLY AND DELIVERY OF VARIOUS HYBRID PALAY SEEDS
DA-RFO-1-2025-GOODS-062 | LOT 1: SUPPLY AND DELIVERY OF FIVE HUNDRED (500) BAGS HYBRID PALAY SEEDS (NSIC Rc456H) | RICE | No | Competitive Bidding | 2025-05-19 | June 10, 2025 to July 1, 2025 |  | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) |  | 2025-07-01 | AWAITING POST-QUAL REPORT | [11 empty] | Government of the Philippines (current year's budget) | 2500000 |  |  | 2500000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) | 2025-07-01
DA-RFO-1-2025-GOODS-062 | LOT 2: SUPPLY AND DELIVERY OF TWO THOUSAND FOUR HUNDRED EIGHTY-NINE (2,489) BAGS HYBRID PALAY SEEDS (NSIC Rc486H) | RICE | No | Competitive Bidding | 2025-05-19 | June 10, 2025 to July 1, 2025 |  | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) |  | 2025-07-01 | AWAITING POST-QUAL REPORT | [11 empty] | Government of the Philippines (current year's budget) | 12445000 |  |  | 12445000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) | 2025-07-01
DA-RFO-1-2025-GOODS-062 | LOT 3: SUPPLY AND DELIVERY OF THIRTEEN THOUSAND EIGHT HUNDRED FORTY-TWO (13,842) BAGS HYBRID PALAY SEEDS (NSIC Rc234H) | RICE | No | Competitive Bidding | 2025-05-19 | June 10, 2025 to July 1, 2025 |  | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) |  | 2025-07-01 | AWAITING POST-QUAL REPORT | [11 empty] | Government of the Philippines (current year's budget) | 69210000 |  |  | 69210000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) | 2025-07-01
DA-RFO-1-2025-GOODS-062 | LOT 4: SUPPLY AND DELIVERY OF THIRTEEN THOUSAND THREE HUNDRED FIVE (13,305) BAGS HYBRID PALAY SEEDS (NSIC Rc376H) | RICE | No | Competitive Bidding | 2025-05-19 | June 10, 2025 to July 1, 2025 |  | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) |  | 2025-07-01 | AWAITING POST-QUAL REPORT | [11 empty] | Government of the Philippines (current year's budget) | 66525000 |  |  | 66525000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) | 2025-07-01
DA-RFO-1-2025-GOODS-062 | LOT 5: SUPPLY AND DELIVERY OF TWO THOUSAND NINE HUNDRED TWENTY (2,920) BAGS HYBRID PALAY SEEDS (NSIC Rc548H) | RICE | No | Competitive Bidding | 2025-05-19 | June 10, 2025 to July 1, 2025 |  | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) |  | 2025-07-01 | AWAITING POST-QUAL REPORT | [11 empty] | Government of the Philippines (current year's budget) | 14600000 |  |  | 14600000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) | 2025-07-01
DA-RFO-1-2025-GOODS-062 | LOT 6: SUPPLY AND DELIVERY OF SIX THOUSAND THREE HUNDRED NINETY (6,390) BAGS HYBRID PALAY SEEDS (NSIC Rc546H) | RICE | No | Competitive Bidding | 2025-05-19 | June 10, 2025 to July 1, 2025 |  | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) |  | 2025-07-01 | AWAITING POST-QUAL REPORT | [11 empty] | Government of the Philippines (current year's budget) | 31950000 |  |  | 31950000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) | 2025-07-01
DA-RFO-1-2025-GOODS-062 | LOT 7: SUPPLY AND DELIVERY OF SIX THOUSAND THREE HUNDRED NINETY (6,390) BAGS HYBRID PALAY SEEDS (NSIC Rc524H) | RICE | No | Competitive Bidding | 2025-05-19 | June 10, 2025 to July 1, 2025 |  | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) |  | 2025-07-01 | AWAITING POST-QUAL REPORT | [11 empty] | Government of the Philippines (current year's budget) | 31950000 |  |  | 31950000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) | 2025-07-01
DA-RFO-1-2025-GOODS-062 | LOT 8: SUPPLY AND DELIVERY OF TWO THOUSAND EIGHT HUNDRED FIFTY-TWO (2,852) BAGS HYBRID PALAY SEEDS (NSIC Rc132H) | RICE | No | Competitive Bidding | 2025-05-19 | June 10, 2025 to July 1, 2025 |  | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) |  | 2025-07-01 | AWAITING POST-QUAL REPORT | [11 empty] | Government of the Philippines (current year's budget) | 14260000 |  |  | 14260000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) | 2025-07-01
DA-RFO-1-2025-GOODS-062 | LOT 9: SUPPLY AND DELIVERY OF FOUR THOUSAND FOUR HUNDRED TWENTY-TWO (4,422) BAGS HYBRID PALAY SEEDS (NSIC Rc350H) | RICE | No | Competitive Bidding | 2025-05-19 | June 10, 2025 to July 1, 2025 |  | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) |  | 2025-07-01 | AWAITING POST-QUAL REPORT | [11 empty] | Government of the Philippines (current year's budget) | 22110000 |  |  | 22110000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) | 2025-07-01
DA-RFO-1-2025-GOODS-062 | LOT 10: SUPPLY AND DELIVERY OF TWELVE THOUSAND TWO HUNDRED TWENTY-ONE (12,221) BAGS HYBRID PALAY SEEDS (NSIC Rc666H) | RICE | No | Competitive Bidding | 2025-05-19 | June 10, 2025 to July 1, 2025 |  | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) |  | 2025-07-01 | AWAITING POST-QUAL REPORT | [11 empty] | Government of the Philippines (current year's budget) | 61105000 |  |  | 61105000 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 19, 2025 (10:00 AM) |  | JULY 1, 2025 (10:00 AM) | 2025-07-01
SUPPLY AND DELIVERY OF FOUR HUNDRED THOUSAND (400,000) KILOGRAMS CERTIFIED PALAY SEEDS
DA-RFO-1-2025-GOODS-064 | LOT 1: SUPPLY AND DELIVERY OF TWO HUNDRED FORTY THOUSAND (240,000) KILOGRAMS CERTIFIED PALAY SEEDS FOR PANGASINAN | RICE | No | Competitive Bidding | 2024-10-03 | June 23, 2025 to July 15, 2025 |  | JUNE 30, 2025 (9:00 AM) |  | JULY 15, 2025 (9:00 AM | [14 empty] | Government of the Philippines (current year's budget) | 10560000 |  |  | 0 |  |  | - | 1.COA 2.RAFC 3.PCCI | JUNE 30, 2025 (9:00 AM) |  | JULY 15, 2025 (9:00 AM |  |  |  |  | 0
DA-RFO-1-2025-GOODS-064 | LOT 2: SUPPLY AND DELIVERY OF FORTY THOUSAND (40,000) KILOGRAMS CERTIFIED PALAY SEEDS FOR LA UNION | RICE | No | Competitive Bidding | 2024-10-03 | June 23, 2025 to July 15, 2025 |  | JUNE 30, 2025 (9:00 AM) |  | JULY 15, 2025 (9:00 AM | [14 empty] | Government of the Philippines (current year's budget) | 1760000 |  |  | 0 |  |  | - | 1.COA 2.RAFC 3.PCCI | JUNE 30, 2025 (9:00 AM) |  | JULY 15, 2025 (9:00 AM |  |  |  |  | 0
DA-RFO-1-2025-GOODS-064 | LOT 3: SUPPLY AND DELIVERY OF FORTY THOUSAND (40,000) KILOGRAMS CERTIFIED PALAY SEEDS FOR ILOCOS SUR | RICE | No | Competitive Bidding | 2024-10-03 | June 23, 2025 to July 15, 2025 |  | JUNE 30, 2025 (9:00 AM) |  | JULY 15, 2025 (9:00 AM | [14 empty] | Government of the Philippines (current year's budget) | 1760000 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 30, 2025 (9:00 AM) |  | JULY 15, 2025 (9:00 AM
DA-RFO-1-2025-GOODS-064 | LOT 4: SUPPLY AND DELIVERY OF EIGHTY THOUSAND (80,000) KILOGRAMS CERTIFIED PALAY SEEDS FOR ILOCOS NORTE | RICE | No | Competitive Bidding | 2024-10-03 | June 23, 2025 to July 15, 2025 |  | JUNE 30, 2025 (9:00 AM) |  | JULY 15, 2025 (9:00 AM | [14 empty] | Government of the Philippines (current year's budget) | 3520000 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 30, 2025 (9:00 AM) |  | JULY 15, 2025 (9:00 AM
DA-RFO 1-2025-GOODS-065 | SUPPLY AND DELIVERY OF ONE (1) LOT BREEDER GOAT, RUMINANT FEEDS AND CORN SILAGE | Livestock | No | Competitive Bidding | 2025-05-27 | June 23, 2025 to July 15, 2025 |  | JUNE 30, 2025 (10:00 AM) |  | JULY 15, 2025 (10:00 AM | [14 empty] | Government of the Philippines (current year's budget) | 27753000 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 30, 2025 (10:00 AM) |  | JULY 15, 2025 (10:00 AM
DA-RFO 1-2025-GOODS-066 | SUPPLY AND DELIVERY OF ONE (1) LOT TECHNICAL AND SCIENTIFIC EQUIPMENT | ISReC | No | Competitive Bidding | 2025-05-27 | June 23, 2025 to July 15, 2025 |  | JUNE 30, 2025 (1:00 PM) |  | JULY 15, 2025 (1:00 PM | [14 empty] | Government of the Philippines (current year's budget) | 2575000 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.PCCI | JUNE 30, 2025 (1:00 PM) |  | JULY 15, 2025 (1:00 PM
DA-RFO 1-2025-GOODS-067 | SUPPLY AND DELIVERY OF ONE (1) LOT BREEDER CATTLE AND RUMINANT FEEDS | Livestock | No | Competitive Bidding | 2025-05-27 | June 30, 2025 to July 21, 2025 |  | JULY 7, 2025 (1:00 PM) |  | JULY 21, 2025 (1:00 PM) | [14 empty] | Government of the Philippines (current year's budget) | 34353900 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.PCCI | JULY 7, 2025 (1:00 PM) |  | JULY 21, 2025 (1:00 PM)
DA-RFO 1-2025-GOODS-068 | SUPPLY AND DELIVERY OF FIFTY-EIGHT (58) UNITS FORAGE CHOPPER | Livestock | No | Competitive Bidding | 2025-05-27 | June 30, 2025 to July 21, 2025 |  | JULY 7, 2025 (2:00 PM) |  | JULY 21, 2025 (2:00 PM) | [14 empty] | Government of the Philippines (current year's budget) | 6960000 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.PCCI | JULY 7, 2025 (2:00 PM) |  | JULY 21, 2025 (2:00 PM)
DA-RFO 1-2025-GOODS-069 | SUPPLY AND DELIVERY OF TWO HUNDRED SEVENTY-THREE THOUSAND SEVEN HUNDRED THREE (273,703) BOTTLES INORGANIC LIQUID FERTILIZER | RICE | No | Competitive Bidding | JUNE 30, 2025 | July 4-28, 2025 |  | JULY 14, 2025 (2:00 PM) |  | JULY 28, 2025 (9:00 AM) | [14 empty] | Government of the Philippines (current year's budget) | 273703000 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.PCCI | JULY 14, 2025 (2:00 PM) |  | JULY 28, 2025 (9:00 AM)
DA RFO-1-2025-INFRA-001-R | REBIDDING OF PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF LIVESTOCK HOUSING FACILITY (BEEF CATTLE) IN REGION 1 | OAP | Yes | Competitive Bidding | 2024-10-02 | December 13, 2024 to January 07, 2025 |  | DECEMBER 20, 2024 (3:00 PM) |  | JANUARY 21, 2025 (1:00 PM) |  | 2025-01-28 | February 7, 2025 | 2025-02-14 |  |  |  | 2025-02-14 | 2025-03-06 | 2025-03-06 |  |  | FOR CONSTRUCTION; AWAITING ISSUANCE OF ECC |  | Government of the Philippines (current year's budget) | 1000000 |  |  | 918857.9 |  |  |  | 1.COA 2.RAFC 3.CIAP | DECEMBER 20, 2024 (3:00 PM) |  | JANUARY 21, 2025 (1:00 PM) | 2025-01-28 | February 7, 2025
PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF LIVESTOCK HOUSING FACILITY (DAIRY BUFFALO) IN REGION 1
DA-RFO-1-2025-INFRA-002 | LOT 1: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF LIVESTOCK HOUSING FACILITY (DAIRY BUFFALO) IN BRGY. WAREY, MALASIQUI, PANGASINAN | OAP | Yes | Competitive Bidding | 2024-10-02 | November 13 2024 to December 2, 2024 |  | NOVEMBER 20, 2024 (3:00 PM) |  | DECEMBER 2, 2024 (3:00 PM) |  | 2024-12-04 | 2024-12-13 | 2025-01-20 |  |  |  | 2025-01-21 | 2025-02-10 | 2025-02-10 |  |  | FOR CONSTRUCTION; AWAITING ISSUANCE OF ECC |  | Government of the Philippines (current year's budget) | 1000000 |  |  | 960988.74 |  |  |  | 1.COA 2.RAFC 3.CIAP | NOVEMBER 20, 2024 (3:00 PM) |  | DECEMBER 2, 2024 (3:00 PM) | 2024-12-04 | 2024-12-13
DA-RFO-1-2025-INFRA-002 | LOT 2: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF LIVESTOCK HOUSING FACILITY (DAIRY BUFFALO) IN BRGY. BANAOANG, STA. BARBARA, PANGASINAN | OAP | Yes | Competitive Bidding | 2024-10-02 | November 13 2024 to December 2, 2024 |  | NOVEMBER 20, 2024 (3:00 PM) |  | DECEMBER 2, 2024 (3:00 PM) |  | 2024-12-04 | 2024-12-12 | 2025-01-20 |  |  |  | 2025-01-21 | 2025-02-10 | 2025-02-10 |  |  | FOR CONSTRUCTION; AWAITING ISSUANCE OF ECC |  | Government of the Philippines (current year's budget) | 1000000 |  |  | 948146.36 |  |  |  | 1.COA 2.RAFC 3.CIAP | NOVEMBER 20, 2024 (3:00 PM) |  | DECEMBER 2, 2024 (3:00 PM) | 2024-12-04 | 2024-12-12
DA RFO-1-2025-INFRA-003 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE EXTENSION OF LIPAY IRRIGATION CANAL IN BRGY. SAN JOSE AND STO.TOMAS, VINTAR ILOCOS NORTE | RAED | Yes | Competitive Bidding | 2024-10-01 | November 22, 2024 to December 11, 2024 |  | 29-Nov-2024 9:00 AM |  | 11-Dec-2024 9:00 AM |  | 2024-12-16 | 2025-01-28 | 2025-02-12 |  |  |  | 2025-02-14 | 2025-02-27 | 2025-02-27 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 8913135.14 |  |  | 7602216.26 |  |  |  | 1.COA 2.RAFC 3.CIAP | 29-Nov-2024 9:00 AM |  | 11-Dec-2024 9:00 AM | 2024-12-16 | 2025-01-28
DA RFO-1-2025-INFRA-004 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE EXTENSION OF LANCUAS IRRIGATION CANAL IN BRGY. LANCUAS, SAN EMILIO, ILOCOS SUR | RAED | Yes | Competitive Bidding | 2024-10-01 | November 22, 2024 to December 11, 2024 |  | 29-Nov-2024 10:00 AM |  | 11-Dec-2024 10:00 AM |  | 2024-12-16 | 2025-12-20 | 2025-01-20 |  |  |  | 2025-01-21 | 2025-02-10 | 2025-02-10 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 1485000 |  |  | 1269827.49 |  |  |  | 1.COA 2.RAFC 3.CIAP | 29-Nov-2024 10:00 AM |  | 11-Dec-2024 10:00 AM | 2024-12-16 | 2025-12-20
DA RFO-1-2025-INFRA-005 | LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF BANI SOLAR-POWERED IRRIGATION SYSTEM (SPIS) IN BRGY. BANI, SANTA LUCIA, ILOCOS SUR | RAED | Yes | Competitive Bidding | 2024-10-01 | November 22, 2024 to December 11, 2024 |  | 29-Nov-2024 11:00 AM |  | 11-Dec-2024 11:00 AM |  | 2024-12-16 | 2025-12-20 | 2025-01-20 |  |  |  | 2025-01-21 | 2025-02-10 | 2025-02-10 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 6336000.1 |  |  | 6335617.65 |  |  |  | 1.COA 2.RAFC 3.CIAP | 29-Nov-2024 11:00 AM |  | 11-Dec-2024 11:00 AM | 2024-12-16 | 2025-12-20
DA RFO-1-2025-INFRA-006 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE REHABILITATION OF INLAMBO SOLAR-POWERED IRRIGATION SYSTEM (SPIS) IN BRGY. INLAMBO, MANGALDAN, PANGASINAN | RAED | Yes | Competitive Bidding | 2024-10-01 | November 22, 2024 to December 11, 2024 |  | 29-Nov-2024 1:00 PM |  | 11-Dec-2024 1:00 PM |  | 2024-12-16 | 2025-12-20 | 2025-01-20 |  |  |  | 2025-01-21 | 2025-02-10 | 2025-02-10 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 2869047.64 |  |  | 2868878.34 |  |  |  | 1.COA 2.RAFC 3.CIAP | 29-Nov-2024 1:00 PM |  | 11-Dec-2024 1:00 PM | 2024-12-16 | 2025-12-20
DA RFO-1-2025-INFRA-007 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF WAREHOUSE IN BRGY. CALAOCAN, SAN NICOLAS, PANGASINAN | RAED | Yes | Competitive Bidding | 2024-10-01 | November 22, 2024 to December 11, 2024 |  | 29-Nov-2024 2:00 PM |  | 11-Dec-2024 2:00 PM |  | 2024-12-16 | 2025-12-18 | 2025-01-20 |  |  |  | 2025-01-21 | 2025-02-07 | 2025-02-07 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 5939948.11 |  |  | 5077261.07 |  |  |  | 1.COA 2.RAFC 3.CIAP | 29-Nov-2024 2:00 PM |  | 11-Dec-2024 2:00 PM | 2024-12-16 | 2025-12-18
DA RFO-1-2025-INFRA-008 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF WAREHOUSE IN BRGY. PINDANGAN EAST, ALCALA, PANGASINAN | RAED | Yes | Competitive Bidding | 2024-10-01 | November 22, 2024 to December 11, 2024 |  | 29-Nov-2024 3:00 PM |  | 11-Dec-2024 3:00 PM |  | 2024-12-16 | 2025-12-18 | 2025-01-20 |  |  |  | 2025-01-21 | 2025-02-03 | 2025-02-06 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 5939948.11 |  |  | 5612454.27 |  |  |  | 1.COA 2.RAFC 3.CIAP | 29-Nov-2024 3:00 PM |  | 11-Dec-2024 3:00 PM | 2024-12-16 | 2025-12-18
DA RFO-1-2025-INFRA-009 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF WAREHOUSE IN BRGY. STA. LUCIA, ARINGAY, LA UNION | RAED | Yes | Competitive Bidding | 2024-10-01 | November 22, 2024 to December 11, 2024 |  | 29-Nov-2024 4:00 PM |  | 11-Dec-2024 4:00 PM |  | 2024-12-16 | 2025-12-18 | 2025-01-20 |  |  |  | 2025-01-21 | 2025-02-10 | 2025-02-14 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 5939948.11 |  |  | 5077261.07 |  |  |  | 1.COA 2.RAFC 3.CIAP | 29-Nov-2024 4:00 PM |  | 11-Dec-2024 4:00 PM | 2024-12-16 | 2025-12-18
DA RFO-1-2025-INFRA-010 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR CONSTRUCTION OF CAOIGE DIVERSION DAM CANAL LINING IN BRGY. CAOIGE, TUBAO, LA UNION | RAED | No | Competitive Bidding | 2024-10-01 | January 13, 2025 to February 4, 2025 |  | JANUARY 23, 2025 (9:00 AM) |  | FEBRUARY 4, 2025 (9:00 AM) |  | 2025-02-06 | 2025-03-13 | 2025-04-07 |  |  |  | 2025-04-08 | 2025-04-25 | 2025-04-25 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 2475185.16 |  |  | 2162882.38 |  |  |  | 1.COA 2.RAFC 3.CIAP | JANUARY 23, 2025 (9:00 AM) |  | FEBRUARY 4, 2025 (9:00 AM) | 2025-02-06 | 2025-03-13
DA RFO-1-2025-INFRA-011 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE EXTENSION OF SAN MANUEL PAG-ASA SWISA DIVERSION DAM IRRIGATION CANAL IN BRGY. ARZADON, SAN MANUEL, PANGASINAN | RAED | No | Competitive Bidding | 2024-10-01 | January 13, 2025 to February 4, 2025 |  | JANUARY 23, 2025 (10:00 AM) |  | FEBRUARY 4, 2025 (10:00 AM) |  | 2025-02-06 | 2025-02-11 | 2025-03-04 |  |  |  | 2025-03-04 | 2025-03-24 | 2025-03-24 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 2375980.08 |  |  | 2018602.56 |  |  |  | 1.COA 2.RAFC 3.CIAP | JANUARY 23, 2025 (10:00 AM) |  | FEBRUARY 4, 2025 (10:00 AM) | 2025-02-06 | 2025-02-11
DA RFO-1-2025-INFRA-012 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE EXTENSION OF MARUAYA IRRIGATION CANAL IN BRGY. MARUAYA, PIDDIG, ILOCOS NORTE | RAED | No | Competitive Bidding | 2024-10-01 | January 13, 2025 to February 4, 2025 |  | JANUARY 23, 2025 (11:00 AM) |  | FEBRUARY 4, 2025 (11:00 AM) |  | 2025-02-06 | 2025-02-21 | 2025-01-20 |  |  |  | 2025-03-11 | 2025-03-27 | 2025-03-27 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 2178329.59 |  |  | 1885348.09 |  |  |  | 1.COA 2.RAFC 3.CIAP | JANUARY 23, 2025 (11:00 AM) |  | FEBRUARY 4, 2025 (11:00 AM) | 2025-02-06 | 2025-02-21
DA RFO-1-2025-INFRA-013 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE REHABILITATION AND EXTENSION OF BACSIL NORTH DIVERSION DAM II IRRIGATION CANAL IN BRGY. BACSIL NORTH, LAOAG CITY, ILOCOS NORTE | RAED | No | Competitive Bidding | 2024-10-01 | January 13, 2025 to February 4, 2025 |  | JANUARY 23, 2025 (1:00 PM) |  | JANUARY 23, 2025 (1:00 PM) |  | 2025-02-06 | 2025-03-12 | 2025-03-27 |  |  |  | 2025-05-20 | 2025-04-07 | 2025-04-07 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 2177237.27 |  |  | 1815446.43 |  |  |  | 1.COA 2.RAFC 3.CIAP | JANUARY 23, 2025 (1:00 PM) |  | JANUARY 23, 2025 (1:00 PM) | 2025-02-06 | 2025-03-12
DA RFO-1-2025-INFRA-014 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF SAN MARCELINO SOLAR-POWERED IRRIGATION SYSTEM (SPIS) IN BRGY. SAN MARCELINO, DINGRAS, ILOCOS NORTE | RAED | No | Competitive Bidding | 2024-10-01 | January 13, 2025 to February 4, 2025 |  | JANUARY 23, 2025 (2:00 PM) |  | FEBRUARY 4, 2025 (2:00 PM) |  | 2025-02-06 | 2025-02-11 | 2025-03-05 |  |  |  | 2025-03-11 | 2025-03-31 | 2025-03-31 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 6929691.05 |  |  | 6928874.07 |  |  |  | 1.COA 2.RAFC 3.CIAP | JANUARY 23, 2025 (2:00 PM) |  | FEBRUARY 4, 2025 (2:00 PM) | 2025-02-06 | 2025-02-11
DA RFO-1-2025-INFRA-015 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF ARING SOLAR-POWERED IRRIGATION SYSTEM (SPIS) IN BRGY. ARING, BADOC, ILOCOS NORTE | RAED | No | Competitive Bidding | 2024-10-01 | January 14, 2025 to February 4, 2025 |  | JANUARY 23, 2025 (3:00 PM) |  | FEBRUARY 4, 2025 (3:00 PM) |  | 2025-02-06 | 2025-02-11 | 2025-03-11 |  |  |  | 2025-03-11 | 2025-03-28 | 2025-03-31 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 2969837.46 |  |  | 2968877.97 |  |  |  | 1.COA 2.RAFC 3.CIAP | JANUARY 23, 2025 (3:00 PM) |  | FEBRUARY 4, 2025 (3:00 PM) | 2025-02-06 | 2025-02-11
DA RFO-1-2025-INFRA-016 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF PERIMETER FENCE WITH GATE, WAITING SHED AND GUARD HOUSE AT DA-ISREC, SAN JUAN, ILOCOS SUR | ISRec | No | Competitive Bidding | 2024-10-01 | January 13, 2025 to February 5, 2025 |  | JANUARY 24, 2025 (9:00 AM) |  | FEBRUARY 5, 2025 (9:00 AM) |  | 2025-02-06 | 2025-02-21 | 2025-03-10 |  |  |  | 2025-03-11 | 2025-03-19 | 2025-03-21 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 6999956 |  |  | 6083610.45 |  |  |  | 1.COA 2.RAFC 3.CIAP | JANUARY 24, 2025 (9:00 AM) |  | FEBRUARY 5, 2025 (9:00 AM) | 2025-02-06 | 2025-02-21
DA-RFO 1-2025-INFRA-017-N | SECOND NEGOTIATED PROCUREMENT OF PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE IMPROVEMENT OF GOAT BREEDER HOUSE AT DA-INREC, DINGRAS, ILOCOS NORTE | DA-INREC | No | Competitive Bidding | 2024-10-01 | June 3 to 18, 2025 |  | June 10, 2025 (10:00 A.M) |  | June 18, 2025 (10:00 A.M) |  | 2025-06-19 | 2025-06-26 | 2025-07-03 |  |  |  | 2025-07-08 | FOR SIGNATURE NOA AND CONTRACT (WINNING BIDDER) | [5 empty] | Government of the Philippines (current year's budget) | 1500000 |  |  | 1367994.08 |  |  |  | 1.COA 2.RAFC 3.CIAP | June 10, 2025 (10:00 A.M) |  | June 18, 2025 (10:00 A.M) | 2025-06-19 | 2025-06-26
DA-RFO 1-2025-INFRA-018-N | SECOND NEGOTIATED PROCUREMENT OF PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE REPAIR AND MAINTENANCE OF DUPLEX BUILDING AT DA-INREC, DINGRAS, ILOCOS NORTE | DA-INREC | No | Competitive Bidding | 2024-10-01 | June 3 to 18, 2025 |  | June 10, 2025 (11:00 A.M) |  | June 18, 2025 (11:00 A.M) |  | 2025-06-19 | 2025-06-26 | 2025-07-03 |  |  |  | 2025-07-08 | FOR SIGNATURE NOA AND CONTRACT (WINNING BIDDER) | [5 empty] | Government of the Philippines (current year's budget) | 1385069 |  |  | 1367994.08 |  |  |  | 1.COA 2.RAFC 3.CIAP | June 10, 2025 (11:00 A.M) |  | June 18, 2025 (11:00 A.M) | 2025-06-19 | 2025-06-26
DA RFO-1-2025-INFRA-020 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF LIVESTOCK HOUSING FACILITY (BEEF CATTLE) IN BRGY. MALIMPIN, DASOL, PANGASINAN | OAP | No | Competitive Bidding | 2024-10-02 | January 30, 2025 - February 18, 2025 |  | FEBRUARY 6, 2025 (2:00 PM) |  | FEBRUARY 18, 2025 (2:00 PM) |  | 2025-02-26 | 2025-03-07 | 2025-03-24 |  |  |  | 2025-03-24 | 2025-04-07 | 2025-04-07 |  |  | FOR CONSTRUCTION; AWAITING ISSUANCE OF ECC |  | Government of the Philippines (current year's budget) | 1000000 |  |  | 997787.5 |  |  |  | 1.COA 2.RAFC 3.CIAP | FEBRUARY 6, 2025 (2:00 PM) |  | FEBRUARY 18, 2025 (2:00 PM) | 2025-02-26 | 2025-03-07
DA-RFO 1-2025-INFRA-021 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF GOAT BREEDER HOUSE IN POBLACION WEST, NATIVIDAD, PANGASINAN | LIVESTOCK | No | Competitive Bidding | 2024-07-02 | February 5-26, 2025 |  | FEBRUARY 12, 2025 (10:00 AM) |  | FEBRUARY 26, 2025 (10:00 AM) |  | 2025-02-28 | 2025-03-07 | 2025-03-25 |  |  |  | 2025-03-26 | 2025-03-31 | 2025-03-31 |  |  | ONGOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 1700000 |  |  | 1554208.03 |  |  |  | 1.COA 2.RAFC 3.CIAP | FEBRUARY 12, 2025 (10:00 AM) |  | FEBRUARY 26, 2025 (10:00 AM) | 2025-02-28 | 2025-03-07
DA-RFO 1-2025-INFRA-022 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF FRUITS AND VEGETABLES DEHYDRATION PROCESSING FACILITY AT BRGY. DON ALEJANDRO QUIROLGICO, CAOAYAN, ILOCOS SUR | HVCDP | No | Competitive Bidding | 2024-11-04 | February 12, 2025 to March 4, 2025 |  | FEBRUARY 20, 2025 (9:00 AM) |  | MARCH 4, 2025 (9:00 AM) |  | 2025-03-11 | 2025-03-17 | 2025-03-27 |  |  |  | 2025-03-27 | 2025-03-27 | 2025-03-27 |  |  | ONGOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 5940000.75 |  |  | 5213155.54 |  |  |  | 1.COA 2.RAFC 3.CIAP | FEBRUARY 20, 2025 (9:00 AM) |  | MARCH 4, 2025 (9:00 AM) | 2025-03-11 | 2025-03-17
PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION UNDER THE HIGH VALUE CROPS (HVC) BANNER PROGRAM IN REGION 1
DA-RFO-1-2025-INFRA-023 | LOT 1: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF ONE (1) UNIT SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION IN BRGY. CATUDAY, BOLINAO, PANGASINAN | HVCDP | No | Competitive Bidding | 2024-10-02 | February 12, 2025 to March 4, 2025 |  | FEBRUARY 20, 2025 (10:00 AM) |  | MARCH 4, 2025 (10:00 AM) |  | 2025-03-11 | 2025-03-11 | 2025-03-26 |  |  |  | 2025-03-26 | 2025-03-27 | 2025-03-27 |  |  | ONGOING INSTALLATION |  | Government of the Philippines (current year's budget) | 1484996.07 |  |  | 1409261.27 |  |  |  | 1.COA 2.RAFC 3.CIAP | FEBRUARY 20, 2025 (10:00 AM) |  | MARCH 4, 2025 (10:00 AM) | 2025-03-11 | 2025-03-11
DA-RFO-1-2025-INFRA-023 | LOT 2: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF TWO (2) UNITS SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION IN BRGY. OLEA, MALASIQUI, PANGASINAN AND BRGY. NELINTAP, SAN CARLOS CITY, PANGASINAN | HVCDP | No | Competitive Bidding | 2024-10-02 | February 12, 2025 to March 4, 2025 |  | FEBRUARY 20, 2025 (10:00 AM) |  | MARCH 4, 2025 (10:00 AM) |  | 2025-03-11 | 2025-03-11 | 2025-03-26 |  |  |  | 2025-03-26 | 2025-03-27 | 2025-03-27 |  |  | ONGOING INSTALLATION |  | Government of the Philippines (current year's budget) | 2969992.14 |  |  | 2818522.54 |  |  |  | 1.COA 2.RAFC 3.CIAP | FEBRUARY 20, 2025 (10:00 AM) |  | MARCH 4, 2025 (10:00 AM) | 2025-03-11 | 2025-03-11
DA-RFO-1-2025-INFRA-023 | LOT 3: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF TWO (2) UNITS SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION IN BRGY. CABANBAN, MANAOAG, PANGASINAN AND BRGY. MACAAYUG, MANGALDAN, PANGASINAN | HVCDP | No | Competitive Bidding | 2024-10-02 | February 12, 2025 to March 4, 2025 |  | FEBRUARY 20, 2025 (10:00 AM) |  | MARCH 4, 2025 (10:00 AM) |  | 2025-03-11 | 2025-03-11 | 2025-03-26 |  |  |  | 2025-03-26 | 2025-03-27 | 2025-03-27 |  |  | ONGOING INSTALLATION |  | Government of the Philippines (current year's budget) | 2969992.14 |  |  | 2818522.54 |  |  |  | 1.COA 2.RAFC 3.CIAP | FEBRUARY 20, 2025 (10:00 AM) |  | MARCH 4, 2025 (10:00 AM) | 2025-03-11 | 2025-03-11
DA-RFO-1-2025-INFRA-023 | LOT 4: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF TWO (2) UNITS SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION IN BRGY. PALINA WEST, URDANETA CITY, PANGASINAN AND BRGY. TOKETEK, TAYUG, PANGASINAN | HVCDP | No | Competitive Bidding | 2024-10-02 | February 12, 2025 to March 4, 2025 |  | FEBRUARY 20, 2025 (10:00 AM) |  | MARCH 4, 2025 (10:00 AM) |  | 2025-03-11 | 2025-03-11 | 2025-03-26 |  |  |  | 2025-03-26 | 2025-03-27 | 2025-03-27 |  |  | ONGOING INSTALLATION |  | Government of the Philippines (current year's budget) | 2969992.14 |  |  | 2818522.54 |  |  |  | 1.COA 2.RAFC 3.CIAP | FEBRUARY 20, 2025 (10:00 AM) |  | MARCH 4, 2025 (10:00 AM) | 2025-03-11 | 2025-03-11
DA-RFO-1-2025-INFRA-023 | LOT 5: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF THREE (3) UNITS SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION IN BRGY. SAN GABRIEL, LA UNION; BRGY. STO. ROSARIO EAST, ARINGAY, LA UNION AND BRGY. GANA, CABA, LA UNION | HVCDP | No | Competitive Bidding | 2024-10-02 | February 12, 2025 to March 4, 2025 |  | FEBRUARY 20, 2025 (10:00 AM) |  | MARCH 4, 2025 (10:00 AM) |  | 2025-03-11 | 2025-03-11 | 2025-03-26 |  |  |  | 2025-03-26 | 2025-03-27 | 2025-03-27 |  |  | ONGOING INSTALLATION |  | Government of the Philippines (current year's budget) | 4454988.21 |  |  | 4227783.82 |  |  |  | 1.COA 2.RAFC 3.CIAP | FEBRUARY 20, 2025 (10:00 AM) |  | MARCH 4, 2025 (10:00 AM) | 2025-03-11 | 2025-03-11
DA-RFO 1-2025-INFRA-024 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF BOAR STUDIO AT DA-PREC, STA. BARBARA, PANGASINAN | Livestock | No | Competitive Bidding | 2024-11-13 | February 27, 2025 to March 19, 2025 |  | MARCH 6, 2025 (9:00 AM) |  | MARCH 19, 2025 (9:00 AM) |  | 2025-03-21 | 2025-03-26 | 2025-04-14 |  |  |  | 2025-04-21 | 2025-05-05 | 2025-05-05 |  |  | ONGOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 9899638.51 |  |  | 8690134.15 |  |  |  | 1.COA 2.RAFC 3.CIAP | MARCH 6, 2025 (9:00 AM) |  | MARCH 19, 2025 (9:00 AM) | 2025-03-21 | 2025-03-26
PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF GOAT BREEDER HOUSE
DA-RFO 1-2025-INFRA-025 | LOT 1: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF ONE (1) UNIT GOAT BREEDER HOUSE IN BRGY. BALITE, MALASIQUI, PANGASINAN | Livestock | No | Competitive Bidding | 2024-07-02 | February 27, 2025 to March 19, 2025 |  | MARCH 6, 2025 (10:00 AM) |  | MARCH 19, 2025 (10:00 AM) |  | 2025-03-21 | 2025-03-26 | 2025-04-11 |  |  |  | 2025-04-11 | 2025-04-24 | 2025-04-24 |  |  | ONGOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 1700000 |  |  | 1525777.54 |  |  |  | 1.COA 2.RAFC 3.CIAP | MARCH 6, 2025 (10:00 AM) |  | MARCH 19, 2025 (10:00 AM) | 2025-03-21 | 2025-03-26
DA-RFO 1-2025-INFRA-025 | LOT 2: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF ONE (1) UNIT GOAT BREEDER HOUSE IN BRGY. MAMELTAC, CITY OF SAN FERNANDO, LA UNION | Livestock | No | Competitive Bidding | 2024-07-02 | February 27, 2025 to March 19, 2025 |  | MARCH 6, 2025 (10:00 AM) |  | MARCH 19, 2025 (10:00 AM) |  | 2025-03-21 | 2025-03-31 | 2025-04-11 |  |  |  | 2025-04-11 | 2025-04-24 | 2025-04-24 |  |  | ONGOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 1700000 |  |  | 1423971.36 |  |  |  | 1.COA 2.RAFC 3.CIAP | MARCH 6, 2025 (10:00 AM) |  | MARCH 19, 2025 (10:00 AM) | 2025-03-21 | 2025-03-31
DA-RFO 1-2025-INFRA-026 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF CATTLE BREEDER HOUSE IN BRGY. BOGTONG SILAG, MANGATAREM, PANGASINAN | Livestock | No | Competitive Bidding | 2024-07-02 | February 27, 2025 to March 19, 2025 |  | MARCH 6, 2025 (11:00 AM) |  | MARCH 19, 2025 (11:00 AM) |  | 2025-03-21 | 2025-03-26 | 2025-04-14 |  |  |  | 2025-04-21 | 2025-04-30 | 2025-04-30 |  |  | ONGOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 1000000 |  |  | 869903.33 |  |  |  | 1.COA 2.RAFC 3.CIAP | MARCH 6, 2025 (11:00 AM) |  | MARCH 19, 2025 (11:00 AM) | 2025-03-21 | 2025-03-26
DA-RFO 1-2025-INFRA-027 | CONSTRUCTION OF SLOPE PROTECTION AT DA-ILIARC, SAPILANG, BACNOTAN, LA UNION | ILIARC | No | Competitive Bidding | 2025-01-13 | February 27, 2025 to March 19, 2025 |  | MARCH 6, 2025 (1:00 PM) |  | MARCH 19, 2025 (1:00 PM) |  | 2025-03-21 | 2025-03-26 | 2025-04-14 |  |  |  | 2025-04-21 | 2025-04-30 | 2025-04-30 |  |  | ONGOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 5940013.72 |  |  | 4272452.29 |  |  |  | 1.COA 2.RAFC 3.CIAP | MARCH 6, 2025 (1:00 PM) |  | MARCH 19, 2025 (1:00 PM) | 2025-03-21 | 2025-03-26
REBIDDING OF PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF NINE (9) UNITS SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION UNDER THE HIGH VALUE CROPS (HVC) BANNER PROGRAM IN REGION 1
DA-RFO-1-2025-INFRA-028-R | REBIDDING OF LOT 1: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF ONE (1) UNIT SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION IN BRGY. CABAYAOASAN, BUGALLON, PANGASINAN | HVCDP | No | Competitive Bidding | 2025-10-02 | April 30, 2025 to May 20, 2025 |  | MAY 7, 2025 (1:00 PM) |  | MAY 20, 2025 (1:00 PM) |  | 2025-05-26 | 2025-05-28 | 2025-06-20 |  |  |  | 2025-06-23 | 2025-06-30 | 2025-06-30 |  |  | ONGOING INSTALLATION |  | Government of the Philippines (current year's budget) | 1484996.07 |  |  | 1336298.99 |  |  |  | 1.COA 2.RAFC 3.CIAP | MAY 7, 2025 (1:00 PM) |  | MAY 20, 2025 (1:00 PM) | 2025-05-26 | 2025-05-28
DA-RFO-1-2025-INFRA-028-R | REBIDDING OF LOT 2: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF TWO (2) UNITS SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION IN BRGY. AN-ANNAM, BANTAY, ILOCOS SUR AND BRGY. PANTAY TAMURONG, CAOAYAN, ILOCOS SUR | HVCDP | No | Competitive Bidding | 2025-10-02 | April 30, 2025 to May 20, 2025 |  | MAY 7, 2025 (1:00 PM) |  | MAY 20, 2025 (1:00 PM) |  | 2025-05-26 | 2025-05-28 | 2025-06-20 |  |  |  | 2025-06-23 | 2025-06-30 | 2025-06-30 |  |  | ONGOING INSTALLATION |  | Government of the Philippines (current year's budget) | 2969992.14 |  |  | 2967994.4 |  |  |  | 1.COA 2.RAFC 3.CIAP | MAY 7, 2025 (1:00 PM) |  | MAY 20, 2025 (1:00 PM) | 2025-05-26 | 2025-05-28
DA-RFO-1-2025-INFRA-028-R | REBIDDING OF LOT 3: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF ONE (1) UNIT SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION IN BRGY. BUNGRO, CABUGAO, ILOCOS SUR | HVCDP | No | Competitive Bidding | 2025-10-02 | April 30, 2025 to May 20, 2025 |  | MAY 7, 2025 (1:00 PM) |  | MAY 20, 2025 (1:00 PM) |  | 2025-05-26 | 2025-05-28 | 2025-06-20 |  |  |  | 2025-06-23 | 2025-06-30 | 2025-06-30 |  |  | ONGOING INSTALLATION |  | Government of the Philippines (current year's budget) | 1484996.07 |  |  | 1484776.59 |  |  |  | 1.COA 2.RAFC 3.CIAP | MAY 7, 2025 (1:00 PM) |  | MAY 20, 2025 (1:00 PM) | 2025-05-26 | 2025-05-28
NEGOTIATED PROCUREMENT OF PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF NINE (9) UNITS SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION UNDER THE HIGH VALUE CROPS (HVC) BANNER PROGRAM IN REGION 1
DA-RFO 1-2025-INFRA-028-N | NEGOTIATED PROCUREMENT OF LOT 4: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF TWO (2) UNITS SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION IN BRGY. LANGLANGCA SEGUNDO, CANDON CITY, ILOCOS SUR AND BRGY. MABILBILA SUR, SANTA, ILOCOS SUR | HVCDP | No | Competitive Bidding | 2024-10-02 | June 3 to 18, 2025 |  | June 10, 2025 (1:00 P.M) |  | June 18, 2025 (9:00 A.M) |  | 2025-06-18 | 2025-06-24 | 2025-06-27 |  |  |  | 2025-06-27 | 2025-06-30 | 2025-06-30 |  |  | ONGOING INSTALLATION |  | Government of the Philippines (current year's budget) | 2969992.14 |  |  | 2524354.35 |  |  |  | 1.COA 2.RAFC 3.CIAP | June 10, 2025 (1:00 P.M) |  | June 18, 2025 (9:00 A.M) | 2025-06-18 | 2025-06-24
DA-RFO 1-2025-INFRA-028-N | NEGOTIATED PROCUREMENT OF LOT 5: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF ONE (1) UNIT SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION IN BRGY. BACSIL SOUTH, LAOAG CITY, ILOCOS NORTE | HVCDP | No | Competitive Bidding | 2024-10-02 | June 3 to 18, 2025 |  | June 10, 2025 (1:00 P.M) |  | June 18, 2025 (9:00 A.M) |  | 2025-06-18 | 2025-06-24 | 2025-06-27 |  |  |  | 2025-06-27 | 2025-06-30 | 2025-06-30 |  |  | ONGOING INSTALLATION |  | Government of the Philippines (current year's budget) | 1484996.07 |  |  | 1262177.18 |  |  |  | 1.COA 2.RAFC 3.CIAP | June 10, 2025 (1:00 P.M) |  | June 18, 2025 (9:00 A.M) | 2025-06-18 | 2025-06-24
DA-RFO 1-2025-INFRA-028-N | NEGOTIATED PROCUREMENT OF LOT 6: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF TWO (2) UNITS SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION IN BRGY. BALIGAT, BATAC CITY, ILOCOS NORTE AND BRGY. ESCODA, MARCOS, ILOCOS NORTE | HVCDP | No | Competitive Bidding | 2024-10-02 | June 3 to 18, 2025 |  | June 10, 2025 (1:00 P.M) |  | June 18, 2025 (9:00 A.M) |  | 2025-06-19 | 2025-06-24 | 2025-06-27 |  |  |  | 2025-06-27 | 2025-06-30 | 2025-06-30 |  |  | ONGOING INSTALLATION |  | Government of the Philippines (current year's budget) | 2969992.14 |  |  | 2524354.35 |  |  |  | 1.COA 2.RAFC 3.CIAP | June 10, 2025 (1:00 P.M) |  | June 18, 2025 (9:00 A.M) | 2025-06-19 | 2025-06-24
DA-RFO 1-2025-INFRA-030-R | REBIDDING OF PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF ILOCOS SUR RESEARCH CENTER MULTI-CROP WAREHOUSE CUM OFFICE | DA-ISRec | No | Competitive Bidding | 2024-12-09 | July 10-29, 2025 |  | JULY 17, 2025 (9:00 AM) |  | JULY 29, 2025 (9:00 AM) | [14 empty] | Government of the Philippines (current year's budget) | 40594084.62 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.CIAP | JULY 17, 2025 (9:00 AM) |  | JULY 29, 2025 (9:00 AM)
DA RFO-1-2025-INFRA-031-R | REBIDDING OF PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF SAN ANTONIO SOLAR-POWERED IRRIGATION SYSTEM (SPIS) IN BRGY. SAN ANTONIO, ARINGAY, LA UNION | RAED | No | Competitive Bidding | 2024-10-01 | May 26, 2025 to June 3, 2025 |  | JUNE 3, 2025 (2:00 PM) |  | JUNE 17, 2025 (2:00 PM) |  | 2025-06-19 | 2025-06-24 | 2025-06-26 |  |  |  | 2025-06-26 | [6 empty] | Government of the Philippines (current year's budget) | 6435081.48 |  |  | 6434771.98 |  |  |  | 1.COA 2.RAFC 3.CIAP | JUNE 3, 2025 (2:00 PM) |  | JUNE 17, 2025 (2:00 PM) | 2025-06-19 | 2025-06-24
DA-RFO 1-2025-INFRA-032 | ESTABLISHMENT OF MULTI-CROP SEED PROCESSING BUILDING AT INREC DINGRAS, ILOCOS NORTE (PHASE 1) | DA-INREC | No | Competitive Bidding | 2024-12-18 | April 30, 2024 to May 20, 2025 |  | MAY 7, 2025 (10:00 AM) |  | MAY 20, 2025 (10:00 AM) |  | 2025-05-26 | 2025-05-27 | 2025-06-17 |  |  |  | 2025-06-19 | [6 empty] | Government of the Philippines (current year's budget) | 4000000 |  |  | 3402903.96 |  |  |  | 1.COA 2.RAFC 3.CIAP | MAY 7, 2025 (10:00 AM) |  | MAY 20, 2025 (10:00 AM) | 2025-05-26 | 2025-05-27
DA RFO-1-2025-INFRA-033 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE UPGRADING OF BIOLOGICAL CONTROL AGENT (BCA) LABORATORY AT ILOCOS SUR RESEARCH CENTER (ISReC), SAN JUAN, ILOCOS SUR | DA-ISReC | No | Competitive Bidding | N/A | May 26, 2025 to June 3, 2025 |  | JUNE 3, 2025 (1:00 PM) |  | JUNE 17, 2025 (1:00 PM) |  | 2025-06-19 | 2025-06-26 | 2025-07-10 |  |  |  | 2025-07-10 | [6 empty] | Government of the Philippines (current year's budget) | 1000000 |  |  | 910831.7 |  |  |  | 1.COA 2.RAFC 3.CIAP | JUNE 3, 2025 (1:00 PM) |  | JUNE 17, 2025 (1:00 PM) | 2025-06-19 | 2025-06-26
DA-RFO 1-2025-INFRA-034 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF SOLAR-POWERED IRRIGATION SYSTEM (SPIS) WITH DRIP IRRIGATION UNDER HIGH VALUE CROPS (HVC) BANNER PROGRAM IN BRGY. SAGUIGUI, PAGUDPUD, ILOCOS NORTE | HVCDP | No | Competitive Bidding | N/A | May 28, 2025 to June 17, 2025 |  | JUNE 4, 2025 (9:00 PM) |  | JUNE 17, 2025 (3:00 PM) |  | 2025-06-19 | 2025-06-24 | 2025-06-27 |  |  |  | 2025-06-27 | 2025-06-30 | 2025-06-30 |  |  | FOR INSTALLATION |  | Government of the Philippines (current year's budget) | 1484996.07 | [6 empty] | 1.COA 2.RAFC 3.CIAP | JUNE 4, 2025 (9:00 PM) |  | JUNE 17, 2025 (3:00 PM) | 2025-06-19 | 2025-06-24
DA-RFO 1-2025-INFRA-035 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE ESTABLISHMENT OF NURSERY HOUSE FOR BAMBOO AND INSTALLATION OF PROJECT MARKER, SOLAR LIGHTS AND INSTALLATION OF MICRO SPRINKLER AND WATER SYSTEM AT BRGY. CAMANDINGAN, BATAC CITY, ILOCOS NORTE | HVCDP | No | Competitive Bidding | N/A | June 11, 2025 to July 1, 2025 |  | JUNE 19, 2025 (1:00 PM) |  | JULY 1, 2025 (1:00 PM) |  | 2025-07-02 | FOR POST-QUAL | [11 empty] | Government of the Philippines (current year's budget) | 1000000 | [6 empty] | 1.COA 2.RAFC 3.CIAP | JUNE 19, 2025 (1:00 PM) |  | JULY 1, 2025 (1:00 PM)
PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF GREENHOUSE WITH HYDROPONICS SYSTEM UNDER THE NATIONAL URBAN AND PERI URBAN AGRICULTURE PROGRAM (NUPAP) IN REGION I
DA-RFO 1-2025-INFRA-036 | LOT 1: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF ONE (1) UNIT GREENHOUSE WITH HYDROPONICS SYSTEM UNDER THE NATIONAL URBAN AND PERI URBAN AGRICULTURE PROGRAM (NUPAP) IN BRGY. CAMANGGAAN, LAOAG CITY, ILOCOS NORTE | NUPAP | No | Competitive Bidding | N/A | June 11, 2025 to July 1, 2025 |  | JUNE 19, 2025 (2:00 PM) |  | JULY 1, 2025 (2:00 PM) |  | 2025-07-02 | FOR POST-QUAL | [11 empty] | Government of the Philippines (current year's budget) | 996789.67 |  |  | 920000 |  |  |  | 1.COA 2.RAFC 3.CIAP | JUNE 19, 2025 (2:00 PM) |  | JULY 1, 2025 (2:00 PM) | 2025-07-02 | 2025-07-03
DA-RFO 1-2025-INFRA-036 | LOT 2: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE INSTALLATION OF ONE (1) UNIT GREENHOUSE WITH HYDROPONICS SYSTEM UNDER THE NATIONAL URBAN AND PERI URBAN AGRICULTURE PROGRAM (NUPAP) IN BRGY. SANTIAGO NORTE, CITY OF SAN FERNANDO, LA UNION | NUPAP | No | Competitive Bidding | N/A | June 11, 2025 to July 1, 2025 |  | JUNE 19, 2025 (2:00 PM) |  | JULY 1, 2025 (2:00 PM) |  | 2025-07-02 | FOR POST-QUAL | [11 empty] | Government of the Philippines (current year's budget) | 996789.67 |  |  | 830897.65 |  |  |  | 1.COA 2.RAFC 3.CIAP | JUNE 19, 2025 (2:00 PM) |  | JULY 1, 2025 (2:00 PM) | 2025-07-02 | 2025-07-03
DA-RFO 1-2025-INFRA-037 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE ESTABLISHMENT OF GREENHOUSE WITH HYDROPONICS AND SPRINKLER SYSTEM, UNDER NUPAP AT BRGY. CABAROAN DAYA, VIGAN CITY, ILOCOS SUR | NUPAP | No | Competitive Bidding | N/A | June 19, 2025 to July 8, 2025 |  | JUNE 26, 2025 (10:00 AM) |  | JULY 15, 2025 (2:00 PM | [14 empty] | Government of the Philippines (current year's budget) | 1000000 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.CIAP | JUNE 26, 2025 (10:00 AM) |  | JULY 8, 2025 (10:00 AM)
PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF COFFEE PRODUCTS PROCESSING FACILITY IN REGION I
DA-RFO 1-2025-INFRA-038 | LOT 1: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF COFFEE PRODUCTS PROCESSING FACILITY IN BRGY. SAN ELIAS, SIGAY, ILOCOS SUR | HVCDP | No | Competitive Bidding | 2025-05-27 | June 19, 2025 to July 8, 2025 |  | JUNE 26, 2025 (11:00 AM) |  | JULY 15, 2025 (3:00 PM | [14 empty] | Government of the Philippines (current year's budget) | 2969577.29 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.CIAP | JUNE 26, 2025 (11:00 AM) |  | JULY 8, 2025 (11:00 AM)
DA-RFO 1-2025-INFRA-038 | LOT 2: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF COFFEE PRODUCTS PROCESSING FACILITY IN PAGUDPUD, ILOCOS NORTE | HVCDP | No | Competitive Bidding | 2025-05-27 | June 19, 2025 to July 8, 2025 |  | JUNE 26, 2025 (11:00 AM) |  | JULY 15, 2025 (3:00 PM | [14 empty] | Government of the Philippines (current year's budget) | 2969577.29 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.CIAP | JUNE 26, 2025 (11:00 AM) |  | JULY 8, 2025 (11:00 AM)
DA-RFO 1-2025-INFRA-039 | NINE (9) UNITS COLD STORAGE EXPANSION PROJECT | RAED | No | Competitive Bidding | 2025-03-17 | July 11-30 2025 |  | JULY 18, 2025 (9:00 AM) |  | JULY 30, 2025 (9:00 AM) | [14 empty] | Government of the Philippines (current year's budget) | 115817056.47 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.CIAP | JULY 18, 2025 (9:00 AM) |  | JULY 30, 2025 (9:00 AM)
-
-
-
[7 empty] | #DIV/0! | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 1529401261.55 | 0 | 0 | 804805240.58 | 0 | 0 | 0%
|  | Prepared by: | [9 empty] | Recommended for Approval by: | [16 empty] | APPROVED:
|  | DORIS JOY C. GARCIA | [9 empty] | DENNIS I. TACTAC, ABE | [16 empty] | JOHN B. PASCUAL, DVM
|  | BAC Secretariat | [9 empty] | BAC Chairperson | [16 empty] | Head of the Procuring Entity
Note on N25: DECEMBER 17, 2024 LETTER OF EXTENSION UNTIL January 24, 2025
Note on AM25: DECEMBER 17, 2024 LETTER OF EXTENSION UNTIL January 24, 2025

## Tool 1-Processing (hidden)
Summary of Information for Processing of IRPP
Indicator 1: % of Processed Procurement Activities vs Planned in terms of amount |  | #REF!
Formula | Value | Remarks
Total Amount of APP as updated | #REF!
Divide by: Total Amount of ABC of procurement activities started | #REF! | ABC of awarded + ABC of on-going procurement projects (less ABC of Failure of Bids)
Indicator 2: Average % of Variance Between Contract Amount vs Approved Budget for the Contract |  | #REF!
Particular | Value | Remarks
Total Amount of ABC of procurement activities started | #REF!
Total Contact Cost | 2143829534.36
Total Variance for Each Awarded Procurement Project | #REF! | Column shall be hidden
Divide by Number of Awarded Procurement Projects | 160
Indicator 3. Timeliness on the Conduct of Procurement
|  | Indicator 3.1 Average No. of Days to commence procurement (Pre-Proc to Posting of IB) |  | Indicator 3.2: Average No. of Days to open bid proposals (Posting of IB/ to Opening of Bids) |  | Indicator 3.3: Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) |  | Indicator 3.4: Average Number of Days to Conclude Procurement (Posting of IB to Recommend Award) |  | Indicator 3.5: Average Number of Days to Issue Notice to Proceed (from Issuance of NOA to Issuance of NTP) |  | Indicator 3.6: Accumulated Number of Days for the Procurement Process (Posting of IB to NTP)
Mode of Procurement | Total No. of Activities under subject modality | Total No. of Days from PreProc to IB | Average Days from Pre-Proc to Posting of IB | Total No. of Days from IB to Opening | Average Days from Posting of IB to Opening of Bids | Total No. of Days Opening to Recommend Award) | Average Days from Opening of Bids to Recommend Award | Total No. of Days from Posting of IB to Recommend Award | Average Days from Posting of IB to Recommend Award | Total No. of Days from Issuance of NOA to Issue NTP | Average Days from NOA to NTP | Total No. of Days from Posting of IB to Issue NTP | Average Days from Posting of IB to NTP
Competitive Bidding | 193 | 0 | 0 | 0 | 0 | 33 | 0.17098 | 0 | 0 | 26 | 0.13472 | 0 | 0
Limited Source Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Direct Contracting | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Repeat Order | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.1 Two Failed Biddings | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.2 Emergency Cases | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.3 Take-Over of Contracts | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.5 Agency-to-Agency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.7 Highly Technical Consultants | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.9 - Small Value Procurement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.11 NGO Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.12 Community Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Emergency Procurement under Bayanihan Act | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Alternative Method | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 193 | 0 | 0 | 0 | 0 | 1.4348 | 0.17098 | 0 | 0 | 1.1304 | 0.13472 | 0 | 0
*formula for days interval for each procurement activity for each indicator are embedded in the PMR.
Indicator 4. Percentage of Amount and Volume by Tender and Award of Procurement Activities per Mode of Procurement
Mode of Procurement | Total No. of Activities | Total Number of Awarded | Total ABC | Total Contract Cost | %Vol of Awarded | %ABC of Awarded | Total Number of Failed | ABC of Failed
Competitive Bidding | 193 | 160 | 2219028777.18 | 2143829534.36 | 82.9% | 96.61% | 0 | 0
Limited Source Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Direct Contracting | 0 | 0 | 0 | 0 |  |  | 0 | 0
Repeat Order | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.2 Emergency Cases | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.3 Take-Over of Contracts | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.5 Agency-to-Agency | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.7 Highly Technical Consultants | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.9 - Small Value Procurement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.11 NGO Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.12 Community Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 | 0 | 0 |  |  | 0 | 0
Emergency Procurement under Bayanihan Act | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Alternative Method | 0 | 0 | 0 | 0 |  |  | 0 | 0
Total | 193 | 160 | 2219028777.18 | 2219028777.18 | 82.9% | 96.61% | 0 | 0
Total for Alternative Mode of Procurement | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
Indicator 5: Accumulated No. of Days for On-going Procurement Activities
Timeline | No. of Procurement Activities | %
Exceeds 180 days | 0 | 0%
Within 91 to 180 days | 0 | 0%
Within 45 to 90 days | 0 | 0%
Within 0 to 44 days | 0 | 0%
Total | 0 | 0%
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 6. Distribution of On-going, Awarded, and Failed procurement Activities
Status | No. of Procurement Activities | % by No. of Procurement of Activities | ABC Amount of Activities | % by ABC | Contract Cost | Contract/ABC | Variance
Awarded | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Completed | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Failed | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Ongoing | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Total | 0 | 0% | 0 | 0% | 0 | #DIV/0! | #DIV/0!
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 7a: % of Number of Procurement activities conducted under early procurement |  |  | 30.57%
Indicator 7b: % of ABC of Procurement activities conducted under early procurement |  |  | 12.73%
Particular | No. of Procurement Activities | ABC Amount of Activities
Under EPA | 59 | 418482072.21
Regular Procurement | 134 | 2869410479.98
Total | 193 | 3287892552.19
Indicator 8a: Percentage of Number of Awarded Contracts under EPA |  |  | 0%
Indicator 8b: Percentage of Contract Cost of EPA against the total ABC under EPA |  |  | 0%
Formula | No. of Procurement Activities | Amount of ABC Procurement Activities | Contract Cost of Procurement Activities | Percentage Variance
Total Contracts Awarded under EPA* | 0 | 0 | 0 | 0%
Total Contracts Completed under EPA* | 0 | 0 | 0 | 0%
Total Failed Bid under EPA* | 0 | 0 | 0 | 0%
Total Ongoing Activities under EPA* | 0 | 0 | #VALUE! | #VALUE!
Total Procurement Activities under EPA | 59 | 0 | #VALUE!
To compute for the total, a separate sheet may be created of the PMO may simply filter the cells to capture the total number.
Indicator 9: Stages where failure of bidding are encountered
Particular | No. of Procurement Activities | Amount of ABC | Vol. % | Amount %
Invitation To Bid | 0 | 0 | 0% | 0%
Pre-bidding Conference | 0 | 0 | 0% | 0%
Opening of Bids | 0 | 0 | 0% | 0%
Bid Evaluation | 0 | 0 | 0% | 0%
Post-Qualification | 0 | 0 | 0% | 0%
BAC Resolution | 0 | 0 | 0% | 0%
Award | 0 | 0 | 0% | 0%
Cancelled | 0 | 0 | 0% | 0%
TOTAL | 0 | 0

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget)
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget)
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget)
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution
Failed under Section 35.1 (b) |  | BAC Resolution
Failed under Section 35.1 (c) |  | Award
Failed under Section 41 (b) |  | Cancelled
Failed under Section 41 (c)
Contract was extended
Contract was renewed
Cancelled
Others, please encode directly on the cell