## 200M-OMPONG-SARO-E-20-0000156
Department of Agriculture
Ilocos Region
200M Typhoon Ompong Rehabilitation and Recovery Program
SARO-E-20-0000156
As of August 02, 2021
MFO Programs/Projects/Activity | Unit of Measure | Physical |  |  |  |  | FINANCIAL ('000) | [5 empty] | REMARKS
|  | Target No. | Accomplished |  |  |  | ALLOCATION | OBLIGATION |  |  | DISBURSEMENT
|  |  | NO. | % | MOOE | CO |  | Obligated ('000) | Unobligated ('000) | % | Disbursed | %
GENERAL ADMINISTRATIVE SERVICES (GASS) |  | 9 | 2 | 22.2222 | 0 | 79999.99 | 80000 | 17697.065 | 62524.192 | 22.1213 | 6455.03 | 36.4751
Rehabilitation/Enhancement of DA offices and buildings |  | 9 | 2 | 22.2222 |  | 79999.99 | 80000 | 17697.065 | 62524.192 | 22.1213 | 6455.03 | 36.4751
Rehabilitation and Enhancement of Administrative Building |  | 1 |  |  |  | 4863 | 4863 | 4210.705 | 652.295 | 86.5866 | 1760.6 | 41.8125 | On-going wall plastering and riprap with 50.00% physical accomplishment
Rehabilitation and Enhancement of Dormitory Building (PREC Station-additional fund) | [12 empty] | Obligated
Rehabilitation and Enhancement of Multi-purpose building --(Reconstruction of Guests’ House and Operations Building) |  | 1 |  |  |  | 6340.84 | 6340.84 | 3855.713 | 2485.127 | 60.8076 | 1446.47 | 37.515 | On-going wall plastering with 45.59% physical accomplishment
Rehabilitation and Enhancement of Dormitory Building (Laborers’ Quarter) |  | 1 | 1 | 100 |  | 3757.15 | 3757.16 | 3114.424 | 642.736 | 82.893 | 1852.9 | 59.4941 | Waiting for submission of as-built drawings as attachment for final billing with 100.00% physical accomplishment
Rehabilitation and Enhancement of Dormitory Building (PREC Station-additional fund) |  | 1 | [5 empty] | 221.257 |  | 100 |  |  | Obligated
Rehabilitation and Enhancement of Employee’s Quarter |  | 1 | 1 | 100 |  | 724 | 724 | 197.358 | 526.642 | 27.2594 | 197.36 | 100.001 | Completed
Rehabilitation and Enhancement of Duplex Roofing |  | 1 |  |  |  | 1466 | 1466 | 1283.683 | 182.317 | 87.5636 |  |  | 21.02% physical accomplishment but no on-going construction activity;Issued order of termination due to incurred of more than 15% slippage on the contract
Rehabilitation and Enhancement of Veterinary Laboratory |  | 1 |  |  |  | 1229 | 1229 | 606.605 | 622.395 | 49.3576 |  |  | For signature of contract agreement
Rehabilitation and Enhancement of Field Operations Unit Building |  | 1 |  |  |  | 4620 | 4620 | 4207.32 | 412.68 | 91.0675 | 1197.7 | 28.4671 | 71.92% physical accomplishment but no on-going construction activity due to unworkable site brought by rainfall
Reconstruction of Soils and Feeds Laboratory cum Region 1 Disaster Risk Reduction and Management Operations Center |  | 1 |  |  |  | 57000 | 57000 |  | 57000 | 0 |  |  | Project cancelled
OPERATIONS |  | 58 | 38 | 65.5172 | #REF! | #REF! | 120000 | 119297.281 | 702.719 | 99.4144 | 70888.21 | 59.4215
MFO 2.1. PRODUCTION SUPPORT SERVICES (PSS) |  |  |  |  | 0 | 0 | 0
RICE PROGRAM |  |  |  |  | 0 | 0 | 0
Provision of Seeds |  | 0 |  |  | 0 | 0 | 0
Foundation Seeds | bag
Hybrid Seeds | kilogram | [5 empty] | 0
Certified Seeds | 40 kgs./bag
Provision of Fertilizer |  |  |  |  | 0 | 0 | 0
Urea | 50kg/bag
Complete | 50kg/bag
Organic | 50kg/bag
Others | bags
Provision of Soil Ameliorants | packs
CORN/ CASSAVA PROGRAM |  |  |  |  | 0 | 0 | 0
Provision of Seeds | kilogram
Yellow corn (Sweet Corn) | bags
Hybrid | kilogram
OPV White Corn | bags
Provision of Fertilizer |  |  |  |  | 0 | 0 | 0
Urea | 50kg/bag
Complete | 50kg/bag
Organic | 50kg/bag
Others | bags
Provision of Soil Ameliorants | pieces
Laminated Sacks | pieces
HIGH VALUE CROPS |  |  |  |  | 0 | 0 | 0
Provision of Seeds | kilogram |  |  |  | 0 | 0 | 0
Vegetable Seeds |  |  |  |  | 0 | 0 | 0
Lowland
Sweet Pepper | kilogram
Ampalaya | kilogram
Squash | kilogram
Tomato | kilogram
Eggplant | kilogram
Upland
Hybrid | kilogram
OPV | kilogram
Assorted Vegetables | kilogram
Papaya | packets
Spices
Watermelon | kilogram
Others | kilogram
Provision of Planting Materials |  | 0 |  |  | 0 | 0 | 0
Mango | piece
Rambutan | piece
Cacao | piece
Calamansi/Citrus | piece
Coffee | piece
Lanzones | piece
Rootcrops |  | 0 |  |  | 0 | 0 | 0
Sweet Potato | cuttings
PE Plastic Sheet | roll
Provision of Fertilizer |  | 0 |  |  | 0 | 0 | 0
Fertilizer | 50kg/bag
Complete | 50kg/bag
Organic | 50kg/bag
Foliar Spray | liter
Others | bags | [5 empty] | 0
Provision of Soil Ameliorants | pack | [5 empty] | 0
LIVESTOCK |  |  |  |  | 0 | 0 | 0
Re-Stocking of Animals |  |  |  |  | 0 | 0 | 0
Large Ruminants | head
Cattle | head
Carabao | head
Horse | head
Small Ruminants | head | 0 |  |  | 0 | 0 | 0
Goat | head |  |  |  |  | 0 | 0
Doe | head
Buck | head
Male/Female | head | [5 empty] | 0
Sheep
Ewe | head
Ram | head
Male/Female | head
Swine/Native Swine | head | [5 empty] | 0
Poultry | head | 0 |  |  | 0 |  | 0
Ducks | head | [5 empty] | 0
Chicken | head
Chicken | head
Native | head
Free-Ranged Chicken | head | [5 empty] | 0
Turkey | head
Others
Provision of Animal Feeds and supplements/drugs and biologics | bottle
Feeds | bags
Multi-Vitamins | doses
Antibiotic | doses
Vaccine | doses
Dewormer | doses
MFO 2.4. RESEARCH AND DEVELOPMENT
Rehabilitation of Central Luzon Integrated Agricultural Research Center for Hillyland Development (CLIARC-UD) | unit
MFO 3: IRRIGATION NETWORK SERVICES (INS) |  | 38 | 30 | 78.9474 | 100000 | 0 | 100000 | 99999.994 | 0.006 | 100 | 70888.21 | 70.8882
Rehabilitation of Irrigation Dams/Systems |  | 0 |  |  | 100000 | 0 | 100000 |  | 100000
RICE PROGRAM |  | 38 | 30 |  | 100000 | 0 | 100000 | 99999.994 | 0.006 | 100 | 70888.21 | 70.8882
Communal Irrigation System (CIS) | unit | [5 empty] | 0
Diversion Dam (DD) | unit | 25 | 19 | 76 | 61750 |  | 61750 | 64306.781 | -2556.781 | 104.1405 | 44923.511 | 69.8581
Pangasinan |  | 3 | 3 | 100 | 7000 |  | 7000 | 8606.868 | -1606.868 | 122.9553 | 6309.488 | 73.3076
Natividad
Improvement of Bantay Tanggal DD | unit | 1 | 1 | 100 | 1000 |  | 1000 | 967.098 | 32.902 | 96.7098 | 967.098 | 100 | Completed
Mapandan
Construction of additional canal lining | unit | 1 | 1 | 100 |  |  |  | 2297.38 | 0 | 0 | 2297.38 | 100 | Savings; Fund Transferred to LGU- Mapandan
Sual(PREC)
PREC-Sual canal lining | unit | 1 | 1 | 100 | 6000 |  | 6000 | 5342.39 | 657.61 | 89.0398 | 5342.39 | 100 | Completed
La Union |  | 2 | 2 | 100 | 3800 |  | 3800 | 3686.48 | 113.52 | 97.0126 | 3492.88 | 94.7484
San Juan
Dasay DD | unit | 1 | 1 | 100 | 1800 |  | 1800 | 1750.46 | 49.54 | 97.2478 | 1750.46 | 100 | Completed
Rosario
Carunuan West DD | unit | 1 | 1 | 100 | 2000 |  | 2000 | 1936.02 | 63.98 | 96.801 | 1742.42 | 90.0001 | Completed
Ilocos Sur |  | 3 | 3 | 100 | 8400 |  | 8400 | 8272.473 | 127.527 | 98.4818 | 7445.22 | 89.9999
Quirino
Manugos DD | unit | 1 | 1 | 100 | 2500 |  | 2500 | 2486.913 | 13.087 | 99.4765 | 2238.22 | 89.9999 | Completed
Sinait
Ubbog DD | unit | 1 | 1 | 100 | 2800 |  | 2800 | 2700 | 100 | 96.4286 | 2430 | 90 | Completed
Nagcullooban DD | unit | 1 | 1 | 100 | 3100 |  | 3100 | 3085.56 | 14.44 | 99.5342 | 2777 | 89.9999 | Completed
Ilocos Norte |  | 17 | 11 | 64.7059 | 42550 |  | 42550 | 43740.96 | -1190.96 | 102.799 | 27675.923 | 63.2723
Carasi
Bungad DD | unit | 1 |  |  | 5150 |  | 5150 | 4985.066 | 164.934 | 96.7974 | 3767.21 | 75.5699 | Reported completed by the contractor and for verification of the RIC with 92.66% physical accomplishment
Bimoyayong DD | unit | 1 | 1 | 100 | 1200 |  | 1200 | 1135.992 | 64.008 | 94.666 | 1022.39 | 89.9998 | Completed
Bangui
Taguiporo Grande DD | unit | 1 | 1 | 100 | 3000 |  | 3000 | 2849.972 | 150.028 | 94.9991 | 2004.39 | 70.3302 | Completed; On-going process of final billing
Burgos
Ablan DD | unit | 1 | 1 | 100 | 3000 |  | 3000 | 2781.73 | 218.27 | 92.7243 | 2781.73 | 100 | Completed
Vintar
Cabisuculan DD | unit | 1 | 1 | 100 | 1000 |  | 1000 | 989.86 | 10.14 | 98.986 | 890.88 | 90.0006 | Completed
Dipilat Canal Lining | unit | 1 | 1 | 100 | 200 |  | 200 | 190.13 | 9.87 | 95.065 | 171.11 | 89.9963 | Completed
Zanjera Camaquin DD | unit | 1 | 1 | 100 | 500 |  | 500 | 460.622 | 39.378 | 92.1244 | 414.5 | 89.987 | Completed
Piddig
Abucay Canal Lining | unit | 1 | 1 | 100 | 2000 |  | 2000 | 1931.698 | 68.302 | 96.5849 | 1931.7 | 100.0001 | Completed
Batac
Improvement of Irrigation Canal | unit | 1 | [5 empty] | 3759.62 | 0 | 0 |  |  | 96.29 % physical accomplishment with no on-going construction activity due to unworkable site brought by rainfall; Savings (Under Irrigation Network Services on National Rice Program)
Pagudpud
Rincon DD | unit | 1 |  |  | 3000 |  | 3000 | 2896.052 | 103.948 | 96.5351 | 900.45 | 31.0923 | For resumption of work with 34.55% physical accomplishment
Tabbog DD | unit | 1 |  |  | 4000 |  | 4000 | 4027.807 | -27.807 | 100.6952 | 2870.17 | 71.2589 | Reported completed by the contractor for re-inspection of RIC with 93.93% physical accomplishment
Pinili
Bungro DD | unit | 1 | 1 | 100 | 3000 |  | 3000 | 2708.485 | 291.515 | 90.2828 | 2708.49 | 100.0002 | Completed
Paoay
San Agustin DD | unit | 1 | 1 | 100 | 3000 |  | 3000 | 2800.721 | 199.279 | 93.3574 |  |  | Recommended for final inspection with 100.00% physical accomplishment
Salbang DD | unit | 1 |  |  | 4000 |  | 4000 | 3556.84 | 443.16 | 88.921 | 2264.233 | 63.6586 | On-going concrete pouring and installation of reinforced concrete pipe with 89.10% physical accomplishment
Solsona
Barcelona DD | unit | 1 |  |  | 2500 |  | 2500 | 2422.27 | 77.73 | 96.8908 |  |  | 62.87% physical accomplishment but no on-going construction activity
Bubuos Capurictan DD | unit | 1 | 1 | 100 | 4000 |  | 4000 | 3502.431 | 497.569 | 87.5608 | 3207.01 | 91.5653 | Completed
Nagpatpatan Canal Lining | unit | 1 | 1 | 100 | 3000 |  | 3000 | 2741.664 | 258.336 | 91.3888 | 2741.66 | 99.9999 | Completed
Small Water Impounding Projects (SWIP) | unit | 13 | 11 | 84.6154 | 38250 | 0 | 38250 | 35693.213 | 2556.787 | 93.3156 | 25964.699 | 72.7441
Pangasinan |  | 5 | 5 | 100 | 13000 | 0 | 13000 | 12684.308 | 315.692 | 97.5716 | 12684.309 | 100
Umingan
Casilan SWIP | unit | 1 | 1 | 100 | 2000 |  | 2000 | 1996.4 | 3.6 | 99.82 | 1996.4 | 100 | Completed
Digap SWIP | unit | 1 | 1 | 100 | 1500 |  | 1500 | 1495.897 | 4.103 | 99.7265 | 1495.9 | 100.0002 | Completed
Balungao
San Aurelio SWIP | unit | 1 | 1 | 100 | 2500 |  | 2500 | 2420.547 | 79.453 | 96.8219 | 2420.547 | 100 | Completed
Angayan Sur SWIP | unit | 1 | 1 | 100 | 2000 |  | 2000 | 1936.422 | 63.578 | 96.8211 | 1936.42 | 99.9999 | Completed
Centro SWIP | unit | 1 | 1 | 100 | 5000 |  | 5000 | 4835.042 | 164.958 | 96.7008 | 4835.042 | 100 | Completed
Ilocos Sur |  | 1 | 1 | 100 | 3000 | 0 | 3000 | 2766.512 | 233.488 | 92.2171 | 2766.51
Sta.Maria
Pinsal SWIP | unit | 1 | 1 | 100 | 3000 |  | 3000 | 2766.512 | 233.488 | 92.2171 | 2766.51 |  | Completed
Ilocos Norte |  | 7 | 5 | 71.4286 | 22250 | 0 | 22250 | 20242.393 | 2007.607 | 90.977 | 10513.88
Burgos
Nagsurot SWIP | unit | 1 | 1 | 100 | 3000 |  | 3000 | 2857.839 | 142.161 | 95.2613 | 2857.84 | 100 | Completed
Vintar
Saricao SWIP | unit | 1 | 1 | 100 | 3000 |  | 3000 | 2954.265 | 45.735 | 98.4755 | 2658.84 | 90.0001 | Completed
Sarrat
San Cristobal SWIP | unit | 1 | 1 | 100 | 4000 |  | 4000 | 3693.273 | 306.727 | 92.3318 | 2108.18 | 57.0816 | Completed; On-going of final billing
Piddig
Tangaoan SWIP | unit | 1 |  |  | 4250 |  | 4250 | 3743.846 | 506.154 | 88.0905 |  |  | On-going construction of canal with 57.40% physical accomplishment
Batac
Pimentel SWIP | unit | 1 |  |  | 3000 |  | 3000 | 2907.958 | 92.042 | 96.9319 |  |  | On-going laying of boulders (stone masonry) with 58.47% physical accomplishment
Pinili
Nagtrigoan SWIP | unit | 1 | 1 | 100 | 2000 |  | 2000 | 1641.521 | 358.479 | 82.076 | 1477.37 | 90.0001 | Completed
San Nicolas
Samac SWIP | unit | 1 | 1 | 100 | 3000 |  | 3000 | 2443.691 | 556.309 | 81.4564 | 1411.65 | 57.7671 | For preparation of billing documents with 100.00% physical accomplishment
MFO 5: AGRICULTURAL FARM MACHINERIES, EQUIPMENT AND FACILITIES |  | 20 | 8 | 40 | #REF! | #REF! | 20000 | 19297.287 | 702.713 | 96.4864
Rehabilitation of Production and Post-Harvest Facilities |  | 20 | 8 | 40 | #REF! | #REF! | 20000 | 19297.287 | 702.713
RICE PROGRAM |  | 2 | 0 | 0 | 0 | 3136 | 3136 | 3136 | 0 | 100
Mushroom Growing facility | unit | 1 |  |  |  | 990 | 990 | 334.206 | 655.794 | 33.7582 |  |  | For commencement of work
Buffer seed bodega | unit | 1 |  |  |  | 2146 | 2146 | 2801.794 | -655.794 | 130.5589 |  |  | 60.00 % physical accomplishment but no on-going construction activity due to unworkable site brought by rainfall
HIGH VALUE CROPS |  | 10 | 3 | 30 | 0 | 11417.69 | 11417.68 | 10766.387 | 651.293 | 94.2958
Mango seedling nursery | unit | 1 |  |  |  | 675 | 675 | 477.284 | 197.716 |  |  |  | 58.38% physical accomplishment but no on-going construction activity
Screenhouses | unit |  |  |  |  | 2150
a.) Dingras, Ilocos Norte | unit | 1 |  |  |  |  | 750 | 731.693 | 18.307 | 97.5591 |  |  | 36.44% physical accomplishment but no on-going construction activity
b.) Batac City, Ilocos Norte | unit | 1 | 1 | 100 |  |  | 750 | 743.914 | 6.086 | 99.1885 |  |  | Completed; On-going process of final billing
c.) Sual, Pangasinan | unit | 1 | 1 | 100 |  |  | 650 | 638 | 12 | 98.1538 |  |  | On- going process of final billing with 100.00% physical accomplishment
Perimeter Fence
a.) INREC Station | site | 1 | 1 | 100 |  | 6263.59 | 6263.58 | 2164.286 | 918.143 | 85.3416 |  |  | Completed
b.) PREC Station | site | 1 | [5 empty] | 3181.151 |  |  |  |  | Temporary suspended
Greenhouse | unit | 1 |  |  |  | 650 | 650 | 585.625 | 64.375 | 90.0962 |  |  | 5.00% physical accomplishment but no on-going construction activity
Garlic Storage Facility | unit | 1 |  |  |  | 758 | 758 | 1274.151 | -516.151 | 168.0938 |  |  | On-going excavation for concrete footing with 23.94% physical accomplishment
Nursery (2) | units | 2 |  |  |  | 921.1 | 921.1 | 770.283 | -49.2 | 105.34 |  |  | Temporary suspended
Nursery and Warehouse/Seed Storage (PREC Station) | unit | 1 | [5 empty] | 200 |  |  |  |  | Obligated
LIVESTOCK |  | 8 | 5 | 62.5 | 0 | 5446.32 | 5446.32 | 5394.9 | 337.626 | 99.0559 | 2480.408 | 45.9769
Honey bee cages roofing | unit | 1 |  |  |  | 95 | 95 |  | 95 | 0 |  |  | Project Cancelled; Allocated fund will be utilized for other infrastructure projects with adjusted project cost.
Organic goat house | unit | 1 |  |  |  | 800 | 800 | 779.949 | 20.051 | 97.4936 |  |  | For signature of contract agreement
Goat House | unit | 2 | 1 | 100 |  | 1580 | 1580 | 1621 | -41 | 102.5949 | 942.02 | 58.1135 | For signature of SWA and as-built drawings with 100.00% physical accomplishment
Livestock Section pump house | unit | 1 | 1 | 100 |  | 290 | 290 | 215.134 | 74.866 | 74.1841 | 197.29 | 91.7056 | Completed
Chicken house with fence | unit | 1 | 1 | 100 |  | 620 | 620 | 607.5 | 12.5 | 97.9839 | 607.498 | 99.9997 | Completed
Duck house | unit | 1 | 1 | 100 |  | 793.52 | 793.52 | 733.598 | 59.922 | 92.4486 | 733.6 | 100.0003 | Completed
Piggery house with fence | unit | 1 | 1 | 100 |  | 1267.8 | 1267.8 | 1151.513 | 116.287 | 90.8277 |  |  | Completed; On-going preparation of billing documents
Buffer seed bodega (support fund) | unit | [6 empty] | 286.206 |  | 100 |  |  | Allocated fund will be used in the construction of buffer seed bodega under Rice Program.
GRAND TOTAL |  |  |  |  | #REF! | #REF! | 200000 | 136994.346 | 63005.654 | 68.4972 | 77343.24 | 56.4572
Prepared by: | Reviewed by : |  |  | Certified correct: | [7 empty] | Noted by:
MARICHU C. VILLEGAS | IRENE P. TACTAC |  |  | DOMINADOR R. LIM, JR. |  |  |  |  | ARNOLD T. EBREO |  |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  |  |  |  | Chief, Accounting Section |  |  | OIC-Regional Executive Director

## ompong-SARO-BMB-E-19-0012554
DEPARTMENT OF AGRICULTURE
REGIONAL FIELD OFFFICE 1
TYPHOON OMPONG REHABILITATION FUND
SARO-E-19-0012554
As of august 02, 2021
Program/ Sub-program/ Indicators | Indicator | PHYSICAL |  |  | FINANCIAL | [5 empty] | REMARKS
|  | TARGET (No.) | ACCOMPLISHED |  | ALLOCATION (PhP) | OBLIGATION |  |  | DISBURSEMENT
|  |  | NO. | % |  | OBLIGATED (PhP) | UNOBLIGATED (PhP) | % | Disbursed | %
RICE BANNER PROGRAM |  |  |  | 0 | 192655000 | 192655000 | 0 | 100 | 190957000 | 99.1186
Production Support Services Sub-Program |  | 0 |  |  | 77955000 | 77955000 | 0 | 100 | 76338000 | 97.9257
> Hybrid seeds (@15/bag for 1 ha) |  |  |  |  | 77955000 | 77955000 | 0 | 0 | 76338000 | 97.9257 | Total procured seeds is good for 17,434 ha. Which is more than the target, this is due to efficient bidding process; Complete distribution to farmer beneficiaries
Procured/Distributed | Area served | 15591 | 17434 | 111.8209 | 77955000 | 77955000 |  | 0 | 76338000 | 97.9257
Agri-Fishery Machineries, Equipment and Facilities Services |  | 0 |  |  | 114700000 | 114700000 | 0 | 100 | 114619000 | 99.9294
Post Harvest Equipment and Machineries |  |  |  |  | 114700000 | 114700000 | 0 | 100 | 114619000 | 99.9294
> Combined harvester | [10 empty] | Completed
Procured/Distributed | unit | 20 | 13 | 65 | 75700000 | 75700000 | 0 | 100 | 75685000 | 99.9802
> Tractor | [10 empty] | Completed
Procured/Distributed | unit | 26 | 23 | 88.4615 | 39000000 | 39000000 | 0 | 100 | 38934000 | 99.8308
HVCDP |  | 0 |  |  | 10230000 | 10230000 | 0 | 100 | 10230000 | 100
Fertilizer & Other Soil Ameliorants
Soil Ameliorant |  |  |  |  | 10230000 | 10230000 | 0 | 100 | 10230000 | 100 | Completed.
Procured/Distributed | kilogram | 55297 | 55297 | 100 | 10230000 | 10230000 | 0 | 100 | 10230000 | 100
LIVESTOCK BANNER PROGRAM |  |  |  |  | 77520000 | 77520000 | 0 | 100 | 70065000 | 90.3831 | 0
Provision of Livestock Livelihood Projects |  |  |  |  | 77520000 | 77520000 | 0 | 100 | 70065000 | 90.3831
>Goat
Procured/Distributed | heads | 6300 | 6300 | 100 | 40500000 | 40500000 |  | 100 | 40473000 | 99.9333 | Completed
>Sheep
Procured/Distributed | heads | 4200 | 4200 | 100 | 25200000 | 25200000 |  | 100 | 25182000 | 99.9286 | Completed
>Improved chicken
Procured/Distributed | heads | 18250 | 16336 | 89.5123 | 7300000 | 7300000 |  | 100 | 0 | 0 | Completed; Unmet physical target is due to higher unit cost of the improved chicken.
>Ducks
Procured/Distributed | heads | 11000 | 11000 | 100 | 4400000 | 4400000 |  | 100 | 4290000 | 97.5 | Completed
Veterinary Drugs
Procured/Distributed | doses | 3000 | 3000 | 100 | 120000 | 120000 |  | 100 | 120000 | 100 | Completed
Grand Total |  |  |  |  | 280405000 | 280405000 | 0 | 100 | 271252000 | 96.7358
Prepared by: | Reviewed by : |  |  | Certified correct: | [5 empty] | Noted by:
MARICHU C. VILLEGAS | IRENE P. TACTAC |  |  | DOMINADOR R. LIM, JR. |  |  | ARNOLD T. EBREO |  |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  |  | Chief, Accounting Section |  |  | OIC-Regional Executive Director

## ASF-SARO BMB-E-19-0012266
DEPARTMENT OF AGRICULTURE
REHABILITATION/RECOVERY ACCOMPLISHMENT REPORT
For African Swine Fever Affected Areas
ASA No. 2019-000166
As of July 01, 2021
INTERVENTION | UNIT OF MEASURE | PHYSICAL |  |  | FINANCIAL | [5 empty] | REMARKS
|  | TARGET (No.) | ACCOMPLISHED |  | ALLOCATION (PhP) | OBLIGATION |  |  | DISBURSEMENT
|  |  | NO. | % |  | OBLIGATED (PhP) | UNOBLIGATED (PhP) | % | Disbursed | %
Support to Operations
LIVESTOCK |  |  |  |  | 30916160 | 30762389 | 153771 |  | 30762389
Livestock and Poultry Dispersal | [10 empty] | Completed/Distributed; Mortality -1 yearling (emergency slaughter)
Large Ruminants | heads | 762 |  |  | 25910000 | 25823575 | 86425 | 99.6664 | 25823575 | 100
a. Cattle | heads | 762 | 765
Upgraded Yearling | heads | 470 | 471 |  |  | 14118225 |  |  | 14118225
Upgraded Heifer | heads | 280 | 282 |  |  | 11225950 |  |  | 11225950
Upgraded Junior Bull | heads | 12 | 12 |  |  | 479400 |  |  | 479400
Poultry | heads | 3352 |  |  | 1832000 | 1764900 | 67100 | 96.3373 | 1764900 | 100 | Completed/ Distributed
a. Chicken | heads | 3352 | 639
Free Range Chicken (Pullet) | heads | 2880 | 580
Free Range Chicken (Rooster) | heads | 472 | 59
Agricultural Expenses |  |  |  |  | 3174160 | 3173914 | 246 | 99.9922 | 3173914 | 100
Drugs and Biologics | doses | 738 | [8 empty] | Realignment of projects.
Feed Supplements | bags | 2784
Liquid Disinfectant | gals | 100 | 100 |  |  | 245000 |  |  | 245000 | 100 | Payment completed last February 2020/ Used in disease monitoring and surveillance
Hydrated lime | bags | 50 | 50 |  |  | 50000 |  |  | 50000 | 100
ASF Test Kits | sets | 30 | 30 |  |  | 600000 |  |  | 600000 | 100 | Completed/ Distributed
Positive Control | sets | 10 | 10 |  |  | 57400 |  |  | 57400 | 100
Liquid Disinfectants | gals | 100 | 100 |  |  | 245000 |  |  | 245000 | 100
Animal Feeds | bags | 300 | 300 |  |  | 437850 |  |  | 437850 | 100
Veterinary Drugs/Supplements | bots | 2068 | 2068 |  |  | 1538664 |  |  | 1538664 | 100
Prepared by: |  | Reviewed by : |  |  | Certified correct: |  |  |  |  | Noted by:
MARICHU C. VILLEGAS |  | IRENE P. TACTAC |  |  | DOMINADOR R. LIM, JR. |  | ARNOLD T. EBREO |  |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen |  | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  | Chief, Accounting Section |  |  | OIC-Regional Executive Director

## SARO# BMB-E-16-0019036Lando (hidden)
DEPARTMENT OF AGRICULTURE
Regional Field Office
San Fernando City, La Union
STATUS OF CALAMITY FUND FOR TYPHOON LANDO
SARO #BMB-E-16-0019036
as of November 30, 2018
PROGRAM/PROJECTS/ ACTIVITIES | INDICATOR | PHYSICAL STATUS |  |  | FINANCIAL STATUS |  |  |  | DISBURSEMENT |  | STATUS/ REMARKS
|  | TARGET (No.) | ACCOMPLISHMENT |  | ALLOC. | OBLIG. | % | BALANCE | DISBURSED | %
|  |  | No. | %
GRAND TOTAL |  |  |  |  | 151238620.21 | 144600969.21 | 95.6111 | 6637651 | 25404114.15 | 17.5684
MFO 2. TECHNICAL SUPPORT SERVICES |  |  |  |  | 28218620 | 28081869 | 99.5154 | 136751 | 16385500.8 | 58.349
MFO 2.1 PRODUCTION SUPPORT SERVICES |  |  |  |  | 17668620 | 17668620 | 100 | 0 | 16385500.8 | 92.7379 |  | 15
Palay Certified Seeds (40kg/bag) | no. of bags distributed | 8577 | 8577 | 100 | 11664720 | 11664720 | 100 | 0 | 10381600.8 | 89 | Distribution completed
Soil Ameliorant (packs of 2 kg) | no. of packs distributed | 17154 | 8716 | 50.8103 | 6003900 | 6003900 | 100 | 0 | 6003900 | 100 | On-going distribution
MFO 2.3 RESEARCH & DEVELOPMENT SERVICES |  | 5 |  |  | 10550000 | 10413249 | 98.7038 | 136751 | 0
A. Rehab/repair of Da-Research & Experimentation Center | no. rehabilitated/repaired | 5 | 0 | 0 | 10550000 | 10413249 | 98.7038 | 136751 | 0
Rehabilitation of fertilizer bodega, PREC, Sta. Barabara, Pang. | no. rehabilitated/repaired | 1 | 0 | 0 | 1000000 | 994072 | 99.4072 | 5928 | 0 |  | 65 % accomplishment
Rehabilitation of Motor pool garage, Sual & PREC, Sta. Barabara, Pang. | no. rehabilitated/repaired | 1 | 0 | 0 | 3450000 | 3335334 | 96.6763 | 114666 | 0 |  | Motorpool garage, Sual : On-going construction while the Motorpool Garage, Sta. Barbara : NTP to be issued/to be signed
Rehabilitation of guest house 2, PREC, Sta. Barbara, Pangasinan | no. rehabilitated/repaired | 1 | 0 | 0 | 2300000 | 2300000 | 100 | 0 | 0 |  | For schedule of bidding; On going revision due to change of site
Rehabilitation of duck house, Sual, Pangasinan | no. rehabilitated/repaired | 1 | 0 | 0 | 2900000 | 2900000 | 100 | 0 | 0 |  | For approval of PR, POW and revised plans. For schedule of bidding
Rehabilitation of multi-purpose shed, Sual, Pangasinan | no. rehabilitated/repaired | 1 | 0 | 0 | 900000 | 883843 | 98.2048 | 16157 | 0 |  | On-going construction
MFO 3. IRRIGATION NETWORK SERVICES |  | 39 | 4 | 10.2564 | 123020000.21 | 116519100.21 | 94.7156 | 6500900 | 9018613.35 | 1.8037
Limmansangan SWIP, Alaminos, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 3044150.21 | 3044150.21 | 100 | 0 | 0 | 0 | MOA already signed, for submission of other pertinent documents for fund transfer
Bunao CIS, Mangatarem, Pangasinan | no. of repaired/rehabilitated | 1 | 1 | 100 | 5000000 | 5000000 | 100 | 0 | 2295312.41 | 0.45906 | Completed | 45
Don Gorio CIS, Mangatarem, Pangasinan | no. of repaired/rehabilitated | 1 | 1 | 100 | 5000000 | 5000000 | 100 | 0 | 2772890.27 | 0.55458 | Completed | 52
Victory Dam, Mangatarem, Pangasinan | no. of repaired/rehabilitated | 1 | 1 | 100 | 5000000 | 5000000 | 100 | 0 | 2012805.48 | 0.40256 | Completed; for inspection | 50
Simon-Casagatan CIS, Mangatarem, Pangasinan | no. of repaired/rehabilitated | 1 | 1 | 100 | 5000000 | 5000000 | 100 | 0 | 1937605.19 | 0.38752 | Completed; for inspection | 48
Cabaroan-Sanchez CIS, Mangatarem, Pang. | no. of repaired/rehabilitated | 1 | 0 | 0 | 5000000 | 5000000 | 100 | 0 | 0 | 0 | on-going @ 5% accomp; suspended due to standing crops | 55
Luna Este SWIP, umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1605650 | 1605650 | 100 | 0 | 0 | 0 | Bidded and awarded | 13
Puraw SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1500000 | 1500000 | 100 | 0 | 0 | 0 | Bidded and awarded | 14
Carayungan SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1200000 | 1200000 | 100 | 0 | 0 | 0 | Bidded and awarded | 13
Ricos II SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1200000 | 1200000 | 100 | 0 | 0 | 0 | Bidded and awarded | 12
Diaz SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5300000 | 5300000 | 100 | 0 | 0 | 0 | Bidded and awarded | 53
Digap SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1000000 | 1000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 12
Diket SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1200000 | 1200000 | 100 | 0 | 0 | 0 | Bidded and awarded | 12
Upper Banila Irrigation Project, Umingan, Pang. | no. of repaired/rehabilitated | 1 | 0 | 0 | 1500000 | 1500000 | 100 | 0 | 0 | 0 | Bidded and awarded | 15
Calaocan SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1200000 | 1200000 | 100 | 0 | 0 | 0 | Bidded and awarded | 14
Digad SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1000000 | 1000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 16
Tanggal Espiritu CIS, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 2000000 | 2000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 15
Tanggal Barrat CIS, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 3000000 | 3000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 20
Tanggal Vicente CIS, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 2000000 | 2000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 16
Matibbeg DD, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 2000000 | 2000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 20
Sira-Buenaflor DD, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 6000000 | 6000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 52
Waig-KabitnonganDD, San Quintin, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 4000000 | 4000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 30
Camagsese CIS, Sual, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5500000 | 0 | 0 | 5500000 | 0 | 0 | For submission of pertinent documents for FT by the LGU | 48
Victoria CIS, Sual, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5500000 | 5000000 | 90.9091 | 500000 | 0 | 0 | Obligated for fund transfer to LGU | 52
Tanggal Padua CIS, Sual, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5500000 | 5000000 | 90.9091 | 500000 | 0 | 0 | Obligated for fund transfer to LGU | 50
Nangalisan DD, Infanta, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 2000000 | 2000000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 15
Bamban CIS, Infanta, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 3000000 | 3000000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 19
Gayun Gayun CIS, Agno, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1500000 | 1500000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 12
Pateng I CIS, Agno, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1500000 | 1500000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 12
Pateng II CIS, Agno, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1500000 | 1500000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 11
Agbayani Dam, Balungao,Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 6000000 | 6000000 | 100 | 0 | 0 | 0 | Site still submerge in water | 53
Madilap Dam, Balungao, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5000000 | 5000000 | 100 | 0 | 0 | 0 | Site still submerge in water | 49
Catillaongan Dam, Balungao, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5000000 | 5000000 | 100 | 0 | 0 | 0 | On-going construction @ 30% accomp | 48
Calancian Dam, Balungao, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5000000 | 5000000 | 100 | 0 | 0 | 0 | On-going construction @ 15% accomp | 52
Casiaman DD, Bacnotan, La Union | no. of repaired/rehabilitated | 1 | 0 | 0 | 1500000 | 1500000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 14
Nagsabaran CIS, San Juan, La Union | no. of repaired/rehabilitated | 1 | 0 | 0 | 2000000 | 2000000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 15
Pideg I CIS, Tubao, La Union | no. of repaired/rehabilitated | 1 | 0 | 0 | 3510000 | 3509100 | 99.9744 | 900 | 0 | 0 | Already FT transferred to LGU for implementation | 23
Pideg II CIS, Tubao, La Union | no. of repaired/rehabilitated | 1 | 0 | 0 | 560200 | 560200 | 100 | 0 | 0 | 0 | Already FT transferred to LGU for implementation | 10
Dacnap- Baliw SSIP, Pugo, La Union | no. of repaired/rehabilitated | 1 | 0 | 0 | 4700000 | 4700000 | 100 | 0 | 0 | 0 | Already FT transferred to LGU for implementation | 40

## 16M_SARO-BMB-E-21-0001862
DEPARTMENT OF AGRICULTURE
REHABILITATION/RECOVERY ACCOMPLISHMENT REPORT
Typhoon Nika, Ofel, Pepito, Quinta, Rolly, Ulysses
SARO-BMB-E-21-0001862/ GAA CY 2021
As of August 02, 2021
Region I
P/P/As | Indicator | DESCRIPTION | LOCATION |  | BENEFICIARIES |  |  | PHYSICAL |  |  | FINANCIAL | [5 empty] | REMARKS
|  |  | PROVINCE | MUNICIPALITY | TARGET (No.) | SERVED |  | TARGET (No.) | ACCOMPLISHED |  | ALLOCATION (PhP) | OBLIGATION |  |  | DISBURSEMENT
[6 empty] | NO. | % |  | NO. | % |  | OBLIGATED (PhP) | UNOBLIGATED (PhP) | % | Disbursed | % (Disbursed vs Obligated)
Production Support Services Sub-Program | [10 empty] | 16000000 |  | 16000000
Corn Banner Program
Provision of Seeds
GM Hybrid Yellow Corn | bags | [6 empty] | 9000 | 0 | 0 | 5000000 | 0 | 0 |  | 0 | 0 | For Earmarking
High Value Crops Development Program
Provision of Seeds
Vegetables Seeds | kilogram | [6 empty] | 500 | 0 | 0 | 6000000 | 0 | 0 |  | 0 | 0 | For Posting (PhilGeps)
Livestock Banner Program
Livelihood Assistance Program
Cattle | heads | [6 empty] | 30 | 0 | 0 | 1460000 |  | 0 |  | 0 | 0 | For Earmarking
Chicken | heads | [6 empty] | 4000 | 0 | 0 | 2708000 | 0
Mallard Duck | heads | [6 empty] | 1200 | 0 | 0 | 832000 | 0 | 0 |  | 0 | 0
TOTAL |  |  |  |  | #REF! | #REF! |  |  |  |  | 16000000 |  |  | #REF!
Prepared by: |  | Reviewed by : |  | Certified by |  |  |  | Reviewed by : |  |  | Certified correct: |  |  |  |  | Noted by:
MARICHU C. VILLEGAS |  | IRENE P. TACTAc |  | GILDA R.RODRIGUEZ |  |  | JOEL G. MACONOCIDO | IRENE P. TACTAC |  |  | DOMINADOR R. LIM, JR. |  | ARNOLD T. EBREO | JOEL G. MACONOCIDO |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen |  | RDRRM Focal/Coordinator |  | Chief, Budget Section |  |  | OIC-Chief, Admin and Finance Division | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  | Chief, Accounting Section | OIC-Chief, Admin and Finance Division |  | OIC-Regional Executive Director

## ASF-14M_Indemnification (hidden)
DEPARTMENT OF AGRICULTURE
REHABILITATION/RECOVERY ACCOMPLISHMENT REPORT
For African Swine Fever Affected Farmers/Raisers
As of February 01, 2021
Region I
INTERVENTION | UNIT OF MEASURE | DESCRIPTION | LOCATION |  | BENEFICIARIES |  |  | PHYSICAL |  |  | FINANCIAL | [5 empty] | REMARKS
|  |  | PROVINCE | MUNICIPALITY | TARGET (No.) | SERVED |  | TARGET (No.) | ACCOMPLISHED |  | ALLOCATION (PhP) | OBLIGATION |  |  | DISBURSEMENT
[6 empty] | NO. | % |  | NO. | % |  | OBLIGATED (PhP) | UNOBLIGATED (PhP) | % | Disbursed | % (Disbursed vs Obligated)
Indemnification |  |  |  |  | #REF! | #REF! | #REF! | 2911 | 2911 | 100% | 14555000 | 14555000 | 0 | 100% | 14555000 | 100%
1. Distribution of cash assistance | no. of animals indemnified |  |  |  | #REF! | #REF! | #REF! | 2911 | 2911 | 100% | 14555000 | 14555000 | 0 | #REF! | 14555000 | 100% | Completed/ Distributed
TOTAL |  |  |  |  | #REF! | #REF! |  | 2911 | 2911 | 100% | 14555000 | 14555000 | 0 | #REF! | 14555000 | 100%
Prepared by: |  | Reviewed by : |  | Certified by |  |  |  | Reviewed by : |  |  | Certified correct: |  |  |  |  | Noted by:
JULIUS R. BRIONES |  | IRENE P. TACTAc |  | GILDA R.RODRIGUEZ |  |  | JOEL G. MACONOCIDO | IRENE P. TACTAC |  |  | CRISTINA A. JACINTO |  | ARNOLD T. EBREO | JOEL G. MACONOCIDO |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen |  | RDRRM Focal/Coordinator |  | Chief, Budget Section |  |  | OIC-Chief, Admin and Finance Division | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  | Chief, Accounting Section | OIC-Chief, Admin and Finance Division |  | OIC-Regional Executive Director