## Ineng-ASA-2019-00135
DEPARTMENT OF AGRICULTURE
REHABILITATION/RECOVERY ACCOMPLISHMENT REPORT
For Typhoon Ineng Affected Areas
ASA-2019-00135
As of August 02, 2021
P/P/As/Province |  | Output Indicator | Physical |  |  | Financial ('000) | [5 empty] | REMARKS
|  |  | Target (No.) | Accomplished |  | Allocation ('000) | OBLIGATION |  |  | DISBURSEMENT
|  |  |  | No. | % |  | Obligated ('000) | Unobligated ('000) | % | Disbursed | %
Rice Banner Program | [5 empty] | 32148 | 31761.354 | 386.646 | 98.7973 | 26738.979 | 84.1872
1. Provision of palay seeds |  | Area Served (ha) | 4060 | 4575 | 112.6847 | 20300 | 20286 | 14 | 99.931 | 20286 | 100 | Procured a total of 68,628 kg or 4,575 hectares which is higher than the target. This is due to efficient bidding process; Distribution to farmers complete.
2. Provision of soil ameliorants |  | No. of packs provided (@4kg/pack) | 4060 | 4060 | 100 | 3248 | 3248 | 0 | 100 | 3248 | 100 | Completed
3. Provision of agricultural machineries and equipment
| a. Rice Mill | No. of units provided
| b. Recirculating dryers | No. of units provided
| c. Multi-Purpose Lifting Machine | No. of units provided
3. Rehabilitation/Improvement and Construction of Small Scale Irrigation Projects (SSIPs)
| a. Small Water Impounding Projects/Diversion Dams | No. of units rehabilitated/constructed |  |  |  | 8600 | 8227.354 | 372.646 | 95.6669 | 3204.979 | 38.9552
[8 empty] | 0 | #DIV/0! |  |  | For PPC
| b. Mini Solar Powered Irrigation Projects (SPIS) | No. of units rehabilitated/constructed | [5 empty] | 0 | #DIV/0! |  |  | For PPC
[8 empty] | 0 | #DIV/0! |  |  | For PPC
Corn Banner Program | [5 empty] | 0 |  | 0 | #DIV/0! |  |  | For PPC
1. Provision of corn seeds |  | No. of bags provided | 0 |  |  | 0 |  | 0 | #DIV/0! |  |  | For PPC
[8 empty] | 0 | #DIV/0! |  |  | For PPC
2. Provision of agricultural machineries and equipment | [7 empty] | 0 | #DIV/0! |  |  | For PPC
| a.4-WD tractors | No. of units provided | [5 empty] | 0 | #DIV/0! |  |  | For PPC
| b. Combine harvester | No. of units provided | [5 empty] | 0 | #DIV/0! |  |  | For PPC
| c. Mobile dryer (6-toner) | No. of units provided | [5 empty] | 0 | #DIV/0! |  |  | For PPC
[8 empty] | 0 | #DIV/0! |  |  | For PPC
| Rehabilitation of Nagtrigoan SWIP | No. of units rehabilitated/constructed | 1 | 1 | 100 | 1000 | 908.697 | 91.303 | 90.8697 |  |  | On-going process of final billing with 100.00% physical accomplishment
| Rehabilitation of Dalayap DD | No. of units rehabilitated/constructed | 1 | 1 | 100 | 1000 | 882.05 | 117.95 | 88.205 |  |  | For inspection and verification of completeness of the project by RIC with 100.00% physical accomplishment
| Rehabilitation of Caunayan CIS | No. of units rehabilitated/constructed | 1 | 1 | 100 | 1200 | 1186.617 | 13.383 | 98.8847 | 1186.62 | 100.0003 | Completed
| Rehabilitation/Improvement of Lipay DD Canal lining | No. of units rehabilitated/constructed | 1 | 1 | 100 | 1000 | 991.826 | 8.174 | 99.1826 |  |  | For signature of as-built drawings with 100% physical accomplishment
| Improvement of Ester DD | No. of units rehabilitated/constructed | 1 | 1 | 100 | 500 | 492.949 | 7.051 | 98.5898 |  |  | Waiting for inspection report with 100% physical accomplishment
| Improvement of Esperanza DD | No. of units rehabilitated/constructed | 1 | 1 | 100 | 500 | 492.949 | 7.051 | 98.5898 | 492.949 | 100 | Completed
| Improvement of Bacsil Norte Canal Lining | No. of units rehabilitated/constructed | 1 | 1 | 100 | 450 | 445.406 | 4.594 | 98.9791 | 445.41 | 100.0009 | Completed
| Rehabilitation of Burbor Dam | No. of units rehabilitated/constructed | 1 | 1 | 100 | 1200 | 1200 | 0 | 100 | 1080 | 90 | 100.00% physical accomplishment
| Improvement of Nagpatpatan Canal Lining | No. of units rehabilitated/constructed | 1 | 1 | 100 | 1500 | 1376.86 | 123.14 | 91.7907 |  |  | Recommended for final inspection with 100.00% physical accomplishment
| Repair of Small Water Impounding Project-Nueva Era | No. of units rehabilitated/constructed | 1 |  |  | 250 | 250 | 0 | 100 |  |  | Suspended construction activities due to standing crops
High Value Crops Development Program | [5 empty] | 10300 | 10300 | 0 | 100 | 10300 | 100
1. Provision of assorted vegetable seeds |  | No. of kg provided | 1030 | 1274 | 123.6893 | 10300 | 10300 | 0 | 100 | 10300 | 100 | Completed
|  | Ilocos Norte | 900 |  |  | 9000
|  | Ilocos Sur | 100 |  |  | 1000
|  | La Union | 30 |  |  | 300
2. Provision of agricultural machineries and equipment
| a. Multi-Purpose lifting machine | No. of units provided | 0 |  |  | 0
| b. Multi-Cultivator | No. of units provided | 0 |  |  | 0
|  | Ilocos Norte | 0
|  | Ilocos Sur | 0
|  | La Union | 0
Livestock Banner Program | [5 empty] | 79000 | 79000 | 0 | 100 | 79000 | 100
a. Provision of livelihood projects (replacement of stocks) |  | No. of stocks provided |  |  |  | 75000 | 75000 | 0 | 100 | 75000 | 100
Regionwide
|  | Goat | 2500 | 2500 | 100 | 37500 | 37500 | 0 | 100 | 37500 | 100 | Completed
|  | Cattle | 741 | 492 | 66.3968 | 31500 | 31500 | 0 | 100 | 31500 | 100 | Completed
|  | Chicken | 5000 | 4241 | 84.82 | 3000 | 3000 | 0 | 100 | 3000 | 100 | Completed
|  | Duck | 5000 | 4759 | 95.18 | 3000 | 3000 | 0 | 100 | 3000 | 100 | Completed
b. Provision of drugs and biologics |  | No. of doses provided | 50000 | 50000 | 100 | 4000 | 4000 | 0 | 100 | 4000 | 100 | Completed
|  | Ilocos Norte | 50000 |  |  | 4000
| GRAND TOTAL |  |  |  |  | 121448 | 121061.354 | 386.646 |  | 116038.979 | 95.8514
Prepared by: |  | Reviewed by : |  |  | Certified correct: | [5 empty] | Noted by:
MARICHU C. VILLEGAS |  | IRENE P. TACTAC |  |  | DOMINADOR R. LIM, JR. |  |  | ARNOLD T. EBREO |  |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen |  | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  |  | Chief, Accounting Section |  |  | OIC-Regional Executive Director

## SARO# BMB-E-16-0019036Lando (hidden)
DEPARTMENT OF AGRICULTURE
Regional Field Office
San Fernando City, La Union
STATUS OF CALAMITY FUND FOR TYPHOON LANDO
SARO #BMB-E-16-0019036
as of November 30, 2018
PROGRAM/PROJECTS/ ACTIVITIES | INDICATOR | PHYSICAL STATUS |  |  | FINANCIAL STATUS |  |  |  | DISBURSEMENT |  | STATUS/ REMARKS
|  | TARGET (No.) | ACCOMPLISHMENT |  | ALLOC. | OBLIG. | % | BALANCE | DISBURSED | %
|  |  | No. | %
GRAND TOTAL |  |  |  |  | 151238620.21 | 144600969.21 | 95.6111 | 6637651 | 25404114.15 | 17.5684
MFO 2. TECHNICAL SUPPORT SERVICES |  |  |  |  | 28218620 | 28081869 | 99.5154 | 136751 | 16385500.8 | 58.349
MFO 2.1 PRODUCTION SUPPORT SERVICES |  |  |  |  | 17668620 | 17668620 | 100 | 0 | 16385500.8 | 92.7379 |  | 15
Palay Certified Seeds (40kg/bag) | no. of bags distributed | 8577 | 8577 | 100 | 11664720 | 11664720 | 100 | 0 | 10381600.8 | 89 | Distribution completed
Soil Ameliorant (packs of 2 kg) | no. of packs distributed | 17154 | 8716 | 50.8103 | 6003900 | 6003900 | 100 | 0 | 6003900 | 100 | On-going distribution
MFO 2.3 RESEARCH & DEVELOPMENT SERVICES |  | 5 |  |  | 10550000 | 10413249 | 98.7038 | 136751 | 0
A. Rehab/repair of Da-Research & Experimentation Center | no. rehabilitated/repaired | 5 | 0 | 0 | 10550000 | 10413249 | 98.7038 | 136751 | 0
Rehabilitation of fertilizer bodega, PREC, Sta. Barabara, Pang. | no. rehabilitated/repaired | 1 | 0 | 0 | 1000000 | 994072 | 99.4072 | 5928 | 0 |  | 65 % accomplishment
Rehabilitation of Motor pool garage, Sual & PREC, Sta. Barabara, Pang. | no. rehabilitated/repaired | 1 | 0 | 0 | 3450000 | 3335334 | 96.6763 | 114666 | 0 |  | Motorpool garage, Sual : On-going construction while the Motorpool Garage, Sta. Barbara : NTP to be issued/to be signed
Rehabilitation of guest house 2, PREC, Sta. Barbara, Pangasinan | no. rehabilitated/repaired | 1 | 0 | 0 | 2300000 | 2300000 | 100 | 0 | 0 |  | For schedule of bidding; On going revision due to change of site
Rehabilitation of duck house, Sual, Pangasinan | no. rehabilitated/repaired | 1 | 0 | 0 | 2900000 | 2900000 | 100 | 0 | 0 |  | For approval of PR, POW and revised plans. For schedule of bidding
Rehabilitation of multi-purpose shed, Sual, Pangasinan | no. rehabilitated/repaired | 1 | 0 | 0 | 900000 | 883843 | 98.2048 | 16157 | 0 |  | On-going construction
MFO 3. IRRIGATION NETWORK SERVICES |  | 39 | 4 | 10.2564 | 123020000.21 | 116519100.21 | 94.7156 | 6500900 | 9018613.35 | 1.8037
Limmansangan SWIP, Alaminos, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 3044150.21 | 3044150.21 | 100 | 0 | 0 | 0 | MOA already signed, for submission of other pertinent documents for fund transfer
Bunao CIS, Mangatarem, Pangasinan | no. of repaired/rehabilitated | 1 | 1 | 100 | 5000000 | 5000000 | 100 | 0 | 2295312.41 | 0.45906 | Completed | 45
Don Gorio CIS, Mangatarem, Pangasinan | no. of repaired/rehabilitated | 1 | 1 | 100 | 5000000 | 5000000 | 100 | 0 | 2772890.27 | 0.55458 | Completed | 52
Victory Dam, Mangatarem, Pangasinan | no. of repaired/rehabilitated | 1 | 1 | 100 | 5000000 | 5000000 | 100 | 0 | 2012805.48 | 0.40256 | Completed; for inspection | 50
Simon-Casagatan CIS, Mangatarem, Pangasinan | no. of repaired/rehabilitated | 1 | 1 | 100 | 5000000 | 5000000 | 100 | 0 | 1937605.19 | 0.38752 | Completed; for inspection | 48
Cabaroan-Sanchez CIS, Mangatarem, Pang. | no. of repaired/rehabilitated | 1 | 0 | 0 | 5000000 | 5000000 | 100 | 0 | 0 | 0 | on-going @ 5% accomp; suspended due to standing crops | 55
Luna Este SWIP, umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1605650 | 1605650 | 100 | 0 | 0 | 0 | Bidded and awarded | 13
Puraw SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1500000 | 1500000 | 100 | 0 | 0 | 0 | Bidded and awarded | 14
Carayungan SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1200000 | 1200000 | 100 | 0 | 0 | 0 | Bidded and awarded | 13
Ricos II SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1200000 | 1200000 | 100 | 0 | 0 | 0 | Bidded and awarded | 12
Diaz SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5300000 | 5300000 | 100 | 0 | 0 | 0 | Bidded and awarded | 53
Digap SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1000000 | 1000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 12
Diket SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1200000 | 1200000 | 100 | 0 | 0 | 0 | Bidded and awarded | 12
Upper Banila Irrigation Project, Umingan, Pang. | no. of repaired/rehabilitated | 1 | 0 | 0 | 1500000 | 1500000 | 100 | 0 | 0 | 0 | Bidded and awarded | 15
Calaocan SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1200000 | 1200000 | 100 | 0 | 0 | 0 | Bidded and awarded | 14
Digad SWIP, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1000000 | 1000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 16
Tanggal Espiritu CIS, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 2000000 | 2000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 15
Tanggal Barrat CIS, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 3000000 | 3000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 20
Tanggal Vicente CIS, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 2000000 | 2000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 16
Matibbeg DD, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 2000000 | 2000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 20
Sira-Buenaflor DD, Umingan, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 6000000 | 6000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 52
Waig-KabitnonganDD, San Quintin, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 4000000 | 4000000 | 100 | 0 | 0 | 0 | Bidded and awarded | 30
Camagsese CIS, Sual, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5500000 | 0 | 0 | 5500000 | 0 | 0 | For submission of pertinent documents for FT by the LGU | 48
Victoria CIS, Sual, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5500000 | 5000000 | 90.9091 | 500000 | 0 | 0 | Obligated for fund transfer to LGU | 52
Tanggal Padua CIS, Sual, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5500000 | 5000000 | 90.9091 | 500000 | 0 | 0 | Obligated for fund transfer to LGU | 50
Nangalisan DD, Infanta, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 2000000 | 2000000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 15
Bamban CIS, Infanta, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 3000000 | 3000000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 19
Gayun Gayun CIS, Agno, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1500000 | 1500000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 12
Pateng I CIS, Agno, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1500000 | 1500000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 12
Pateng II CIS, Agno, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 1500000 | 1500000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 11
Agbayani Dam, Balungao,Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 6000000 | 6000000 | 100 | 0 | 0 | 0 | Site still submerge in water | 53
Madilap Dam, Balungao, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5000000 | 5000000 | 100 | 0 | 0 | 0 | Site still submerge in water | 49
Catillaongan Dam, Balungao, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5000000 | 5000000 | 100 | 0 | 0 | 0 | On-going construction @ 30% accomp | 48
Calancian Dam, Balungao, Pangasinan | no. of repaired/rehabilitated | 1 | 0 | 0 | 5000000 | 5000000 | 100 | 0 | 0 | 0 | On-going construction @ 15% accomp | 52
Casiaman DD, Bacnotan, La Union | no. of repaired/rehabilitated | 1 | 0 | 0 | 1500000 | 1500000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 14
Nagsabaran CIS, San Juan, La Union | no. of repaired/rehabilitated | 1 | 0 | 0 | 2000000 | 2000000 | 100 | 0 | 0 | 0 | Obligated for fund transfer to LGU | 15
Pideg I CIS, Tubao, La Union | no. of repaired/rehabilitated | 1 | 0 | 0 | 3510000 | 3509100 | 99.9744 | 900 | 0 | 0 | Already FT transferred to LGU for implementation | 23
Pideg II CIS, Tubao, La Union | no. of repaired/rehabilitated | 1 | 0 | 0 | 560200 | 560200 | 100 | 0 | 0 | 0 | Already FT transferred to LGU for implementation | 10
Dacnap- Baliw SSIP, Pugo, La Union | no. of repaired/rehabilitated | 1 | 0 | 0 | 4700000 | 4700000 | 100 | 0 | 0 | 0 | Already FT transferred to LGU for implementation | 40

## Fall_ArmyWorm
DEPARTMENT OF AGRICULTURE
REHABILITATION/RECOVERY ACCOMPLISHMENT REPORT
For Fall ArmyWorm Affected Areas
ASA # 2020- 000111
As of June 01, 2021
Region I
INTERVENTION | UNIT OF MEASURE | DESCRIPTION | LOCATION |  | BENEFICIARIES |  |  | PHYSICAL |  |  | FINANCIAL | [5 empty] | REMARKS
|  |  | PROVINCE | MUNICIPALITY | TARGET (No.) | SERVED |  | TARGET (No.) | ACCOMPLISHED |  | ALLOCATION (PhP) | OBLIGATION |  |  | DISBURSEMENT
[6 empty] | NO. | % |  | NO. | % |  | OBLIGATED (PhP) | UNOBLIGATED (PhP) | % | Disbursed | % (Disbursed vs Obligated)
Procurement of Pheromone lure | pcs |  |  |  | #REF! | #REF! | #REF! | 4435 | 4435 | 100% | 2883000 | 2882750 | 250 | 99.99% | 2882750 | 100% | Completed
Procurement of Insecticides |  |  |  |  | #REF! | #REF! | #REF! | 4633 | 4633 | 100% | 5200000 | 5126470 | 73530 |  | 3305390 | 100% | Completed
a. ) Organic insecticides |  |  |  |  | #REF! | #REF! | #REF! |  |  |  |  | 3305390 | 0
- Botanical | bottle | [6 empty] | 1655 | 1655 | 100%
- Microbial (Bacillus sp.) | bottle | [6 empty] | 400 | 400 | 100%
b.) Synthetic insecticides
- Spinetoram | bottle | [6 empty] | 430 | 430 | 100%
- Tetraniliprole | bottle | [6 empty] | 430 | 430 | 100%
- Chlorfluazon | bottle | [6 empty] | 1718 | 1718 | 100% |  | 1821080 | 0 |  | 1821080 | 100% | Completed/ Delivered
TOTAL |  |  |  |  | #REF! | #REF! |  | 9068 | 9068 |  | 8083000 | 8009220 | 73780 | 0 | 8009220
Prepared by: |  | Reviewed by : |  | Certified by |  |  |  | Reviewed by : |  |  | Certified correct: |  |  |  |  | Noted by:
MARICHU C. VILLEGAS |  | IRENE P. TACTAc |  | GILDA R.RODRIGUEZ |  |  | JOEL G. MACONOCIDO | IRENE P. TACTAC |  |  | DOMINADOR R. LIM, JR. |  | ARNOLD T. EBREO |  |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen |  | RDRRM Focal/Coordinator |  | Chief, Budget Section |  |  | OIC-Chief, Admin and Finance Division | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  | Chief, Accounting Section |  |  | OIC-Regional Executive Director

## ASF-2021-000045
DEPARTMENT OF AGRICULTURE
REHABILITATION/RECOVERY ACCOMPLISHMENT REPORT
For African Swine Fever Virus Detection Kit
ASA-2021-000045
As of August 02, 2021
Region I
INTERVENTION | UNIT OF MEASURE | DESCRIPTION | LOCATION |  | BENEFICIARIES |  |  | PHYSICAL |  |  | FINANCIAL | [5 empty] | REMARKS
|  |  | PROVINCE | MUNICIPALITY | TARGET (No.) | SERVED |  | TARGET (No.) | ACCOMPLISHED |  | ALLOCATION (PhP) | OBLIGATION |  |  | DISBURSEMENT
[6 empty] | NO. | % |  | NO. | % |  | OBLIGATED (PhP) | UNOBLIGATED (PhP) | % | Disbursed | % (Disbursed vs Obligated)
[5 empty] | #REF! | #REF! | #REF! | 150 | 150 |  | 9450000 | 9450000 | 0 | 100% | -
Procurement of Convection Polymerase Chain Reaction (cPCR) | pcs. |  |  |  | #REF! | #REF! | #REF! | 150 | 150 | 100% | 9450000 | 9450000 | - | #REF! | - | - | Distributed; For processing of payment
TOTAL |  |  |  |  | #REF! | #REF! |  | 150 | 150 | 100% | 9450000 | 9450000 | - | #REF! | -
Prepared by: |  | Reviewed by : |  | Certified by |  |  |  | Reviewed by : |  |  | Certified correct: |  |  |  |  | Noted by:
MARICHU C. VILLEGAS |  | IRENE P. TACTAc |  | GILDA R.RODRIGUEZ |  |  | JOEL G. MACONOCIDO | IRENE P. TACTAC |  |  | DOMINADOR R. LIM, JR. |  | ARNOLD T. EBREO | JOEL G. MACONOCIDO |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen |  | RDRRM Focal/Coordinator |  | Chief, Budget Section |  |  | OIC-Chief, Admin and Finance Division | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  | Chief, Accounting Section | OIC-Chief, Admin and Finance Division |  | OIC-Regional Executive Director

## ASA- 2021-000035
DEPARTMENT OF AGRICULTURE
REHABILITATION/RECOVERY ACCOMPLISHMENT REPORT
Typhoon Nika, Ofel, Pepito, Quinta, Rolly, Ulysses
ASA- 2021-000035
As of august 02, 2021
Region I
INTERVENTION | UNIT OF MEASURE | DESCRIPTION | LOCATION |  | BENEFICIARIES |  |  | PHYSICAL |  |  | FINANCIAL | [5 empty] | REMARKS
|  |  | PROVINCE | MUNICIPALITY | TARGET (No.) | SERVED |  | TARGET (No.) | ACCOMPLISHED |  | ALLOCATION (PhP) | OBLIGATION |  |  | DISBURSEMENT
[6 empty] | NO. | % |  | NO. | % |  | OBLIGATED (PhP) | UNOBLIGATED (PhP) | % | Disbursed | % (Disbursed vs Obligated)
[5 empty] | #REF! | #REF! | #REF! | 500 | 0 |  | 6000000 | 0 | 6000000 | 0% | 0
Provision of Assorted vegetable seeds | kilograms |  |  |  | #REF! | #REF! | #REF! | 500 |  |  | 6000000 |  |  | #REF! |  |  | For Posting (PhilGeps)
TOTAL |  |  |  |  | #REF! | #REF! |  | 500 |  |  | 6000000 |  |  | #REF!
Prepared by: |  | Reviewed by : |  | Certified by |  |  |  | Reviewed by : |  |  | Certified correct: |  |  |  |  | Noted by:
MARICHU C. VILLEGAS |  | IRENE P. TACTAc |  | GILDA R.RODRIGUEZ |  |  | JOEL G. MACONOCIDO | IRENE P. TACTAC |  |  | DOMINADOR R. LIM, JR. |  | ARNOLD T. EBREO | JOEL G. MACONOCIDO |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen |  | RDRRM Focal/Coordinator |  | Chief, Budget Section |  |  | OIC-Chief, Admin and Finance Division | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  | Chief, Accounting Section | OIC-Chief, Admin and Finance Division |  | OIC-Regional Executive Director

## ASF-41M_Indemnification
DEPARTMENT OF AGRICULTURE
REHABILITATION/RECOVERY ACCOMPLISHMENT REPORT
For African Swine Fever Affected Farmers/Raisers
ASA # 2020-000487
As of August 02, 2021
Region I
INTERVENTION | UNIT OF MEASURE | DESCRIPTION | LOCATION |  | BENEFICIARIES |  |  | PHYSICAL |  |  | FINANCIAL | [5 empty] | REMARKS
|  |  | PROVINCE | MUNICIPALITY | TARGET (No.) | SERVED |  | TARGET (No.) | ACCOMPLISHED |  | ALLOCATION (PhP) | OBLIGATION |  |  | DISBURSEMENT
[6 empty] | NO. | % |  | NO. | % |  | OBLIGATED (PhP) | UNOBLIGATED (PhP) | % | Disbursed | % (Disbursed vs Obligated)
Indemnification |  |  |  |  | #REF! | #REF! | #REF! | 8338 | 8323 | 99.82% | 41690000 | 41690000 | 0 | 100% | 41615000
| no. of animals indemnified |  |  |  | #REF! | #REF! | #REF! | 8338 | 8323 | 99.82% | 41690000 | 41690000 | 0 | #REF! | 41615000 | 99.82% | Distributed; Remaining amount is for savings
TOTAL |  |  |  |  | #REF! | #REF! |  | 8338 | 8323 | 99.82% | 41690000 | 41690000 | 0 | #REF! | 41615000
Prepared by: |  | Reviewed by : |  | Certified by |  |  |  | Reviewed by : |  |  | Certified correct: |  |  |  |  | Noted by:
MARICHU C. VILLEGAS |  | IRENE P. TACTAc |  | GILDA R.RODRIGUEZ |  |  | JOEL G. MACONOCIDO | IRENE P. TACTAC |  |  | DOMINADOR R. LIM, JR. |  | ARNOLD T. EBREO | JOEL G. MACONOCIDO |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen |  | RDRRM Focal/Coordinator |  | Chief, Budget Section |  |  | OIC-Chief, Admin and Finance Division | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  | Chief, Accounting Section | OIC-Chief, Admin and Finance Division |  | OIC-Regional Executive Director

## 60M_ASA No. 2021-000022
DEPARTMENT OF AGRICULTURE
REHABILITATION/RECOVERY ACCOMPLISHMENT REPORT
For African Swine Fever Affected Farmers/Raisers
ASA-No 2021-000022
As of August 02, 2021
Region I
P/P/As | Indicator | DESCRIPTION | LOCATION |  | BENEFICIARIES |  |  | PHYSICAL |  |  | FINANCIAL | [5 empty] | REMARKS
|  |  | PROVINCE | MUNICIPALITY | TARGET (No.) | SERVED |  | TARGET (No.) | ACCOMPLISHED |  | ALLOCATION (PhP) | OBLIGATION |  |  | DISBURSEMENT
[6 empty] | NO. | % |  | NO. | % |  | OBLIGATED (PhP) | UNOBLIGATED (PhP) | % | Disbursed | % (Disbursed vs Obligated)
Support to Operations | [10 empty] | 60000000 |  | 600000
Re-Stocking of Animals | [10 empty] | 24000000 |  | 24000000
Swine | head | [6 empty] | 3600 |  |  | 24000000 |  | 24000000 |  |  |  | For Bid-Opening
Provision of feeds, supplements, drugs and biologics | [10 empty] | 36000000 |  | 36000000
Multi-Vitamins | dose | [6 empty] | 48000 |  |  | 480000 |  | 480000 |  |  |  | For Bid-Opening
Antibiotic | dose | [6 empty] | 28800 |  |  | 870000 |  | 870000
Dewormer | dose | [6 empty] | 12000 |  |  | 90000 |  | 90000
Feeds | bag | [6 empty] | 21600 |  |  | 34560000 |  | 34560000
Drugs and Biologics | box
Prepared by: |  | Reviewed by : |  | Certified by |  |  |  | Reviewed by : |  |  | Certified correct: |  |  |  |  | Noted by:
MARICHU C. VILLEGAS |  | IRENE P. TACTAc |  | GILDA R.RODRIGUEZ |  |  | JOEL G. MACONOCIDO | IRENE P. TACTAC |  |  | DOMINADOR R. LIM, JR. |  | ARNOLD T. EBREO | JOEL G. MACONOCIDO |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen |  | RDRRM Focal/Coordinator |  | Chief, Budget Section |  |  | OIC-Chief, Admin and Finance Division | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  | Chief, Accounting Section | OIC-Chief, Admin and Finance Division |  | OIC-Regional Executive Director

## ASF-ASA-2020-000126
DEPARTMENT OF AGRICULTURE
REHABILITATION/RECOVERY ACCOMPLISHMENT REPORT
For African Swine Fever Affected Farmers/Raisers
ASA-2020-000126
As of February 01, 2021
Region I
INTERVENTION | UNIT OF MEASURE | DESCRIPTION | LOCATION |  | BENEFICIARIES |  |  | PHYSICAL |  |  | FINANCIAL | [5 empty] | REMARKS
|  |  | PROVINCE | MUNICIPALITY | TARGET (No.) | SERVED |  | TARGET (No.) | ACCOMPLISHED |  | ALLOCATION (PhP) | OBLIGATION |  |  | DISBURSEMENT
[6 empty] | NO. | % |  | NO. | % |  | OBLIGATED (PhP) | UNOBLIGATED (PhP) | % | Disbursed | % (Disbursed vs Obligated)
Indemnification |  |  |  |  | #REF! | #REF! | #REF! | 4447 | 4447 | 100% | 22235000 | 22235000 | 0 | 100% | 22235000 | 100%
1. Distribution of cash assistance | no. of animals indemnified |  |  |  | #REF! | #REF! | #REF! | 4447 | 4447 | 100% | 22235000 | 22235000 | 0 | #REF! | 22235000 | 100%
TOTAL |  |  |  |  | #REF! | #REF! |  | 4447 | 4447 | 100% | 22235000 | 22235000 | 0 | #REF! | 22235000 | 100%
Prepared by: |  | Reviewed by : |  | Certified by |  |  |  | Reviewed by : |  |  | Certified correct: |  |  |  |  | Noted by:
JULIUS R. BRIONES |  | IRENE P. TACTAc |  | GILDA R.RODRIGUEZ |  |  | JOEL G. MACONOCIDO | IRENE P. TACTAC |  |  | CRISTINA A. JACINTO |  | ARNOLD T. EBREO | JOEL G. MACONOCIDO |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen |  | RDRRM Focal/Coordinator |  | Chief, Budget Section |  |  | OIC-Chief, Admin and Finance Division | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  | Chief, Accounting Section | OIC-Chief, Admin and Finance Division |  | OIC-Regional Executive Director

## ASF-ASA-2021-017
DEPARTMENT OF AGRICULTURE
REHABILITATION/RECOVERY ACCOMPLISHMENT REPORT
For African Swine Fever Affected Farmers/Raisers
ASA-2021-017
As of June 01, 2021
Region I
INTERVENTION | UNIT OF MEASURE | DESCRIPTION | LOCATION |  | BENEFICIARIES |  |  | PHYSICAL |  |  | FINANCIAL | [5 empty] | REMARKS
|  |  | PROVINCE | MUNICIPALITY | TARGET (No.) | SERVED |  | TARGET (No.) | ACCOMPLISHED |  | ALLOCATION (PhP) | OBLIGATION |  |  | DISBURSEMENT
[6 empty] | NO. | % |  | NO. | % |  | OBLIGATED (PhP) | UNOBLIGATED (PhP) | % | Disbursed | % (Disbursed vs Obligated)
Indemnification |  |  |  |  | #REF! | #REF! | #REF! | 2122 | 2122 |  | 10610000 | 10610000 | 0 | 100% | 10610000
Distribution of cash assistance | no. of animals indemnified |  |  |  | #REF! | #REF! | #REF! | 2122 | 2122 | 100% | 10610000 | 10610000 | 0 | #REF! | 10610000 | 100% | Completed/ Distributed
TOTAL |  |  |  |  | #REF! | #REF! |  | 2122 | 2122 | 100% | 10610000 | 10610000 | 0 | #REF! | 10610000 | 100%
Prepared by: |  | Reviewed by : |  | Certified by |  |  |  | Reviewed by : |  |  | Certified correct: |  |  |  |  | Noted by:
MARICHU C. VILLEGAS |  | IRENE P. TACTAc |  | GILDA R.RODRIGUEZ |  |  | JOEL G. MACONOCIDO | IRENE P. TACTAC |  |  | DOMINADOR R. LIM, JR. |  | ARNOLD T. EBREO | JOEL G. MACONOCIDO |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen |  | RDRRM Focal/Coordinator |  | Chief, Budget Section |  |  | OIC-Chief, Admin and Finance Division | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  | Chief, Accounting Section | OIC-Chief, Admin and Finance Division |  | OIC-Regional Executive Director

## ASF-14M_Indemnification (hidden)
DEPARTMENT OF AGRICULTURE
REHABILITATION/RECOVERY ACCOMPLISHMENT REPORT
For African Swine Fever Affected Farmers/Raisers
As of February 01, 2021
Region I
INTERVENTION | UNIT OF MEASURE | DESCRIPTION | LOCATION |  | BENEFICIARIES |  |  | PHYSICAL |  |  | FINANCIAL | [5 empty] | REMARKS
|  |  | PROVINCE | MUNICIPALITY | TARGET (No.) | SERVED |  | TARGET (No.) | ACCOMPLISHED |  | ALLOCATION (PhP) | OBLIGATION |  |  | DISBURSEMENT
[6 empty] | NO. | % |  | NO. | % |  | OBLIGATED (PhP) | UNOBLIGATED (PhP) | % | Disbursed | % (Disbursed vs Obligated)
Indemnification |  |  |  |  | #REF! | #REF! | #REF! | 2911 | 2911 | 100% | 14555000 | 14555000 | 0 | 100% | 14555000 | 100%
1. Distribution of cash assistance | no. of animals indemnified |  |  |  | #REF! | #REF! | #REF! | 2911 | 2911 | 100% | 14555000 | 14555000 | 0 | #REF! | 14555000 | 100% | Completed/ Distributed
TOTAL |  |  |  |  | #REF! | #REF! |  | 2911 | 2911 | 100% | 14555000 | 14555000 | 0 | #REF! | 14555000 | 100%
Prepared by: |  | Reviewed by : |  | Certified by |  |  |  | Reviewed by : |  |  | Certified correct: |  |  |  |  | Noted by:
JULIUS R. BRIONES |  | IRENE P. TACTAc |  | GILDA R.RODRIGUEZ |  |  | JOEL G. MACONOCIDO | IRENE P. TACTAC |  |  | CRISTINA A. JACINTO |  | ARNOLD T. EBREO | JOEL G. MACONOCIDO |  | NESTOR D. DOMENDEN, CESO IV
Report Officer, RDRRM Opcen |  | RDRRM Focal/Coordinator |  | Chief, Budget Section |  |  | OIC-Chief, Admin and Finance Division | RDRRM Focal/Coordinator |  |  | OIC, Budget Section |  | Chief, Accounting Section | OIC-Chief, Admin and Finance Division |  | OIC-Regional Executive Director