## PMR
Department of Agriculture Regional Field Office 1 | [11 empty] | Procurement Monitoring Report as of January 14, 2025
[5 empty] | Actual Procurement Activities | [20 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column1 | Column2
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
DA-RFO-1-2024-GOODS-069-N | NEGOTIATED PROCUREMENT OF SUPPLY, DELIVERY AND TESTING OF TWO (2) UNITS VETERINARY ULTRASOUND EQUIPMENT (BRANDED) | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | October 14-25, 2024 |  | 2024-10-18 |  | 2024-10-25 |  | 2024-11-19 | 2024-11-22 | 2024-11-29 | 28 | 35 |  | 2024-12-02 | 2024-12-10 | 2024-12-10 | 8 |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 3100000 |  |  | 2761580 |  |  | 0.10917 | 1.COA 2.RAFC 3.PCCI | 2024-10-18 |  | 2024-10-25 | 2024-11-19 | 2024-11-22 |  |  | FALSE | FALSE
DA-RFO-1-2024-GOODS-070 | SUPPLY, DELIVERY, INSTALLATION AND ASSEMBLY OF TWO (2) UNITS DIGITAL WEIGHING SCALE (BRANDED) WITH CATTLE SQUEEZER | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | July 10-30, 2024 |  | 2024-07-17 |  | 2024-08-12 |  | 2024-08-14 | 21-23-Aug-24 | 2024-09-12 |  |  |  | 2024-09-16 | 2024-09-27 | 2024-09-27 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 1600000 |  |  | 1200000 |  |  |  | 1.COA 2.RAFC 3.PCCI | 2024-07-17 |  | 2024-08-12 | 2024-08-14 | 21-23-Aug-24
DA-RFO-1-2024-GOODS-071 | SUPPLY AND DELIVERY OF SIX (6) HEADS PUREBREED ISLAND BORN BRAHMAN CATTLE AND FOURTEEN (14) HEADS UPGRADED CATTLE (BREEDER) | PMED-AMIA | No | Competitive Bidding | N/A | July 24, 2024 to August 12, 2024 |  | 2024-07-31 |  | 2024-08-12 |  | 2024-08-13 | 21-23-Aug-24 | 2024-09-10 |  | 29 |  | 2024-09-16 | 2024-10-01 | 2024-10-01 | 15 |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 1540000 |  |  | 1539000 |  |  | 0.00064935 | 1.COA 2.RAFC 3.PCCI | 2024-07-31 |  | 2024-08-12 | 2024-08-13 | 21-23-Aug-24 |  |  | FALSE | FALSE
DA-RFO-1-2024-GOODS-072 | SUPPLY AND DELIVERY OF EIGHT THOUSAND (8,000) KILORAMS GARLIC PLANTING MATERIALS | HVCDP | No | Competitive Bidding | 2024-07-02 | August 5, 2024 to August 27, 2024 |  | 2024-08-13 |  | 2024-08-27 |  | 2024-08-30 | 2024-09-05 | 2024-09-09 | 9 | 13 |  | 2024-09-10 | 2024-09-24 | 2024-09-24 | 14 |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 2000000 |  |  | 1996800 |  |  | 0.0016 | 1.COA 2.RAFC 3.PCCI | 2024-08-13 |  | 2024-08-27 | 2024-08-30 | 2024-09-05 |  |  | FALSE | FALSE
DA-RFO-1-2024-GOODS-073 | SUPPLY AND DELIVERY OF SEVEN (7) UNITS MULTICROP THRESHER | CORN | No | Competitive Bidding | N/A | August 7, 2024 to August 27, 2024 |  | 2024-08-14 |  | 2024-08-27 |  | 2024-08-27 | 10-11-Sep-24 | 2024-09-27 |  |  |  | 2024-09-27 | 2024-08-30 | 2024-08-30 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 1750000 |  |  | 1749986 |  |  |  | 1.COA 2.RAFC 3.PCCI | 2024-08-14 |  | 2024-08-27 | 2024-08-27 | 10-11-Sep-24 |  |  | FALSE | FALSE
-
DA-RFO-1-2024-GOODS-074 | LOT 1: SUPPLY AND DELIVERY OF NINETY-ONE THOUSAND NINETY-ONE (91,091) PACKS SOIL AMELIORANT | RICE | No | Competitive Bidding | 2024-07-17 | August 14, 2024 to September 3, 2024 |  | 2024-08-22 |  | 2024-09-03 |  | 2024-09-09 | 2024-09-16 | 2024-10-16 | 1900-01-12 | 1900-02-11 |  | 2024-10-16 | 2024-10-21 | 2024-10-21 | 5 |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 91091000 |  |  | 68318250 |  |  | 0.25 | 1.COA 2.RAFC 3.PCCI | 2024-08-22 |  | 2024-09-03 | 2024-09-09 | 2024-09-17 |  |  | FALSE | FALSE
DA-RFO-1-2024-GOODS-074 | LOT 2: SUPPLY AND DELIVERY OF FORTY THOUSAND (40,000) PACKS SOIL AMELIORANT | RICE | No | Competitive Bidding | 2024-07-17 | August 14, 2024 to September 3, 2024 |  | 2024-08-22 |  | 2024-09-03 |  | 2024-09-09 | 2024-09-17 | 2024-10-11 |  |  |  | 2024-10-14 | 2024-10-21 | 2024-10-21 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 10000000 |  |  | 10000000 |  |  |  | 1.COA 2.RAFC 3.PCCI | 2024-08-22 |  | 2024-09-03 | 2024-09-09 | 2024-09-17
DA-RFO-1-2024-GOODS-076 | SUPPLY AND DELIVERY OF ONE (1) UNIT 4-WHEEL DRIVE TRACTOR | AMIA | No | Competitive Bidding | N/A | September 6-25, 2024 |  | 2024-09-13 |  | 2024-09-27 |  | 2024-10-04 | 2024-10-15 | 2024-11-05 | 1900-01-17 | 1900-02-07 |  | 2024-11-08 | 2024-11-19 | 2024-11-19 | 11 |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 1200000 |  |  | 1195000 |  |  | 0.0041667 | 1.COA 2.RAFC 3.PCCI | 2024-09-13 |  | 2024-09-27 | 2024-10-04 | 2024-10-15 |  |  | FALSE | FALSE
DA-RFO-1-2024-GOODS-077-R | REBIDDING OF SUPPLY AND DELIVERY OF NINE (9) UNITS RICE COMBINE HARVESTER | RICE | No | Competitive Bidding | 2024-08-29 | November 27, 2024 to December 19, 2024 |  | 2024-12-04 |  | 2024-12-18 |  | 2024-12-18 | 2024-12-19 | 2024-12-20 |  |  |  | 2024-12-20 | 2024-12-23 | 2024-12-23 |  |  | 2024-12-26 | 2024-12-26 | Government of the Philippines (current year's budget) | 13950000 |  |  | 13932000 |  |  |  | 1.COA 2.RAFC 3.PCCI | 1.COA 2.RAFC 3.PCCI | 2024-12-04 | 2024-12-18 | 2024-12-18 | 2024-12-19
DA-RFO-1-2024-GOODS-079 | SUPPLY AND DELIVERY OF ONE (1) UNIT MOTOR VEHICLE | GSS | No | Competitive Bidding | N/A | October 3-22, 2024 |  | 2024-10-10 |  | 2024-11-04 |  | 2024-11-06 | 2024-11-15 | 2024-11-29 | 1900-01-10 | 1900-01-24 |  | 2024-11-29 | 2024-12-13 | 2024-12-13 | 14 |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 1339800 |  |  | 1261000 |  |  | 0.058815 | 1.COA 2.RAFC 3.PCCI | 2024-10-10 |  | 2024-11-04 | 2024-11-06 | 2024-11-15 |  |  | FALSE | FALSE
DA-RFO-1-2024-GOODS-082 | SUPPLY AND DELIVERY OF ONE (1) UNIT CARGO TRUCK (WING VAN) | AMAD | No | Competitive Bidding | 2024-10-07 | November 6-26, 2024 |  | 2024-11-14 |  | 2024-11-26 |  | 2024-11-29 | 2024-12-02 | 2024-12-09 | 6 | 13 |  | 2024-12-09 | 2024-12-18 | 2024-12-18 | 9 |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 6000000 |  |  | 5541800 |  |  | 0.076367 | 1.COA 2.RAFC 3.PCCI | 2024-11-14 |  | 2024-11-26 | 2024-11-29 | 2024-12-02 |  |  | FALSE | FALSE
DA-RFO-1-2024-GOODS-083 | SUPPLY AND DELIVERY OF ONE (1) UNIT HAULING VEHICLE | LIVESTOCK | No | Competitive Bidding | 2023-10-12 | November 6-26, 2024 |  | 2024-11-14 |  | 2024-11-26 |  | 2024-11-29 | 2024-12-03 | 2024-12-18 | 7 | 22 |  | 2024-12-18 | 2024-12-27 | 2024-12-27 | 9 |  | COMPLETED |  | Government of the Philippines (current year's budget) | 2500000 |  |  | 1708000 |  |  | 0.3168 | 1.COA 2.RAFC 3.PCCI | 2024-11-14 |  | 2024-11-26 | 2024-11-29 | 2024-12-03 |  |  | FALSE | FALSE
DA-RFO 1-2024-GOODS-085 | SUPPLY AND DELIVERY OF THREE (3) UNITS PRECISION SEEDER | RICE | No | Competitive Bidding | 2024-10-03 | November 21, 2024 to December 10, 2024 |  | 2024-11-28 |  | 2024-12-10 |  | 2024-12-13 | 2024-12-19 | 2024-12-20 |  |  |  | 2024-12-20 | 2024-12-23 | 2024-12-23 |  |  | 2024-12-26 | 2024-12-26 | Government of the Philippines (current year's budget) | 4710000 |  |  | 4620000 |  |  |  | 1.COA 2.RAFC 3.PCCI | 2024-11-28 |  | 2024-12-10 | 2024-12-13 | 2024-12-19
DA-RFO-1-2024-INFRA-029-R | REBIDDING OF LOT 1: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF ONE (1) UNIT CATTLE BREEDER HOUSE IN BRGY. CALAY-AB, STO. DOMINGO, ILOCOS SUR | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | August 28, 2024 to September 16, 2024 |  | 2024-09-04 |  | 2024-09-16 |  | 2024-09-18 | 2024-09-24 | 2024-10-08 |  |  |  | 2024-10-09 | 2024-10-28 | 2024-10-28 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 1000000 |  |  | 850061.13 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-09-04 |  | 2024-09-16 | 2024-09-18 | 2024-09-24
DA-RFO-1-2024-INFRA-029-R | REBIDDING OF LOT 2: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF TWO (2) UNITS CATTLE BREEDER HOUSE IN BRGY. NANGALISAN, BACNOTAN, LA UNION AND BRGY. LACONG, SAN GABRIEL, LA UNION | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | August 28, 2024 to September 16, 2024 |  | 2024-09-04 |  | 2024-09-16 |  | 2024-09-18 | 2024-09-24 | 2024-10-08 |  |  |  | 2024-10-09 | 2024-10-28 | 2024-10-28 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 2000000 |  |  | 1700122.26 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-09-04 |  | 2024-09-16 | 2024-09-18 | 2024-09-24
DA-RFO-1-2024-INFRA-029 | LOT 3: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF THREE (3) UNITS CATTLE BREEDER HOUSE IN BRGY. LABUAN, SAN QUINTIN, PANGASINAN, BRGY. SAN PEDRO WEST, ROSALES, PANGASINAN AND BRGY. NANCAMALIRAN WEST, URDANETA CITY, PANGASINAN | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | July 10-30, 2024 |  | 2024-07-17 |  | 2024-07-30 |  | 2024-08-01 | 2024-08-14 | 2024-08-30 |  |  |  | 2024-09-02 | 2024-09-23 | 2024-09-27 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 3000000 |  |  | 2782397.76 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-07-17 |  | 2024-07-30 | 2024-08-01 | 2024-08-14
DA-RFO-1-2024-INFRA-029 | LOT 4: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF ONE (1) UNIT CATTLE BREEDER HOUSE IN BRGY. BONGOLAN, LABRADOR, PANGASINAN | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | July 10-30, 2024 |  | 2024-07-17 |  | 2024-07-30 |  | 2024-08-01 | 2024-08-13 | 2024-08-30 |  |  |  | 2024-09-05 | 2024-09-23 | 2024-09-27 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 1000000 |  |  | 920682.35 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-07-17 |  | 2024-07-30 | 2024-08-01 | 2024-08-13
DA-RFO-1-2024-INFRA-030 | LOT 1: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF TWO (2) UNITS CATTLE FEEDLOT HOUSE IN BRGY. PORPORIKET, SUDIPEN, LA UNION AND BRGY. PALUGSI, BAUANG, LA UNION | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | July 10-30, 2024 |  | 2024-07-17 |  | 2024-07-30 |  | 2024-08-01 | 2024-08-13 | 2024-08-30 |  |  |  | 2024-09-02 | 2024-09-23 | 2024-09-23 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 2000000 |  |  | 1999888.88 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-07-17 |  | 2024-07-30 | 2024-08-01 | 2024-08-13
DA-RFO-1-2024-INFRA-030 | LOT 2: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF TWO (2) UNITS CATTLE FEEDLOT HOUSE IN BRGY. BANAOANG, MALASIQUI, PANGASINAN AND BRGY. BANAOANG, STA. BARBARA, PANGASINAN | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | July 10-30, 2024 |  | 2024-07-17 |  | 2024-07-30 |  | 2024-08-01 | 2024-08-14 | 2024-08-30 |  |  |  | 2024-09-02 | 2024-09-23 | 2024-09-23 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 2000000 |  |  | 1765305.76 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-07-17 |  | 2024-07-30 | 2024-08-01 | 2024-08-14
DA-RFO-1-2024-INFRA-030 | LOT 3: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF TWO (2) UNITS CATTLE FEEDLOT HOUSE IN BERSAMIN, ALCALA, PANGASINAN AND BRGY. POPONTO, BAUTISTA, PANGASINAN | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | July 10-30, 2024 |  | 2024-07-17 |  | 2024-07-30 |  | 2024-08-01 | 2024-08-14 | 2024-08-30 |  |  |  | 2024-09-02 | 2024-09-23 | 2024-09-27 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 2000000 |  |  | 1899912.04 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-07-17 |  | 2024-07-30 | 2024-08-01 | 2024-08-14
DA-RFO-1-2024-INFRA-031 | LOT 2: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF ONE (1) UNIT GOAT BREEDER HOUSE IN BRGY. LABUAN, SAN QUINTIN, PANGASINAN | LIVESTOCK | No | Competitive Bidding | 2024-07-02 | July 24, 2024 to August 12, 2024 |  | 2024-07-31 |  | 2024-08-12 |  | 2024-08-16 | 2024-08-28 | 2024-10-04 |  |  |  | 2024-10-07 | 2024-10-28 | 2024-10-28 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 1700000 |  |  | 1494697.47 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-07-31 |  | 2024-08-12 | 2024-08-16 | 2024-08-28
DA-RFO-1-2024-INFRA-031 | LOT 3: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF TWO (2) UNITS GOAT BREEDER HOUSE IN BRGY. PATAR, MABINI, PANGASINAN AND BRGY. SAMPALOC, BOLINAO, PANGASINAN | LIVESTOCK | No | Competitive Bidding | 2024-07-02 | July 24, 2024 to August 12, 2024 |  | 2024-07-31 |  | 2024-08-12 |  | 2024-08-16 | 2024-08-30 | 2024-10-04 |  |  |  | 2024-10-07 | 2024-10-02 | 2024-10-22 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 3400000 |  |  | 2931678.98 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-07-31 |  | 2024-08-12 | 2024-08-16 | 2024-08-30
DA-RFO-1-2024-INFRA-031 | LOT 4: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF TWO (2) UNITS GOAT BREEDER HOUSE IN BRGY. LIBAS, SAN CARLOS CITY, PANGASINAN AND BRGY. NAMDACAN, BAUTISTA, PANGASINAN | LIVESTOCK | No | Competitive Bidding | 2024-07-02 | July 24, 2024 to August 12, 2024 |  | 2024-07-31 |  | 2024-08-12 |  | 2024-08-16 | 2024-08-30 | 2024-10-04 |  |  |  | 2024-10-07 | 2024-10-02 | 2024-10-22 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 3400000 |  |  | 2957529.67 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-07-31 |  | 2024-08-12 | 2024-08-16 | 2024-08-30
DA-RFO-1-2024-INFRA-031 | LOT 5: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF TWO (2) UNITS GOAT BREEDER HOUSE IN BRGY. SAN ISIDRO, AGOO, LA UNION AND BRGY. SAN ANTONIO, ARINGAY, LA UNION | LIVESTOCK | No | Competitive Bidding | 2024-07-02 | July 24, 2024 to August 12, 2024 |  | 2024-07-31 |  | 2024-08-12 |  | 2024-08-16 | 2024-08-20 | 2024-10-04 |  |  |  | 2024-10-07 | 2024-10-21 | 2024-10-22 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 3400000 |  |  | 2973799.97 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-07-31 |  | 2024-08-12 | 2024-08-16 | 2024-08-20
DA-RFO-1-2024-INFRA-031 | LOT 6: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF ONE (1) UNIT GOAT BREEDER HOUSE IN BRGY. GUSING NORTE, NAGUILIAN, LA UNION | LIVESTOCK | No | Competitive Bidding | 2024-07-02 | July 24, 2024 to August 12, 2024 |  | 2024-07-31 |  | 2024-08-12 |  | 2024-08-16 | 2024-08-28 | 2024-10-04 |  |  |  | 2024-10-07 | 2024-10-28 | 2024-10-28 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 1700000 |  |  | 1494697.47 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-07-31 |  | 2024-08-12 | 2024-08-16 | 2024-08-28
DA-RFO-1-2024-INFRA-031 | LOT 8: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF ONE (1) UNIT GOAT BREEDER HOUSE IN BRGY. TAPAO-TIGUE, CURRIMAO, ILOCOS NORTE | LIVESTOCK | No | Competitive Bidding | 2024-07-02 | July 24, 2024 to August 12, 2024 |  | 2024-10-10 |  | 2024-10-22 |  | 2024-08-16 | 2024-08-30 | 2024-10-04 |  |  |  | 2024-10-07 | 2024-10-22 | 2024-10-22 |  |  | COMPLETED | COMPLETED | Government of the Philippines (current year's budget) | 1700000 |  |  | 1611899.08 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-10-10 |  | 2024-10-22 | 2024-08-16 | 2024-08-30
-
-
-
-
-
[25 empty] | Total Allotted Budget of Procurement Activities | 169080800 | 0 | 0 |  |  |  | 16.49%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 141206088.82 | 0 | 0
[25 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 27874711.18 | [14 empty] | 2023-06-30
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column42
ONGOING PROCUREMENT ACTIVITIES | [31 empty] | -
0.0012903
DA-RFO-1-2024-GOODS-078-N | NEGOTIATED PROCUREMENT OF SUPPLY AND DELIVERY OF ONE THOUSAND FIVE HUNDRED (1,500) HEADS READY-TO-LAY (RTL) WHITE LEGHORN AND TWO HUNDRED SEVENTY (270) BAGS CHICKEN LAYER FEEDS | LIVESTOCK | No | Competitive Bidding | N/A | January 9-21, 2025 |  | 2025-01-13 |  | 2025-01-21 | [12 empty] | FOR OPENING |  | Government of the Philippines (current year's budget) | 1686000 |  |  | 0 |  |  | - | 1.COA 2.RAFC 3.PCCI | 2025-01-13 |  | 2025-01-21 |  |  |  |  | 0
DA-RFO-1-2024-GOODS-081-N | NEGOTIATED PROCUREMENT OF SUPPLY AND DELIVERY OF ONE (1) LOT VARIOUS LOAD CARDS | AMAD | No | Competitive Bidding | N/A | January 9-21, 2025 |  | 2025-01-13 |  | 2025-01-21 | [12 empty] | FOR OPENING |  | Government of the Philippines (current year's budget) | 1841520 |  |  | 0 |  |  | - | 1.COA 2.RAFC 3.PCCI | 2025-01-13 |  | 2025-01-21 |  |  |  |  | 0
DA-RFO-1-2024-GOODS-084-R | REBIDDING OF SUPPLY AND DELIVERY OF ONE (1) LOT VARIOUS MICRONUTRIENTS | INREC | No | Competitive Bidding | 2024-09-20 | DECEMBER 5, 2024 -DECEMBER 26, 2024 |  | 2024-12-12 |  | 2024-12-26 |  | 2025-01-02 | 2025-01-08 |  | 13 | [7 empty] | ON-GOING SIGNATURE OF BAC-RES (BAC MEMBERS) |  | Government of the Philippines (current year's budget) | 2835000 |  |  | 2814750 |  |  | 0.0071429 | 1.COA 2.RAFC 3.PCCI | 2024-12-12 |  | 2024-12-26 |  | 2025-01-02 | 2025-01-08 |  | 0
DA-RFO-1-2024-GOODS-086 | LOT 1: SUPPLY AND DELIVERY OF THREE THOUSAND SIX HUNDRED NINETY-SIX (3,696) BAGS COMPLETE FERTILIZER | HVCDP | No | Competitive Bidding | 2024-11-15 | November 21, 2024 to December 10, 2024 |  | 2024-11-28 |  | 2024-12-10 |  | 2024-12-11 | 2024-12-16 | 2024-12-26 |  |  |  | 2024-12-26 | 2024-12-27 | 2024-12-27 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 6098400 |  |  | 6024480 |  |  |  | 1.COA 2.RAFC 3.PCCI | 2024-11-28 |  | 2024-12-10 |  | 2024-12-11 | 2024-12-16
DA-RFO-1-2024-GOODS-086 | LOT 2: SUPPLY AND DELIVERY OF SIX THOUSAND ONE HUNDRED ONE (6,101) BAGS CALCIUM AMMONIUM NITRATE | HVCDP | No | Competitive Bidding | 2024-11-15 | November 21, 2024 to December 10, 2024 |  | 2024-11-28 |  | 2024-12-10 |  | 2024-12-11 | 2024-12-16 | 2024-12-26 |  |  |  | 2024-12-26 | 2024-12-27 | 2024-12-27 |  |  | FOR DELIVERY |  | Government of the Philippines (current year's budget) | 6101000 |  |  | 4880800 |  |  |  | 1.COA 2.RAFC 3.PCCI | 2024-11-28 |  | 2024-12-10 |  | 2024-12-11 | 2024-12-16
DA-RFO-1-2024-GOODS-087-R | REBIDDING OF LOT 1: SUPPLY AND DELIVERY OF TWO THOUSAND EIGHT HUNDRED FIVE (2,805) BOTTLES BIOFERTILIZER | RICE | No | Competitive Bidding | 2024-05-02 | JANUARY 8, 2025 - JANUARY 28, 2025 |  | 2025-01-16 |  | 2025-01-28 | [12 empty] | FOR OPENING |  | Government of the Philippines (current year's budget) | 4207500 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.PCCI | 2025-01-16 |  | 2025-01-28
DA-RFO-1-2024-GOODS-087 | LOT 2: SUPPLY AND DELIVERY OF TWO THOUSAND (2,000) BOTTLES BIOFERTILIZER | RICE | No | Competitive Bidding | 2024-05-02 | DECEMBER 3, 2024 - DECEMBER 23, 2024 |  | 2024-12-10 |  | 2024-12-23 |  | 2024-12-26 | 2025-01-07 | [9 empty] | FOR SIGNATURE OF BAC-RES (BAC MEMBERS) |  | Government of the Philippines (current year's budget) | 4207500 |  |  | 1500000 |  |  |  | 1.COA 2.RAFC 3.PCCI | 2024-12-10 |  | 2024-12-23 | 2024-12-26 | 2025-01-07
DA-RFO-1-2024-GOODS-088-R | REBIDDING OF SUPPLY AND DELIVERY OF FIVE THOUSAND FOUR HUNDRED FOUR (5,404) SACKS OF RICE | AFD | No | Competitive Bidding | 2024-11-04 | JANUARY 7, 2025 - JANUARY 27, 2025 |  | 2025-01-14 |  | 2025-01-27 | [12 empty] | FOR OPENING |  | Government of the Philippines (current year's budget) | 7295400 |  |  | 0 |  |  |  | 1.COA 2.RAFC 3.PCCI | 2025-01-14 |  | 2025-01-27
DA-RFO-1-2024-INFRA-031 | LOT 1: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF TWO (2) UNITS GOAT BREEDER HOUSE IN BRGY. SAN ANDRES, UMINGAN, PANGASINAN AND BRGY. DICRETO, UMINGAN, PANGASINAN | LIVESTOCK | No | Competitive Bidding | 2024-07-02 | July 24, 2024 to August 12, 2024 |  | 2024-07-31 |  | 2024-08-12 |  | 2024-08-16 | 2024-11-22 | 2024-12-13 |  |  |  | 2024-12-17 | 2024-12-27 | 2024-12-27 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 3400000 |  |  | 2989394.94 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-07-31 |  | 2024-08-12 | 2024-08-16 | 2024-11-22
DA-RFO-1-2024-INFRA-031-R | REBIDDING OF LOT 7: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF ONE (1) UNIT GOAT BREEDER HOUSE IN BRGY. BAYUBAY NORTE, SAN VICENTE, ILOCOS SUR | LIVESTOCK | No | Competitive Bidding | 2024-07-02 | October 3-22, 2024 |  | 2024-10-10 |  | 2024-10-22 |  | 2024-11-05 | 2024-11-13 | 2024-11-26 |  |  |  | 2024-11-29 |  |  |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 1700000 |  |  | 1438888.88 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-10-10 |  | 2024-10-22 | 2024-11-05 | 2024-11-13
DA-RFO-1-2024-INFRA-032-R | REBIDDING OF PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF TWO (2) UNITS CATTLE FEEDLOT HOUSE IN BRGY. 19 SAN LORENZO, SAN NICOLAS, ILOCOS NORTE AND BRGY. CASILIAN, BACARRA, ILOCOS NORTE | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | DECEMBER 2-23, 2024 |  | 2024-12-09 |  | 2024-12-23 |  | 2024-12-26 | January 9-10, 2025 | [9 empty] | AWAITING PQR |  | Government of the Philippines (current year's budget) | 2000000 |  |  | 1715106.54 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-12-09 |  | 2024-12-23 | 2024-12-26 | January 9-10, 2025
DA-RFO-1-2024-INFRA-033-R | REBIDDING OF LOT 1: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF TWO (2) UNITS CATTLE BREEDER HOUSE IN BRGY. CAPARISPISAN, PAGUDPUD, ILOCOS NORTE AND BRGY. DURIPES, BACARRA, ILOCOS NORTE | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | DECEMBER 2-23, 2024 |  | 2024-12-09 |  | 2024-12-23 |  | 2024-12-26 | January 9-10, 2025 | [9 empty] | AWAITING PQR |  | Government of the Philippines (current year's budget) | 2000000 |  |  | 1713543.74 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-12-09 |  | 2024-12-23 | 2024-12-26 | January 9-10, 2025
DA-RFO-1-2024-INFRA-033 | LOT 3: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF THREE (3) UNITS CATTLE BREEDER HOUSE IN MANAOAG, PANGASINAN, BRGY. CALUNETAN, SISON, PANGASINAN AND BRGY. CACANDUNGAN, NATIVIDAD, PANGASINAN | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | NOVEMBER 5-25, 2024 |  | 2024-11-13 |  | 2024-11-25 |  | 2024-11-26 | 2024-12-04 | 2024-12-17 |  |  |  | 2024-12-17 | 2024-12-27 | 2024-12-27 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 3000000 |  |  | 2582622.48 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-11-13 |  | 2024-11-25 | 2024-11-26 | 2024-12-04
DA-RFO-1-2024-INFRA-033 | LOT 4: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF ONE (1) UNIT CATTLE BREEDER HOUSE IN BRGY. BARAOAS, CITY OF SAN FERNANDO, LA UNION | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | NOVEMBER 5-25, 2024 |  | 2024-11-13 |  | 2024-11-25 |  | 2024-11-26 | 2024-12-05 | 2024-12-18 |  |  |  | 2024-12-20 | 2024-12-27 | 2024-12-27 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 1000000 |  |  | 850104.35 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-11-13 |  | 2024-11-25 | 2024-11-26 | 2024-12-05
DA-RFO-1-2024-INFRA-034-R | REBIDDING OF LOT 1: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF ONE (1) UNIT GOAT BREEDER HOUSE IN BRGY. NAGSUROT, BURGOS, ILOCOS NORTE | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | DECEMBER 2-23, 2024 |  | 2024-12-09 |  | 2024-12-23 |  | 2024-12-26 | January 9-10, 2025 | [9 empty] | AWAITING PQR |  | Government of the Philippines (current year's budget) | 1700000 |  |  | 1455065.2 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-12-09 |  | 2024-12-23 | 2024-12-26 | January 9-10, 2025
DA-RFO-1-2024-INFRA-034 | LOT 2: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF TWO (2) UNITS GOAT BREEDER HOUSE IN BRGY. 29,4 STO. TOMAS, LAOAG CITY, ILOCO NORTE AND BRGY. BAAY, BATAC CITY, ILOCOS NORTE | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | NOVEMBER 5-25, 2024 |  | 2024-11-13 |  | 2024-11-25 |  | 2024-11-26 | 2024-12-05 | 2024-12-20 |  |  |  | 2024-12-20 | 2024-12-27 | 2024-12-27 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 3400000 |  |  | 3377478.18 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-11-13 |  | 2024-11-25 | 2024-11-26 | 2024-12-05
DA-RFO-1-2024-INFRA-034 | LOT 3: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF TWO (2) UNITS GOAT BREEDER HOUSE IN BRGY. NALASIN-CABAROAN, VIGAN CITY, ILOCOS SUR AND BRGY. LINGSAT, BANTAY, ILOCOS SUR | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | NOVEMBER 5-25, 2024 |  | 2024-11-13 |  | 2024-11-25 |  | 2024-11-26 | 2024-12-05 | 2024-12-20 |  |  |  | 2024-12-20 | 2024-12-27 | 2024-12-27 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 3400000 |  |  | 2989394.94 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-11-13 |  | 2024-11-25 | 2024-11-26 | 2024-12-05
DA-RFO-1-2024-INFRA-034 | LOT 4: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF ONE (1) UNIT GOAT BREEDER HOUSE IN BRGY. PALTOC, SAN EMILIO, ILOCOS SUR | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | NOVEMBER 5-25, 2024 |  | 2024-11-13 |  | 2024-11-25 |  | 2024-11-26 | 2024-12-05 | 2024-12-20 |  |  |  | 2024-12-20 | 2024-12-27 | 2024-12-27 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 1700000 |  |  | 1494697.47 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-11-13 |  | 2024-11-25 | 2024-11-26 | 2024-12-05
DA-RFO-1-2024-INFRA-034 | LOT 5: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF TWO (2) UNITS GOAT BREEDER HOUSE IN BRGY. FLORES, UMINGAN, PANGASINAN AND BRGY. LABUAN, UMINGAN, PANGASINAN | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | NOVEMBER 5-25, 2024 |  | 2024-11-13 |  | 2024-11-25 |  | 2024-11-26 | 2025-01-08 | [9 empty] | FOR PREPARATION OF POST-BIDDING DOCS |  | Government of the Philippines (current year's budget) | 3400000 |  |  | 3164381.52 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-11-13 |  | 2024-11-25 | 2024-11-26 | 2025-01-08
DA-RFO-1-2024-INFRA-034 | LOT 6: PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF ONE (1) UNIT GOAT BREEDER HOUSE IN BRGY. DULIG, LABRADOR, PANGASINAN | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | NOVEMBER 5-25, 2024 |  | 2024-11-13 |  | 2024-11-25 |  | 2024-11-26 | 2024-12-04 | 2024-12-20 |  |  |  | 2024-12-20 | 2024-12-27 | 2024-12-27 |  |  | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 1700000 |  |  | 1472933.89 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-11-13 |  | 2024-11-25 | 2024-11-26 | 2024-12-04
DA-RFO-1-2024-INFRA-035-R | REBIDDING OF PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF FEED MILL PROCESSING FACILITY IN BRGY. #40 BUYON, BACARRA, ILOCOS NORTE | LIVESTOCK | No | Competitive Bidding | 2024-05-31 | DECEMBER 2-23, 2024 |  | 2024-12-09 |  | 2024-12-23 |  | 2024-12-26 | January 9-10, 2025 | [9 empty] | AWAITING PQR |  | Government of the Philippines (current year's budget) | 10000000 |  |  | 8287664 |  |  |  | 1.COA 2.RAFC 3.CIAP | 2024-12-09 |  | 2024-12-23 | 2024-12-26 | January 9-10, 2025
DA-RFO-1-2024-INFRA-036 | PROVISION OF LABOR, MATERIALS, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF MULTI-PURPOSE RESEARCH AND DEVELOPMENT CENTER PHASE 1 AT DA-PREC, SUAL, PANGASINAN | PREC | No | Competitive Bidding | N/A | NOVEMBER 6-26, 2024 |  | 2024-11-14 |  | 2024-11-26 |  | 2024-11-26 | 2024-12-04 |  | 8 | [7 empty] | ON-GOING CONSTRUCTION |  | Government of the Philippines (current year's budget) | 1979361.7 |  |  | 1689520.61 |  |  | 0.14643 | 1.COA 2.RAFC 3.CIAP | 2024-11-14 |  | 2024-11-26 | 2024-11-26 | 2024-12-04 |  |  | 0
DA-RFO 1-2024-INFRA-038 | PROVISION OF LABOR, MATERIAL, EQUIPMENT RENTAL AND OTHER INCIDENTALS NEEDED FOR THE CONSTRUCTION OF VEHICLE DISINFECTION FACILITY IN DA-PREC - STA. BARBARA BREEDING CENTER (SBBC), STA. BARBARA, PANGASINAN | LIVESTOCK | No | Competitive Bidding | 2024-07-02 | NOVEMBER 26, 2024 - DECEMBER 18, 2024 |  | 2024-12-03 |  | 2024-12-18 |  | 2024-12-20 | 2025-01-08 |  | 21 | [7 empty] | FOR PREPARATION OF POST-BIDDING DOCS |  | Government of the Philippines (current year's budget) | 2000000 |  |  | 1812293.34 |  |  | 0.093853 | 1.COA 2.RAFC 3.CIAP | 2024-12-03 |  | 2024-12-18 | 2024-12-20 | 2025-01-08 |  |  | 0
[7 empty] | #DIV/0! | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 76651681.7 | 0 | 0 | 52253120.08 | 0 | 0 | 8.248%
|  | Prepared by: | [9 empty] | Recommended for Approval by: | [16 empty] | APPROVED:
|  | FEMA B. CASIL-PELAYO | [9 empty] | DENNIS I. TACTAC, ABE | [16 empty] | JOHN B. PASCUAL, DVM
|  | BAC Secretariat | [9 empty] | BAC Chairperson | [16 empty] | Head of the Procuring Entity

## Tool 1-Processing (hidden)
Summary of Information for Processing of IRPP
Indicator 1: % of Processed Procurement Activities vs Planned in terms of amount |  | #REF!
Formula | Value | Remarks
Total Amount of APP as updated | #REF!
Divide by: Total Amount of ABC of procurement activities started | #REF! | ABC of awarded + ABC of on-going procurement projects (less ABC of Failure of Bids)
Indicator 2: Average % of Variance Between Contract Amount vs Approved Budget for the Contract |  | #REF!
Particular | Value | Remarks
Total Amount of ABC of procurement activities started | #REF!
Total Contact Cost | 169306883.95
Total Variance for Each Awarded Procurement Project | #REF! | Column shall be hidden
Divide by Number of Awarded Procurement Projects | 36
Indicator 3. Timeliness on the Conduct of Procurement
|  | Indicator 3.1 Average No. of Days to commence procurement (Pre-Proc to Posting of IB) |  | Indicator 3.2: Average No. of Days to open bid proposals (Posting of IB/ to Opening of Bids) |  | Indicator 3.3: Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) |  | Indicator 3.4: Average Number of Days to Conclude Procurement (Posting of IB to Recommend Award) |  | Indicator 3.5: Average Number of Days to Issue Notice to Proceed (from Issuance of NOA to Issuance of NTP) |  | Indicator 3.6: Accumulated Number of Days for the Procurement Process (Posting of IB to NTP)
Mode of Procurement | Total No. of Activities under subject modality | Total No. of Days from PreProc to IB | Average Days from Pre-Proc to Posting of IB | Total No. of Days from IB to Opening | Average Days from Posting of IB to Opening of Bids | Total No. of Days Opening to Recommend Award) | Average Days from Opening of Bids to Recommend Award | Total No. of Days from Posting of IB to Recommend Award | Average Days from Posting of IB to Recommend Award | Total No. of Days from Issuance of NOA to Issue NTP | Average Days from NOA to NTP | Total No. of Days from Posting of IB to Issue NTP | Average Days from Posting of IB to NTP
Competitive Bidding | 49 | 0 | 0 | 0 | 0 | 219 | 4.4694 | 0 | 0 | 85 | 1.7347 | 0 | 0
Limited Source Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Direct Contracting | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Repeat Order | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.1 Two Failed Biddings | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.2 Emergency Cases | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.3 Take-Over of Contracts | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.5 Agency-to-Agency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.7 Highly Technical Consultants | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.9 - Small Value Procurement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.11 NGO Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.12 Community Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Emergency Procurement under Bayanihan Act | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Alternative Method | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 49 | 0 | 0 | 0 | 0 | 9.5217 | 4.4694 | 0 | 0 | 3.6957 | 1.7347 | 0 | 0
*formula for days interval for each procurement activity for each indicator are embedded in the PMR.
Indicator 4. Percentage of Amount and Volume by Tender and Award of Procurement Activities per Mode of Procurement
Mode of Procurement | Total No. of Activities | Total Number of Awarded | Total ABC | Total Contract Cost | %Vol of Awarded | %ABC of Awarded | Total Number of Failed | ABC of Failed
Competitive Bidding | 49 | 36 | 200580200 | 169306883.95 | 73.47% | 84.41% | 0 | 0
Limited Source Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Direct Contracting | 0 | 0 | 0 | 0 |  |  | 0 | 0
Repeat Order | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.2 Emergency Cases | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.3 Take-Over of Contracts | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.5 Agency-to-Agency | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.7 Highly Technical Consultants | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.9 - Small Value Procurement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.11 NGO Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.12 Community Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 | 0 | 0 |  |  | 0 | 0
Emergency Procurement under Bayanihan Act | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Alternative Method | 0 | 0 | 0 | 0 |  |  | 0 | 0
Total | 49 | 36 | 200580200 | 200580200 | 73.47% | 84.41% | 0 | 0
Total for Alternative Mode of Procurement | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
Indicator 5: Accumulated No. of Days for On-going Procurement Activities
Timeline | No. of Procurement Activities | %
Exceeds 180 days | 0 | 0%
Within 91 to 180 days | 0 | 0%
Within 45 to 90 days | 0 | 0%
Within 0 to 44 days | 0 | 0%
Total | 0 | 0%
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 6. Distribution of On-going, Awarded, and Failed procurement Activities
Status | No. of Procurement Activities | % by No. of Procurement of Activities | ABC Amount of Activities | % by ABC | Contract Cost | Contract/ABC | Variance
Awarded | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Completed | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Failed | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Ongoing | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Total | 0 | 0% | 0 | 0% | 0 | #DIV/0! | #DIV/0!
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 7a: % of Number of Procurement activities conducted under early procurement |  |  | 0%
Indicator 7b: % of ABC of Procurement activities conducted under early procurement |  |  | 0%
Particular | No. of Procurement Activities | ABC Amount of Activities
Under EPA | 0 | 0
Regular Procurement | 49 | 207220600
Total | 49 | 207220600
Indicator 8a: Percentage of Number of Awarded Contracts under EPA |  |  | 0%
Indicator 8b: Percentage of Contract Cost of EPA against the total ABC under EPA |  |  | 0%
Formula | No. of Procurement Activities | Amount of ABC Procurement Activities | Contract Cost of Procurement Activities | Percentage Variance
Total Contracts Awarded under EPA* | 0 | 0 | 0 | 0%
Total Contracts Completed under EPA* | 0 | 0 | 0 | 0%
Total Failed Bid under EPA* | 0 | 0 | 0 | 0%
Total Ongoing Activities under EPA* | 0 | 0 | #VALUE! | #VALUE!
Total Procurement Activities under EPA | 0 | 0 | #VALUE!
To compute for the total, a separate sheet may be created of the PMO may simply filter the cells to capture the total number.
Indicator 9: Stages where failure of bidding are encountered
Particular | No. of Procurement Activities | Amount of ABC | Vol. % | Amount %
Invitation To Bid | 0 | 0 | 0% | 0%
Pre-bidding Conference | 0 | 0 | 0% | 0%
Opening of Bids | 0 | 0 | 0% | 0%
Bid Evaluation | 0 | 0 | 0% | 0%
Post-Qualification | 0 | 0 | 0% | 0%
BAC Resolution | 0 | 0 | 0% | 0%
Award | 0 | 0 | 0% | 0%
Cancelled | 0 | 0 | 0% | 0%
TOTAL | 0 | 0

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget)
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget)
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget)
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution
Failed under Section 35.1 (b) |  | BAC Resolution
Failed under Section 35.1 (c) |  | Award
Failed under Section 41 (b) |  | Cancelled
Failed under Section 41 (c)
Contract was extended
Contract was renewed
Cancelled
Others, please encode directly on the cell